DECISION PAPER

TO: MRMBERS OF THE NELSON COUNTY BOARD OF EDUCATION

FROM: Charles Thompson, Construction and Maintenance Liaison/DPP

CC: Dr. Janice Lantz, Superintendent

SUBJECT: Change Order #51 for Foster Height’s renovation

DATE: June 15, 2010

ISSUE: Poor soil was found in the parking area during renovation at Foster Heights. The cost for the necessary undercut and fill was $2,170.82 from Filcon Construction LLC. After a previous credit of $1,882.61 is deducted a final add of $348.01 to Filcon resulted.

RECOMMENDATION: Approval of Change Order #51 for the Foster Height’s renovation

RECOMMENDED MOTION: I move that the nelson county board of education approve Change Order #51 for Foster Height’s renovation.