## Sheet1
KDE APPROVAL DATE: MAY 2023 | [6 empty] | DFP REVISIONS
TODD COUNTY SCHOOLS
DISTRICT FACILITY PLAN
NEXT DFP DUE: MAY 2027
PLAN OF SCHOOL ORGANIZATION
1. | Current Plan |  |  | PS-5, 6-8, 7-12, 9-12
2. | Long Range Plan |  |  | PS-5, 6-8, 7-12, 9-12
SCHOOL CENTERS | [5 empty] | Status |  | Current Organization |  |  | EOY 2018-19 Student Enrollment / Capacity
1. | Secondary
| a. | Todd County Central High School (A1) |  |  |  | Permanent |  | 9-12 Center |  |  | 556/414
| b. | Horizons Alternative School (A5) |  |  |  | Permanent |  | 7-12 Center |  |  | 17
2. | Middle
| a. | Todd County Middle School (A1) |  |  |  | Permanent |  | 6-8 Center |  |  | 497/467
3. | Elementary
| a. | North Todd Elementary School (A1) |  |  |  | Permanent |  | PS-5 Center |  |  | 347/483
| b. | South Todd Elementary School (A1) |  |  |  | Permanent |  | PS-5 Center |  |  | 457/596
CAPITAL CONSTRUCTION PRIORITIES (Schedule after the 2024 Biennium)
2c. | Major renovation/additions of educational facilities; including expansions, kitchens, cafeterias, libraries,
| administrative areas, auditoriums, and gymnasiums. | [8 empty] | Eff. % | Cost Est.
| 1. | Todd County Central High School | [5 empty] | 94667 | sf.
|  | Over 30 Years - 1963, 1968, 1996 | [5 empty] | 72167 | sf. |  | 12324294
Major Renovation to include:
|  | SITEWORK | Replace site lighting, install roadway, replace parking lots, replace pedestrian paving, replace site development
|  | SUPERSTRUCTURE | Replace damaged superstructure, replace exterior stairs and rails, replace damaged exterior walls
|  | ROOFING | Replace roof, gutters, and downspouts
|  | DOORS | Replace exterior doors, replace industrial doors, replace interior doors
|  | WINDOWS | Replace exterior windows
|  | INTERIOR FINISHES | Replace wall finishes, replace floor finishes, replace ceiling finishes
|  | MECHANICAL | Replace primary HVAC pumps and piping, replace chillers, replace controls and instrumentation, replace exhaust ventilation systems
|  | ELECTRICAL | Replace lighting equipment, replace clock and program system, replace fire alarm system, replace security system, replace exit and emergency light systems, replace emergency power and generation systems, replace intercommunications and pagaing systems, install battery backup for servers, replace electrical distribution systems, replace wheelchair lifts in gym and auditorium
|  | PLUMBING | Replace hot water boilers, replace plumbing fixtures, replace domestic water distribution piping, replace domestic water heaters, replace water supply, replace rain water drainage, replace gas supply system
|  | SEWAGE | Replace sanitary sewer, replace storm sewer, replace damaged sanitary waste piping
|  | FIXED EQUIPMENT | Replace damaged partitions, replace fittings, replace damaged stairs, install ADA signage, renovate locker rooms, replace gym bleachers, renovate culinary arts spaces
|  | Under 30, Over 15 Years - 1999, 2000, 2006 | [5 empty] | 22500 | sf. |  | 3842430
Major Renovation to include:
|  | SITEWORK | N/A
|  | SUPERSTRUCTURE | Replace roofing, gutters, and downspouts
|  | DOORS | Replace damaged interior and exterior doors, replace damaged industrial doors
|  | WINDOWS | N/A
|  | INTERIOR FINISHES | Replace damaged ceiling finishes, replace damaged wall finishes
|  | MECHANICAL | N/A
|  | ELECTRICAL | N/A
|  | PLUMBING | N/A
|  | SEWAGE | N/A
|  | FIXED EQUIPMENT | Replace damaged partitions, replace damaged fittings
| 2. | Todd County Middle School | [5 empty] | 64578 | sf. |  | 9274371
Over 30 Years - 1978, 1991, 1995
Major Renovation to include:
|  | SITEWORK | Replace site lighting, install roadway, replace parking lots, replace pedestrian paving, replace site development, install garbage area and structure
|  | SUPERSTRUCTURE | Repair damaged exterior walls
|  | ROOFING | Replace roof, gutters, downspouts
|  | DOORS | Replace exterior doors, replace interior doors
|  | WINDOWS | Replace exterior windows
|  | INTERIOR FINISHES | Replace wall finishes, repair/replace floor finishes, repair/replace ceiling finishes
|  | MECHANICAL | Replace exhaust ventilation systems
|  | ELECTRICAL | Replace lighting equipment, replace clock and program system, replace electrical service and distribution, replace emergency power and generation systems
|  | PLUMBING | Replace hot water boilers with piping, replace plumbing fixtures, replace domestic water distribution piping, replace sprinkler system piping, install sink in workroom
|  | SEWAGE | Replace sanitary sewer, replace storm sewer, repair sanitary waste piping
|  | FIXED EQUIPMENT | Repair partitions, replace fittings, repair stairs and rails, replace kitchen equipment, install secure entrance, provide ADA signage, replace gymnasium bleachers, renovate band room and support spaces, expand media center, install battery backup for servers
|  | Construct: | 6 | resource | 375 | sf. |  | 2250 | sf. | 71% | 1122338.0282
|  |  | 1 | Media Center expansion | 1016 | sf. |  | 1016 | sf. | 71% | 506797.9718
|  |  | 1 | FRC | 300 | sf. |  | 300 | sf. | 71% | 149645.0704
|  |  | 1 | vocal music classroom | 900 | sf. |  | 900 | sf. | 71% | 448935.2113
|  |  | 1 | custodial receiving | 250 | sf. |  | 250 | sf. | 71% | 124704.2254
| 3. | North Todd Elementary School | [5 empty] | 64939 | sf.
|  | Over 30 Years - 1988 | [5 empty] | 48333 | sf. |  | 7941345
Major Renovation to include:
|  | SITEWORK | Replace site lighting, install roadway, replace parking lots, replace pedestrian paving, replace site development
|  | SUPERSTRUCTURE | Replace damaged superstructure, replace damaged exterior walls
|  | ROOFING | Replace roof, gutters, and downspouts
|  | DOORS | Replace exterior doors, replace industrial doors, replace interior doors
|  | WINDOWS | Replace exterior windows
|  | INTERIOR FINISHES | Replace wall finishes, replace floor finishes, replace ceiling finishes
|  | MECHANICAL | Replace primary HVAC pumps and piping, replace packaged units, replace controls and instrumentation, replace exhaust ventilation systems
|  | ELECTRICAL | Replace lighting equipment, replace clock and program system, replace fire alarm system, replace security system, replace exit and emergency light systems, replace emergency power and generation systems, replace intercommunications and pagaing systems, install battery backup for servers, replace electrical distribution systems
|  | PLUMBING | Replace water heaters and boilers, replace plumbing fixtures, replace domestic water distribution piping, replace domestic water heaters, replace water supply, replace rain water drainage, replace gas supply system
|  | SEWAGE | Replace sanitary sewer, replace storm sewer, replace damaged sanitary waste piping, connect wastewater to Elkton water treatment plan
|  | FIXED EQUIPMENT | Replace fittings, install ADA signage, install secure entrance, install secure perimeter fencing, install covered entryways
|  | Under 30, Over 15 Years - 1998, 2009 | [5 empty] | 16606 | sf. |  | 2384871
Major Renovation to include:
|  | SITEWORK | N/A
|  | SUPERSTRUCTURE | Replace roofing, gutters, and downspouts
|  | DOORS | Replace damaged interior and exterior doors, replace damaged industrial doors
|  | WINDOWS | N/A
|  | INTERIOR FINISHES | Replace damaged ceiling finishes, replace damaged wall finishes
|  | MECHANICAL | N/A
|  | ELECTRICAL | N/A
|  | PLUMBING | N/A
|  | SEWAGE | N/A
|  | FIXED EQUIPMENT | Replace damaged partitions, replace damaged fittings, install new garbage area and structure, replace damaged kitchen equipment
| 4. | South Todd Elementary School | [5 empty] | 64939 | sf.
|  | Over 30 Years - 1988 | [5 empty] | 48333 | sf. |  | 6941345
Major Renovation to include:
|  | SITEWORK | Replace site lighting, install roadway, replace parking lots, replace pedestrian paving, replace site development
|  | SUPERSTRUCTURE | Replace damaged superstructure, replace damaged exterior walls
|  | ROOFING | Replace roof, gutters, and downspouts
|  | DOORS | Replace exterior doors, replace industrial doors, replace interior doors
|  | WINDOWS | Replace exterior windows
|  | INTERIOR FINISHES | Replace wall finishes, replace floor finishes, replace ceiling finishes
|  | MECHANICAL | Replace primary HVAC pumps and piping, replace packaged units, replace controls and instrumentation, replace exhaust ventilation systems
|  | ELECTRICAL | Replace lighting equipment, replace clock and program system, replace fire alarm system, replace security system, replace exit and emergency light systems, replace emergency power and generation systems, replace intercommunications and pagaing systems, install battery backup for servers, replace electrical distribution systems
|  | PLUMBING | Replace water heaters and boilers, replace plumbing fixtures, replace domestic water distribution piping, replace domestic water heaters, replace water supply, replace rain water drainage, replace gas supply system
|  | SEWAGE | Replace sanitary sewer, replace storm sewer, replace damaged sanitary waste piping
|  | FIXED EQUIPMENT | Replace fittings, install ADA signage, install secure entrance, install secure perimeter fencing, install covered entryways
|  | Under 30, Over 15 Years - 1998, 2009 | [5 empty] | 16606 | sf. |  | 2384871
Major Renovation to include:
|  | SITEWORK | N/A
|  | SUPERSTRUCTURE | Replace roofing, gutters, and downspouts
|  | DOORS | Replace damaged interior and exterior doors, replace damaged industrial doors
|  | WINDOWS | N/A
|  | INTERIOR FINISHES | Replace damaged ceiling finishes, replace damaged wall finishes
|  | MECHANICAL | N/A
|  | ELECTRICAL | N/A
|  | PLUMBING | N/A
|  | SEWAGE | N/A
|  | FIXED EQUIPMENT | Replace damaged partitions, replace damaged fittings, install new garbage area and structure, replace damaged kitchen equipment
| 5. | Horizons Alternative School | [5 empty] | 5253 | sf. |  | 1508819
Over 30 Years - 1960, 1986
Major Renovation to include:
|  | SITEWORK | Replace site lighting, install roadway, replace parking lots, replace pedestrian paving, replace site development
|  | SUPERSTRUCTURE | Replace damaged exterior walls
|  | ROOFING | Replace roof, gutters, and downspouts
|  | DOORS | Replace exterior doors, replace industrial doors, replace interior doors
|  | WINDOWS | Replace exterior windows
|  | INTERIOR FINISHES | Replace wall finishes, replace floor finishes, replace ceiling finishes
|  | MECHANICAL | Replace exhaust ventilation systems
|  | ELECTRICAL | Replace lighting equipment, replace clock and program system, replace fire alarm system, replace security system, replace exit and emergency light systems, replace emergency power and generation systems, replace intercommunications and pagaing systems, install battery backup for servers, replace electrical distribution systems
|  | PLUMBING | Replace water heaters and boilers, replace plumbing fixtures, replace domestic water distribution piping, replace domestic water heaters, replace water supply, replace rain water drainage, replace gas supply system
|  | SEWAGE | Replace sanitary sewer, replace storm sewer, replace damaged sanitary waste piping
|  | FIXED EQUIPMENT | Replace fittings, install ADA signage, install secure entrance, install new garbage area and structure, replace damaged partitions, replace kitchen equipment
2d. | KERA Strands New Additions: Preschool, SBDM Office & Conf., Fam. Res. | [8 empty] | Eff. % | Cost Est.
| 1. | Todd County Central High School | [8 empty] | 150000
Replace/Modernize hard-wired technology connections.
| 2. | Todd County Middle School | [8 empty] | 100000
Replace/Modernize hard-wired technology connections.
| 3. | North Todd Elementary School | [8 empty] | 100000
Replace/Modernize hard-wired technology connections.
| 4. | South Todd Elementary School | [8 empty] | 100000
Replace/Modernize hard-wired technology connections.
| 5. | Horizons Alternative School | [8 empty] | 50000
Replace/Modernize hard-wired technology connections.
CAPITAL CONSTRUCTION PRIORITIES (Regardless of Schedule)
3. | Construction of non-educational additions or expansions including kitchen, cafeterias, administrative areas, auditoriums, and gymnasiums.
| 1. | Todd County Central High School | [5 empty] | 94667 | sf.
|  | Construct: | 1 | HB 678 (2022) Health & Wellness Center | 10000 | sf. |  | 10000 | sf. |  | 3059000
|  |  | 1 | HB 678 (2022) Restroom, concessions, and press box facilities at baseball field | 1500 | sf. |  | 1500 | sf. |  | 458850
|  |  | 1 | HB 678 (2022) Hitting facility for baseball/softball | 1500 | sf. |  | 1500 | sf. |  | 458850
|  |  | 1 | HB 678 (2022) Archery facility | 4000 | sf. |  | 4000 | sf. |  | 1223600
| 2. | Todd County Middle School | [5 empty] | 64578 | sf.
|  |  | 1 | HB 678 (2022) Outdoor athletic facility with baseball, softball, football field | [6 empty] | 4000000
4. | Management support areas; Construct, acquisition, or renovation of central offices, bus garages, or central stores
[10 empty] | Eff. % | Cost Est.
| 1. | Central Office | [5 empty] | 8151 | sf. |  | 1170606
Under 30 Years, Over 15 Years - 2006
Major Renovation to include:
|  | SITEWORK | N/A
|  | SUPERSTRUCTURE | N/A
|  | ROOFING | Replace roof, gutters, and downspouts
|  | DOORS | Replace damaged exterior doors, Replace damaged interior doors
|  | WINDOWS | Replace damaged exterior windows
|  | INTERIOR FINISHES | Repair damaged wall finishes, replace damaged floor finishes, replace damaged ceiling finishes
|  | MECHANICAL | Replace exhaust ventilation systems
|  | ELECTRICAL | Replace lighting equipment, install battery backup for servers
|  | PLUMBING | Replace water heaters and boilers
|  | SEWAGE | N/A
|  | FIXED EQUIPMENT | Install ADA signage
| 2. | Maintenance & district storage bldg | [5 empty] | 4000 | sf.
|  | Demolish existing facility | [8 empty] | 400000
|  | Construct: | Maintenance and District Storage Facility |  |  |  |  | 6000 | sf. | 74% | 1530243.2432
| 3. | Bus Garage | [5 empty] | 4000 | sf.
|  | Demolish existing facility | [8 empty] | 400000
|  | Construct: | Bus Garage; Replace fuel pumps and management system |  |  |  |  | 6000 | sf. | 74% | 2304405.4054
DISTRICT NEED | [10 empty] | 64460321.1557
5. | Discretionary Construction Projects; Functional Centers; Improvements by new construction or renovation.
Estimated Costs of these projects will not be included in the FACILITY NEEDS ASSESSMENT TOTAL.
| 1. | Annex Building | [5 empty] | 15250 | sf. |  | 2190129
Major Renovation to include: repair/replacement of interior and exterior doors, industrial doors, roofing, partitions, fittings, wall finishes, floor finishes, ceiling finishes, plumbing fixtures, packaged air conditioning units, controls and instrumentation, lighting equipment, intercommunications and paging, clock and program systems, emergency power and generation systems, and pedestrian paving; install solar panels and associated infrastructure.
| 2. | Todd County Middle School
|  | Construct: | 1 | Outdoor Learning Environment and Barn for Agriculture Science | 4043 | sf. |  | 4043 | sf. |  | 1236753.7
| 3. | Renovate restroom, concessions, and press box facilities at football stadium | [8 empty] | 500000
| 4. | Re-construct baseball field to re-orient to new concessions building | [8 empty] | 750000
| 5. | Greenhouse replacement at high school | [8 empty] | 357500
| 6. | Renovate playground at North Todd Elementary | [8 empty] | 253500
| 7. | Renovate playground at South Todd Elementary | [8 empty] | 253500