## Page 1
KENTUCKY DEPARTMENT OF EDUCATION | [16 empty] | BG-1
702 KAR 4:160 | [16 empty] | PROJECT APPLICATION FORM
PROJECT IDENTIFICATION | [5 empty] | Initial: | xx |  |  | Revised: |  |  |  |  | Emergency:
[6 empty] | Date: | 2023-06-09
District |  |  |  |  | District |  |  |  | Facility | [6 empty] | School
Name: | Bellevue Independent |  |  |  | Code: | 032 |  |  | Name: | Grandview Elementary | [5 empty] | Code: | 010
Grade Level Served: |  |  |  | PS-5 |  |  |  |  | Current Student Capacity: | 450 | District Facilities Plan Date: |  |  |  |  | Dec. 2024
Project Name: |  |  | Grandview Elementary- Gym Addition and HVAC Renovation | [8 empty] | Building ID Number:
REH Project #372-922
Project Site Physical Address:
|  |  |  | 500 Grandview Ave |  |  |  |  | Bellevue
|  |  |  | Street |  |  |  |  | City
Construction Delivery Method: |  |  |  |  | General Contractor |  |  |  | Construction Mgr. |  |  |  | Guaranteed Energy Savings Contract
District's Procurement Standard: |  |  |  |  | Model Procurement |  |  |  | Bid Law
[5 empty] | (KRS 45A) |  |  |  | (KRS 424.260)
1. DESCRIPTION AND SCOPE OF PROPOSED PROJECT
A. | Check and complete the applicable items:
|  | 1. | New Building
|  | 2. | Addition
|  | 3. | Major Renovation (Describe) |  |  |  | See description below.
|  | 4. | New Relocatable Classroom |  |  |  |  | Number | [5 empty] | Size
|  | 5. | Equipment/Furnishings Procurement (Describe)
|  | 6. | Minor Project (Describe)
|  | 7. | Site (Complete the Following)
|  |  | a. | New Site Acquisition | [5 empty] | Expansion | [5 empty] | Number of Acres
|  |  | b. | A site has been acquired in accordance with 702 KAR 4:050 requirements.
|  |  | c. | Location
|  |  | d. | Proposed site currently owned by District |  |  |  |  | Yes |  |  |  | No | If no, list site owner:
B. | Compliance with 702 KAR 4:180 and 702 KAR 4:160
This application is being submitted for (refer to current District Facility Plan):
|  | 1. | Priority Category: |  |  |  |  | 2C.2.2, 2C.2.3, 5.3.3
|  | 2. | Discretionary Item Number:
|  | 3. | Minor project not listed on Facility Plan:
C. | Provide a complete narrative of the proposed project.
This project consists of a total renovation of the existing Grandview Elementary School. It includes finishes for MEP upgrades, as well as an addition of a gymnasium, stage, and athletic space and full renovation of the cafeteria into a designated space. The project will be phased in over a year and a half and will have a significant amount of abatement and the need to work around an active school schedule.
D. | Proposed work related to the project but excluded from the scope of this BG1:

## Page 2
KENTUCKY DEPARTMENT OF EDUCATION | [11 empty] | BG-1
702 KAR 4:160 | [11 empty] | PROJECT APPLICATION FORM
SCHOOL DISTRICT: |  |  |  | Bellevue |  | Initial: | xx |  | Revised: |  | BG#
[6 empty] | Date: | 2023-06-09
PROJECT NAME: |  |  | Grandview Elementary- Gym Addition and HVAC Renovation
REH Project #372-922
II. |  | PROPOSED PLAN TO FINANCE APPLICATION
|  | A. Statement of Probable Costs: | [6 empty] | B. Funds Available:
| 1. Total Construction Cost** |  |  |  | 11118000 |  |  |  | 1. SFCC Cash Req.
| 2. Architect/Engineer Fee |  |  |  | 764918.4 |  |  |  | 2. SFCC Bond Req.
| 3. Construction Manager Fee | [7 empty] | 3. SFCC Bond Sale
| 4. Bond Discount | [7 empty] | 4. Local FSPK Bond Sale
| 5. Fiscal Agent Fee | [7 empty] | 5. Local Gen. Fund Bond Sale
| 6. Construction Contingencies |  |  |  | 582282 |  |  |  | 6. Cash - General Fund
| 7. Site Acquisition | [7 empty] | 7. Cash - Capital Outlay
| 8. Equipment/Furnishings | [7 empty] | 8. Cash - Building Fund
| 9. Equipment/Computers | [7 empty] | 9. Cash - Inv. Earnings
| 10. Technology Network Sys. (KETS) | [7 empty] | 10. KETS
| 11. Other* |  | Abatement |  | 125000 |  |  |  | 11. KYTC Reimbursement
| 12. Other* |  | Commissioning |  | 30000 |  |  |  | 12. Other* | SFCC Grant |  | 12726200
| 13. Other* |  | Special Testing |  | 40000 |  |  |  | 13. Other*
| 14. Other* |  | Geotech |  | 25000 |  |  |  | 14. Other*
| 15. Other* |  | Repro/adv/reimb |  | 9000 |  |  |  | 15. Other*
| 16. Other* |  | Sanitary Sewer Camera |  | 4000 |  |  |  | 16. Other*
| 17. Other* |  | TAB |  | 10000 |  |  |  | 17. Other*
| 18. Other* |  | Permits |  | 8000 |  |  |  | 18. Other*
| 19. Other* |  | Topo |  | 10000 |  |  |  | 19. Other*
| Total Project Cost |  |  |  | 12726200.4 |  |  |  | Total Funds Available
| *Define | [7 empty] | *Define
THE ABOVE INFORMATION IS A STATEMENT OF PROBABLE COST AND FUNDS AVAILABLE AND IS REQUIRED TO BE REVISED TO
CORRESPOND TO ACTUAL BIDS RECEIVED PRIOR TO THE SIGNING OF CONSTRUCTION CONTRACTS.
TO BE COMPLETED ON INITIAL & REVISED APPLICATION: The signing of this financial document certifies the above
stated funds are available and designated for this project during this fiscal year.
[5 empty] | Superintendent |  |  |  |  | Date
[5 empty] | Finance Officer |  |  |  |  | Date
[5 empty] | Chairman |  |  |  |  | Date
NOTE: Any district anticipating the financing of this and/or other projects in a combined school revenue Bond should
discuss the financing with the Director/Branch Manager, KDE - District Financial Management.
TO BE COMPLETED ON INITIAL APPLICATION:
This building project application is approved by the KDE - District Facilities Branch indicating compliance with current
District Facility Plan or minor project under 702 KAR 4:180.
Comments:
Branch Manager, KDE - District Facilities Branch | [11 empty] | Date
TO BE COMPLETED ON INITIAL & REVISED APPLICATION: | [7 empty] | TO BE COMPLETED ON INITIAL APPLICATION:
Tentative financial approval based upon information | [7 empty] | This building project application is hereby approved according
provided to this office in support of projected cost. | [7 empty] | to the conditions outlined in the application. Proceed in
accordance with the attached submittal checklist.
Comments:
Comments:
KDE - District Financial Management | [7 empty] | KDE - District Support
Date: | [7 empty] | Date: