# OCS Construction Report

July 2023

## OCHS Foundation Repairs & Roof Project Ph. 3 (Remaining Bldg. 1 – Roof Replacement Gym and Auditorium

Conditional Approval for construction received, Roof tear-off and temp roof installation ongoing.

Construction schedule:

| Construction commencement | Weather permitting gym access will be restored prior to the first day of school |
| --- | --- |
| Substantial Completion | January 2024 |

## SOHS Phase II – Fieldhouse Renovation & Site Improvements

| Project closeout in progress. |  |  |
| --- | --- | --- |
| BG-4 submitted for approval tonight. |  |  |

## SOHS Major Renovation Phase 3 – Fire Alarm Upgrades

Project nearing completion – working with ADT to tie into monitoring system.

Pre-punch is in progress.

## East Oldham M.S. Classroom Addition and Roof Replacement

| Project closeout in progress. |  |
| --- | --- |
| BG-1 Project Reconciliation | August 2023 |

## Athletic Stadium and Field Improvements at Various Schools Bid Package A (SOHS Field Lighting), Bid Package B (SOHS Concession Stand / SOHS & OCHS Stadium Upgrades), and Bid Package C (Turf Replacement OCHS & NOHS)

SOHS Field Lighting (Bid Package A):

Lights have been installed and are operational.

Closeout in process.

| BG-4 | August 2023 |
| --- | --- |

SOHS Concession Stand / SOHS & OCHS Stadium Upgrades:

OCHS

SOSH Concession Stand & Ticket Booth & Track Improvements / OCHS Ticket Booth & Track Improvements (Bid Package B):

OCHS Ticket Booth:

Footing and foundations complete, electrical rough-ins complete.

CMU and Brickwork complete, Roof structure installed, masonry columns complete.

Metal canopy installed.

SOHS Concession Stand:

Rock removal complete, concrete foundation walls complete, steel is on site

SOHS Scoreboard:

Foundations drilling underway.

SOHS Ticket Booth:

CMU complete; brickwork complete, roof trusses installed.

Turf Replacement at NOHS & OCHS (Bid Package C)

NOHS Turf Replacement:

Grass turf removal complete.

Grading of fields is complete.

Subgrade drainage complete.

Top rock installed.

Field event pits and runway nearing completion.

OCHS Turf Replacement:

Drainage complete, final grading complete, gravel sub-surface complete, sideline fencing complete, concrete curbs at jump-pits complete. Turf installation started.

Schedule for Bid Packages A, B, & C

| Substantial Completion | SOHS | Field Lighting |  | April 2023 |  |
| --- | --- | --- | --- | --- | --- |
| Substantial Completion | OCHS | Turf Replacement |  | July 16, 2023 (MFG Delay) |  |
| Substantial Completion | SOHS | Ticket Booth & Scoreboard |  | July 31, 2023 (Expected Delay) |  |
| Substantial Completion | OCHS | New Ticket Booth & Entry Plaza |  | July 31, 2023 (Expected Delay) |  |
| Substantial Completion | NOHS | Turf Replacement |  | August 18, 2023 |  |
| Substantial Completion | OCHS | Track & Field Improvements |  | August 28, 2023 |  |
| Substantial Completion | SOHS | Home & Visitor Bleachers |  | March 6, 2024 |  |
| Substantial Completion | SOHS | Track Improvements |  | June 13, 2024 |  |

## OCHS & Buckner ES Emergency Boiler Replacement

- OCHS:	Boiler #1 - Replacement Completed 11/20.  Boiler #2 - Completed 01/22.

- Buckner ES: Boiler # 1 - Replacement Complete 10/19/22. Boiler #2 To be installed in coordination with BES Mechanical Room Upgrades 90% complete.

## OC Preschool – Expansion and Roof Replacement

Tentative Schedule

| DDs | July 2023 |
| --- | --- |
| CDs | August 2023 |
| Bids/Contracts | October 2023 |
| Construction starts on addition | October 2023 |
| Interior Renovation starts | January 2024 |
| Substantial Completion | June 2024 |

## Buckner Mechanical Room Upgrades

| Anticipated Substantial Completion | August 30, 2023 |
| --- | --- |

## District Wide Landscape and Site Improvements

- Design Team selected.

- Notice to Proceed received.

- Contract B101 being processed.

- In-House Landscaping & Site Improvement under way.

## OCHS HVAC Upgrades

| Exterior door installation complete, including keying to school system. Cooling tower has been set, piping and hookups within mechanical room ongoing. Boiler inspection on chilled/hot water piping completed, insulation started. |  |
| --- | --- |
| Substantial Completion: | August 1, 2023 |

## NOHS Soffit, Roof, and Metalwork Repairs

Recommendation to reject bid, revise scope and re-bid submitted tonight

Tentative Schedule

| Bid/Contracts | TBD |
| --- | --- |
| Substantial Completion | TBD |

## Career Tech Renovation at OCMS

Tentative Schedule:

| Re-Bid/Contracts | September 2023 |
| --- | --- |
| Substantial Completion | June 2024 |

## Career Tech Addition at SOMS

Tentative Schedule:

| DDs | August 2023 |
| --- | --- |
| BG-2, BG-3, CDs | October 2023 |
| Bid/Contracts | November 2023 |
| Substantial Completion | TBD |

## Site Accessibility at Various Elementary Schools

Centerfield:

- Concrete sidewalk from log cabin complete

- Play surface grading complete, equipment installed

- Retaining wall and steps nearing completion, sidewalk complete.

- Play surface near log cabin installed.

- Anticipated completion at all sites: August 8, 2023

Kenwood

- Existing playground equipment removed, curb installed, sub-surface drainage complete, grading complete, rock installation ongoing pending change order review tonight and equipment delivery.

Buckner

- Rough grading ongoing, curbs complete, mulch placed.

Camden Station

- Mobilization started

- Shade canoy delivery/installation to be completed prior to the first day of school.

## Field #2 Renovations at OCHS & NOHS

Design ongoing

Tentative Schedule:

| DDs | July 2023 |
| --- | --- |
| CDs | August 2023 |
| Bid/Contracts | September 2023 |
| Construction Commencement | November 2023 |
| Substantial Completion | July 2023 |

## SOHS Shop Renovation

Welding Shop

Demolition complete, electrical rough-in above ceiling complete, wall patching complete

Core drilling for new waterlines and rough-ins completed.

Spray on acoustic ceiling treatment complete, painting ongoing

Main Lobby Restrooms and corridor

Demolition complete.

Painting in corridor complete, ongoing in restrooms

Ceiling grid installed in restrooms

## Central Office Interior Renovations & Site Improvements

| Design on hold pending Board approval of two story addition. |  |
| --- | --- |
| Anticipated Schedule (w/ addition): |  |
| BG-2, BG-3, DDs | June 2023 |
| CDs | September 2023 |
| Bid/Contracts | October 2023 |
| Work Commencement | December 2023 |
| Substantial Completion | December 2024 |

# Minor project Overview

Interior Renovations or Non-Bonded / “Cash” projects.  Schedules are anticipated and subject to major project scheduling priority, school holidays and available resources.

## Former Liberty Asbestos Abatement & Demolition

On hold pending summer construction schedule.

## Flooring Replacement at Various Schools

- Proposal requests for NOHS 600 wing received – work to be completed Fall Break.

- Proposal for counselors’ office for Goshen Elementary School received –scheduled to begin this week.

- Proposal for flooring replacement at OCHS Girls Volleyball locker room and Room 231A received. NTP has been processed. Work scheduled for 1st week of August.

## OCHS Auditorium Lighting

- RFP Lighting Consultant to Board – August ‘23

## OCHS Berm at Tennis Courts

- Pricing for sidewalk has been received.

- Work to be scheduled as weather permits.

## Safety & Security at Middle Schools

- Initial BG-1

## LaGrange Elementary School Lower Level Modifications

- Demo completed

- New wall installed, electric rough-in complete

- Painting anticipated to be complete this week.

- Flooring has been ordered

- Ceiling proposals have been requested.

-End of Report