## Sheet1
BG1 PROJECT APPLICATION FORM (INITIAL)
DISTRICT: | Spencer County
Project Name: | Spencer County Early Learning Center Partial Renovation
BG NUMBER: | To be determined
Construction Delivery Method |  |  | General Contractor
Procurement Standard |  |  | Model Procurement
Emergency |  |  | Yes / No
Description of Scope
Applicable Items
New Building |  |  | Yes / No | No
Addition |  |  | Yes / No | No
Major Renovation |  |  | Yes / No | Yes
GESC |  |  | Yes / No | No
Roofing |  |  | Yes / No | Yes
HVAC |  |  | Yes / No | Yes
ADA Compliance |  |  | Yes / No | Yes
Life Safety / Security |  |  | Yes / No | Yes
Minor Project |  |  | Yes / No | No
New Relocatable Classroom |  |  | Yes / No | No
Equipment / Furnishings Procurement |  |  | Yes / No | Yes
Site |  |  | Yes / No | No
DISTRICT FACILITY PLAN (DFP)
Compliance with 702 KAR 4:180 and 702 KAR 4:160
DFP Approved Date |  |  | TBD - Revision in Progress
DFP Priority |  |  | 2c.5
Inventory
Facility Name | Spencer Co. Early Learning Center
Building Number:
Name: | Spencer Co. Early Learning Center
Type: | School
Scope
Provide a Complete Narrative of the Proposed Project
Major renovation of the second floor of the building including roof replacement, interior finishes, door hardware,
casework, signage, HVAC modifications and upgrades, electrical and lighting upgrades,
plumbing upgrades including fixtures, life safety systems including fire protection and
anunciation systems, security system upgrades, reconfiguring spaces for Preschool and Head Start, storm sewer upgrades.
Work Related to Project But Excluded from this BG1 Scope
N/A
Financial Plan
Probable Costs
Proposed Plan to Finance Application
Total Construction Cost |  |  |  | 2800000
Construction Contingency (8%) |  |  |  | 224000
Architect / Engineer Fee |  |  |  | 210000
Construction Manager Fee |  |  |  | 0
Fiscal Agent Fee |  |  |  | 12530.75
Bond Discount |  |  |  | 52667.24
Equipment / Furnishings |  |  |  | 150000
Equipment / Computers |  |  |  | 100000
Technology Network System (KETS) |  |  |  | 75000
Site Acquisition |  |  |  | 0
Site Survey |  |  |  | 0
Geotechnical Investigations |  |  |  | 0
Special Inspections |  |  |  | 0
Commissioning |  |  |  | 25000
Advertising |  |  |  | 500
Printing |  |  |  | 15000
Other Probable Costs
Title |  |  |  | Amount
Asbestos Abatement |  |  |  | 68000
Bank & Rating |  |  |  | 5610.84
No Data
No Data
Total Project Cost |  |  |  | 3738308.83
Funds Available
Bond Sale - SFCC |  |  |  | 0
Bond Requirement - SFCC |  |  |  | 0
Local FSPK Bond Sale |  |  |  | 3738308.83
Local General Fund Bond Sale |  |  |  | 0
Cash - SFCC Requirement |  |  |  | 0
Cash - Building Fund |  |  |  | 0
Cash - Capital Outlay |  |  |  | 0
Cash - Investment Earnings |  |  |  | 0
Cash - General Fund |  |  |  | 0
City - County - KYTC Reimbursement |  |  |  | 0
KETS |  |  |  | 0
Federal Funds |  |  |  | 0
External Partner Agreement |  |  |  | 0
Residual Funds
BG Number | Fund Source |  |  |  | Amount
No data | No Data
|  | Residual Funds Total |  |  | 0
Other Available Funds
Title |  |  |  | Amount
No Data |  |  |  | 0
No Data |  |  |  | 0
Total Funds Available |  |  |  | 3738308.83
Please be advised this form is for information only. To generate the Initial BG-1 form for signature, this information must be posted into the FACPAC system for KDE reivew and approval.