**Board Memo**

**DATE:** 12/14/2023

**AGENDA ITEM DETAILS:**

**School/Department**Boone County High School **Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #4 for Boone County High Reno, Phase 2, BG 21-295

**Date/Term (Beginning and End Dates/Year)**

11/20/2023

**APPLICABLE BOARD POLICY & STRATEGIC PLAN GOAL:**

05.1
Goal 4E: Boone County Schools will provide safe, clean, learner ready facilities. 1. Prioritize the district facilities plan to ensure alignment with the desired state as directed by the strategic plan.

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This change order includes the following:

Proposal 6 – Adding approximately 15’ of the underground utilities to the mobile classrooms as requested by the electric provider.

ADD - $5,537.00
Proposal 47 – This is a credit for charges and assessment from Duke that were part of the bid which was beyond what was required. During bidding, the design professionals have to make an educated guess since Duke does not provide pricing prior to construction.

DEDUCT - $50,000.00
Proposal 57 – This credit is for not replacing 31 lintels above the windows. The original specifications had the lintels scheduled for full replacement, assuming due to the age that they would be rusted. When replacement began, it was determined they were in outstanding condition and could be repainted without any impact.

DEDUCT - $6,510.00
Proposal 58 – Add a wall hydrant to the restroom per the request of the code official.

ADD - $1,476.00
Proposal 62R – Additional storm drainage between the academic wing and old standalone band building. It was determined to be less expensive to have this drainage added while the contractor was on-site.

ADD - $38,511.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$10,986.00 Decreased

 **Funding Source**

Local FSPK Bond Sale

 **\*If more than one funding source, list below along with amount or percent for each source**

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #4 for Boone County High Reno, BP #2, BG 21-295,

as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations