DECISION PAPER

TO: MEMBERS OF THE NELSON COUNTY BOARD OF EDUCATION

FROM: Charles Thompson, Construction and Maintenance Liaison/DPP

CC; Anthony Orr, Superintendent

SUBJECT: Change Order #14 for Thomas Nelson High School (TNHS)

DATE: August 17, 2010

ISSUE: Masonry walls for toilet partitions at Thomas Nelson High School were extended in order to accommodate stabilization of head rails. The manufacturer of plastic panels and frames would not warranty without head rails. The cost from River City Development Corp to extend the walls is $2365.00.

RECOMMENDATION: Approval of Change Order #14 for TNHS

RECOMMENDED MOTION: I move that the Nelson County Board of Education approve Change Order #14 for TNHS.