## BG-5
KENTUCKY DEPARTMENT OF EDUCATION | [17 empty] | BG-5
702 KAR 4:160 | [17 empty] | PROJECT CLOSEOUT FORM
District: | [6 empty] | District |  |  | Facility |  |  |  |  | School Code:
Name: |  | Russellville Independent |  |  |  |  | Code: | 523 |  | Name: | Stevenson Elementary School | [5 empty] | 25
BG #: |  | 22-409 |  |  | Project Name: |  |  | Stevenson Elementary Window Replacement
A. PROJECT COMPLETION & INVENTORY UPDATE
| Project Total Gross Square Footage: | [5 empty] | n/a
| The work performed under this project has been reviewed and found to be substantially complete, according to the KDE approved Construction Documents. | [10 empty] | Date of Project Substantial Completion :
2023-12-22
| Upon project completion, submit a revised total building inventory file, per 702 KAR 4:180, for building(s) modified or newly constructed during the project. | [10 empty] | Date of Inventory Update:
n/a
B. RECONCILIATION OF FINAL PROJECT COST
|  |  |  | C |  | CURRENT BG-1 COSTS (reconciled with bid amts.) |  |  | FINAL PROJECT COSTS |  |  | CURRENT BG-1 FUNDS AVAILABLE (reconciled with bid amounts) |  |  | FINAL FUND SOURCES UTILIZED
1. | Total Construction Cost |  |  |  |  | 439850 |  |  | 439850 | 1. Bond Sale - SFCC |  | 0 |  |  | 0
2 | Construction Contingency |  |  |  |  | 21995 |  |  | 0 | 2. Bond Requirement - SFCC |  | 0 |  |  | 0
3. | Architect/Engineer Fee |  |  |  |  | 43900 |  |  | 45388.25 | 3. Local FSPK Bond Sale |  | 0 |  |  | 0
4. | Construction Manager Fee |  |  |  |  | 0 |  |  | 0 | 4. Local General Fund Bond Sale |  | 0 |  |  | 0
5. | Fiscal Agent Fee |  |  |  |  | 0 |  |  | 0 | 5. Cash - SFCC Requirement |  | 0 |  |  | 0
6. | Bond Discount |  |  |  |  | 0 |  |  | 0 | 6. Cash - Building Fund |  | 394639 |  |  | 0
7. | Equipment/Furnishings |  |  |  |  | 0 |  |  | 0 | 7. Cash - Capital Outlay |  | 111806 |  |  | 0
8. | Equipment/Computers |  |  |  |  | 0 |  |  | 0 | 8. Cash - Investment Earnings |  | 0 |  |  | 0
9. | Technology Network (KETS) |  |  |  |  | 0 |  |  | 0 | 9. Cash - General Fund |  | 0 |  |  | 0
10. | Site Acquisition |  |  |  |  | 0 |  |  | 0 | 10. City-County - KYTC Reimbursement |  | 0 |  |  | 0
11. | Site Survey |  |  |  |  | 0 |  |  | 0 | 11. KETS |  | 0 |  |  | 0
12. | Geotechnical Investigations |  |  |  |  | 0 |  |  | 0 | 12. Federal Funds |  | 0 |  |  | 0
13. | Special Inspections |  |  |  |  | 0 |  |  | 0 | 13. Funds Available - External Partner |  | 0 |  |  | 0
14. | Commissioning |  |  |  |  | 0 |  |  | 0 | 14. Residual Funds |  | 0 |  |  | 0
15. | Advertising |  |  |  |  | 200 |  |  | 67.85 | 15. School Security Funds |  | 0 |  |  | 0
16. | Printing |  |  |  |  | 500 |  |  | 1336.54 |  |  | 0 |  |  | 0
17 | Plan Review |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
18. | Ship, Mileage |  |  |  |  | 0 |  |  | 1126.88 |  |  | 0 |  |  | 0
19. | Issuance Fees |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Total Costs: | [5 empty] | 506445 |  |  | 487769.52 | Total Funds: |  | 506445 |  |  | 0
The expense totals reflected on this form were incurred as a result of the construction for the above reference project.
An accounting of the expenses was presented to the board for review and approval prior to payment.
|  | The | Russellville Independent | [5 empty] | Board of Education accepts this project as being complete subject to the review of KDE.
[7 empty] | Local Board of Education Designee: | [5 empty] | DATE:
LOCAL BOARD ORDER MUST BE ON FILE WITH DISTRICT
Submit one complete copy to KDE for each completed project.
SUBMIT AN INVENTORY UPDATE - PER 702 KAR 4:180
[16 empty] | BG-5 Date: | 2024-08-08
Board Order Date:

## Inv Breakdown
INV# | FEE | CO FEE | PLAN REVIEW | AD | PRINT-IN | PRINT-OUT | MILEAGE | SHIPPING | TOTAL
22012-001 | 18131.25 | [7 empty] | 18131.25
22012-002 | 27257 |  |  | 67.85 | 497.9 | 838.6375 | 1107.7 | 19.182 | 29788.2695
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| 45388.25 | 0 | 0 | 67.85 | 497.9 | 838.6375 | 1107.7 | 19.182 | 47919.5195
1336.5375