Strategic Prevention Framework

I³: Inspired, Individualized, Inclusive

October 2024 - November 2024

| Goal: To reduce the onset & progression of substance misuse & its related problems in Bellevue, KY, by supporting the development & delivery of community substance misuse prevention & mental health promotion services. |  |
| --- | --- |
| Objective 1: | By 9/29/2027, reduce the 30-day use of alcohol among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 2: | By 9/29/2027, reduce regular (30-day) vaping use among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 3: | By 9/29/2027, reduce regular (30-day) cigarette smoking among tenth-grade students by 2% each year as measured by annual KIP data. |
| Objective 4: | By 9/29/2027, tenth-grade students reporting serious psychological distress, according to the K6 KIP data, will decrease by 4% each year. |
| Objective 5: | By 9/29/2027, expand collaboration with community prevention partners, demonstrated by support from community prevention partners at least 2x each year in the project’s family prevention education opportunities, documented by photographic evidence & meeting notes. |

| ASSESSMENT |  |  |
| --- | --- | --- |
| Accomplishments | Description | Align |
| Assessing schools’ assets & resources: | I³ staff reviewed & updated the Resource Map | 1-5 |
| Assessment of schools’ capacity: | I³ staff, in collaboration with GES & BMHS school leadership, are assessing capacity for SEB Tier 2 & Tier 3. | 1-5 |
| Specification of baseline data: | SEB screener was given to all K-5 students (196) and 6-12 (youth-rated 115; teacher-rated 89). The data will be used within the MTSS framework to proactively detect students who need support beyond Tier 1 instruction & support. * *Data utilized in MTSS meetings at GES, BMHS SEB data utilization unknown | 1-4 |
| Monitoring schools needs assessment activities: | The KIP Survey will be administered in the fall of 2024 on November 12th and November 14th | 1-4 |
| Monitoring schools needs assessment activities: | Internal Referrals for mental health & prevention services. * 12 internal referrals for services (GES only) 2 internal referrals for prevention services 2 internal referral assessments completed for prevention services *BMHS mental health referral data and internal referral assessments unknown | 1-4 |
| Monitoring schools needs assessment activities: | External Referrals for mental health & prevention services. 0 student/family external referral 1 student/family Care Solace referrals 0 staff member's Care Solace referrals | 1-4 |
| Monitoring schools needs assessment activities: | Grant staff collect & monitor data on all grant lead initiatives. This includes, but is not limited to: - Outreach & Engagement Data - Participation Data - Outcome Data - Financial Data - Progress Monitoring | 1-5 |
| Use of needs assessment data | Grant staff continues to redirect efforts to target the community with infrastructure development initiatives. | 5 |
| CAPACITY |  |  |
| Accomplishments | Description | Align |
| Professional Development: | SPF Grant Staff: - UK Trauma Center: Window of Tolerance: An Advanced Training on Secondary Traumatic Stress and Resiliency - Vaping Unplugged: Teen Voices on Risks and Recovery with Kyle Wimmer and Cynthia Stremba - Prevention Action Alliance’s advocacy webinar. - Provides updates on events, bills, and legislation along with other prevention and wellness advocacy-related activities within the state and federal government. - Mental Health Literacy Webinar through The Mental Health Literacy Center - Everything You Need to Know about Cannabis by Mental Health America of NKY & Southwest OH - NKY Regional Youth Summit through NKCES - Regional Brain and Behavior Training: Creating a Culture of Academic Engagement and Effective Classroom Management by Character Strong and NKCES - PFS Communities CORT Orientation - UK CTAC Trauma-Informed Practices for Educators Learning Collaborative Learning Session 2 - SPTAC Regions III and IV: LISTENING SESSION OPPORTUNITY - Safe Roads Ahead: How to Discuss Impaired Driving with Children and Teens - Catch My Breath Training GES Mental Health Professional: - Character Strong Bully Prevention Summit - Anxiety Improved and Updated Treatments - Character Strong How to Implement Tier 3 - Character Strong Tier 3 Mental Health Literacy - Character Strong Tier 2 Implementation - Play Therapy Training (Continued) | 5 |
| Facilitated Professional Development: | - Data Analyst led teacher-rated screening training | 5 |
| Building internal coalitions: | Grant staff participated in the following monthly coalition/committee meetings: - GES PBIS Tier 2/3 Meeting - GES Student Care Team Meeting - GES Student Care Team - Ancillary Meeting - 5K Initiative Planning Committee - Rae of Sunshine - SMILE Club Meeting | 5 |
| Building external coalitions: | Grant staff participated in the following monthly coalition/committee meetings: - NKY ASAP - SBMH Grant Committee Meeting - TISS Grant Committee Meeting - NKY Youth Summit Planning Committee Meeting - NKISP Steering Committee Meeting - Campbell County Drug-Free Alliance General Meeting - Team Kentucky - Prevention & Promotion Branch - Students Against Drunk Driving (SADD) | 5 |
| Building external partnerships: | Grant staff meet with the following community agencies: - SUN Behavioral Health - 1N5 - City of Bellevue - Starbucks - Kroger - Trader Joe | 5 |
| Other infrastructure development: | - Review & update the webpage with resources weekly. MH&Prevention Webpage - Resource mapping review & update support for students, staff, & families. BISD Resource Map | 5 |
| PLANNING |  |  |
| Accomplishments | Description | Align |
| Articulation of a vision for prevention activities: | Grant staff will work with school leadership to discuss the following: - Implementation of #iCANendthetrend, tobacco use & vaping prevention program through the UK. - Implementing a chapter of Rae of Sunshine at BMHS - MTSS tiered level of support & SEB Screener Capacity & Decision Rules | 1-5 |
| Articulation of a vision for prevention activities: | Grant staff are working toward planning the following: NOVEMBER - 11/13 - World Kindness Day - 11/14 - Weekly Rae of Sunshine - SMILE Club Meetings - 11/15 - SPF Newsletter #2 - 11/15 - Spill the Tea - 11/19 - I3 Advisory Meeting - 11/20 - Self Esteem groups at GES - 11/26 - Support for the Holidays - 11/25 - Trauma Book Study DECEMBER - 12/04 - Trauma Walk Through (GES & BMHS) - 12/06 - Trauma Book Study - 12/12 - Weekly Rae of Sunshine - SMILE Club Meetings - 12/13 - #iCANendthetrend - 12/17 - Dinner Table Project #2 - 12/18 - Emotional First Aid for Teacher presented by SMILE Club - 12/20 - Spill the Tea - 12/20 - Sober Fun for the Holidays - Abbreviated SPF Newsletter, including sober fun & support for the holidays JANUARY - National Thank You Month - National Mentoring Month - MLK Day - Chinese New Year - 01/08 - Self Esteem groups at GES - 01/09 - SMILE Club - 01/17 - Spill the Tea - 01/17 - I3 Newsletter #3 - 01/21 - I3 Advisory Meeting - 01/22 - 5K Planning - 01/24 - National Compliment Day WINTER - Newsletter - Dinner Table Project - Weekly Rae of Sunshine - SMILE Club Meetings - Prevention Day (Feb 2025) - Pop the Stigma - #SELday SPRING - Newsletter - Dinner Table Project - Weekly Rae of Sunshine - SMILE Club Meetings - Mental Health Roundtables - Mental Health Month - Mental Health Day of Action - 5K Initiative | 1-4 |
| Identification of the district-level priorities: | Mental Health & Prevention Services Handbook - I³ team continues to create an evidence-based policy & procedural handbook for BISD’s mental health & prevention services. - Outlines the screening process - Details referral process - Includes information about MTSS | 1-5 |
| Identification/coordination/allocation of resources: | Prevention Specialists will be trained in Catch My Breath. | 1-3 |
| Identification/coordination/allocation of resources: | Trauma-Informed Grant - The I³ team is working with NKCES to evaluate the strength and weaknesses of BISD’s Trauma Plan. | 4 |
| IMPLEMENTATION |  |  |
| Accomplishments | Description | Align |
| Specific community-level interventions being implemented: | Grant staff implemented the following: OCTOBER - 10/15 - Dinner Table Project #1 - 10/17 - Weekly Rae of Sunshine - SMILE Club Meetings (Chalk the Walk) - 10/23 - NKY Youth Summit - Team volunteered - 10/23 - 10/31 Red Ribbon Week (GES & BMHS) - Life is a Movie: Film Drug-Free - Red Ribbon Week Flyer - 10/26 - National Take-back Day - Flyers distributed & will be placed on webpage - Take-Back Day Flyer.pdf - Lock Box Flyer.pdf - 10/31- Math Night at GES NOVEMBER - 11/11 - Veteran’s Day - Staff Highlight - 11 Ways to Show Gratitude - Mental Health Resources for Veterans - 11/13 - World Kindness Day - GES - Kindness wheel - BMHS - Random Acts of Kindness |  |
| Implemented policies within organizations to facilitate interventions | Grant staff works with the following grants to create procedures for the BISD mental health & prevention team in response to students' & families' mental health & prevention needs. These align with best practices. - Trauma-Informed Grant - Grant staff continues to work with TISS Grant to revise BISD’s trauma-informed plan & create action steps to ensure the implementation of best practices. - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - School-Based Mental Health Grant - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - Prevention - Grant staff continues to review & revise BISD’s Prevention plan, creating action steps to ensure the implementation of best practices. - Created district tobacco/nicotine-free procedure in response to HB-142; the procedure was added to the Code of Conduct and middle/high school behavior matrix. | 4 |
| Specific community-level interventions being implemented: | SBMH Breakdown of time and/or student reached/seen: - Direct sessions: 1,040 minutes = 17.3 hours - Additional sessions: 222 minutes = 3.7 hours - Groups: 0 minutes = 0 hours - Tier 2 performance: 90 minutes = 1.5 hours - Continuity of care meetings: 1,050 minutes = 18 hours SBMH GES Caseload Numbers: - Active cases: 15 - Tier 2 performance: 1 - Referrals: 0 | 4 |
| Specific community-level interventions being implemented: | Prevention Breakdown of time and/or student reached/seen: - Direct sessions: 360 minutes = 6 hours - Additional sessions: 90 minutes = 1.5 hours - Groups: 0 minutes = 0 hours - Tier 2 performance: 0 minutes = 0 hours - Continuity of care meetings: 120 mins = 2 hours Prevention Caseload Numbers: - Active cases: 3 - Tier 2 performance: 0 - Referrals: 0 | 1-4 |  |
| Developed systems for distributing resources: | 5 lockboxes have been provided to families of students. | 1-3 |
| EVALUATION |  |  |
| Accomplishments | Description | Align |
| Monitor & evaluate all activities: | Evaluating SEB data to support our developing MTSS. | 4 |
| Monitor & evaluate all activities: | SPF Grant Data - Outcome data collected on the number of event impressions and post-survey information. | 4 |
| Grant Reporting: | - 10/31 - SPF SPARS Quarter 4 Report – Submitted - 12/31 - SPF eRa Commons Annual Performance Review - Due - 01/31 - SPF SPARS Quarter 1 Report - Due - 01/31 - SPF Continuation Report - Due |  |

| SUSTAINABILITY |  |
| --- | --- |
| Planning for sustaining the infrastructure: | Continue developing & improving the district's MTSS system & mental health support. SEL teams deliver substance abuse prevention curriculum to students. |