Strategic Prevention Framework

I³: Inspired, Individualized, Inclusive

November 2024 - December 2024

| Goal: To reduce the onset & progression of substance misuse & its related problems in Bellevue, KY, by supporting the development & delivery of community substance misuse prevention & mental health promotion services. |  |
| --- | --- |
| Objective 1: | By 9/29/2027, reduce the 30-day use of alcohol among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 2: | By 9/29/2027, reduce regular (30-day) vaping use among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 3: | By 9/29/2027, reduce regular (30-day) cigarette smoking among tenth-grade students by 2% each year as measured by annual KIP data. |
| Objective 4: | By 9/29/2027, tenth-grade students reporting serious psychological distress, according to the K6 KIP data, will decrease by 4% each year. |
| Objective 5: | By 9/29/2027, expand collaboration with community prevention partners, demonstrated by support from community prevention partners at least 2x each year in the project’s family prevention education opportunities, documented by photographic evidence & meeting notes. |

| ASSESSMENT |  |  |
| --- | --- | --- |
| Accomplishments | Description | Align |
| Assessing schools’ assets & resources: | I³ staff reviewed & updated the Resource Map | 1-5 |
| Assessment of schools’ capacity: | I³ staff, in collaboration with GES & BMHS school leadership, are assessing capacity for SEB Tier 2 & Tier 3. | 1-5 |
| Specification of baseline data: | SEB screeners will be given to all K-5 students (teacher-rated) and 6-12 (teacher-rated and youth-rated). The data will be used within the MTSS framework to proactively detect students who need support beyond Tier 1 instruction & support. * *Data utilized in MTSS meetings at GES, BMHS SEB data utilization unknown | 1-4 |
| Monitoring schools needs assessment activities: | The KIP Survey was administered in November to students with signed consents (12 students). Will be exploring other options to collect data. | 1-4 |
| Monitoring schools needs assessment activities: | Internal Referrals for mental health services. * 7 internal referrals for services (GES only) 4 internal referrals accepted 3 internal referrals in progress 5 internal referrals for prevention services 1 internal referral assessments completed for prevention services BMHS MTSS Tracker GES MTSS Tracker *Specific BMHS mental health referral data and internal referral assessments unknown | 1-4 |
| Monitoring schools needs assessment activities: | External Referrals for mental health & prevention services.* 0 student/family external referral 1 student/family Care Solace referrals 0 staff member's Care Solace referrals *Specific BMHS external referral data unknown | 1-4 |
| Monitoring schools needs assessment activities: | Grant staff collect & monitor data on all grant lead initiatives. This includes, but is not limited to: - Outreach & Engagement Data - Participation Data - Outcome Data - Financial Data - Progress Monitoring | 1-5 |
| Use of needs assessment data | Grant staff continues to redirect efforts to target the community with infrastructure development initiatives. | 5 |
| CAPACITY |  |  |
| Accomplishments | Description | Align |
| Professional Development: | SPF Grant Staff: - High in Plain Sight: CURRENT Drug Trends - UK CTAC Trauma-Informed Practices for Educators Learning Collaborative- Learning Session 1 - UK CTAC Trauma-Informed Practices for Educators Learning Collaborative Learning Session 2 - SPTAC Regions III and IV: LISTENING SESSION OPPORTUNITY - Safe Roads Ahead: How to Discuss Impaired Driving with Children and Teens GES Mental Health Professional: - Character Strong - 5 Proactive Ways to Show Deep Kindness | 5 |
| Facilitated Professional Development: | - Mental Health & Prevention team led a trauma-informed care and social-emotional learning training for GES during ERD on 12/4 | 5 |
| Building internal coalitions: | Grant staff participated in the following monthly coalition/committee meetings: - GES PBIS Tier 2/3 Meeting - GES Student Care Team Meeting - GES Student Care Team - Ancillary Meeting - 5K Initiative Planning Committee - Rae of Sunshine - SMILE Club Meeting - Finance meetings | 5 |
| Building external coalitions: | Grant staff participated in the following monthly coalition/committee meetings: - North Key - NKY ASAP - SBMH Grant Committee Meeting - TISS Grant Committee Meeting - NKY Youth Summit Post-Event Planning Committee Meeting - NKISP Steering Committee Meeting - Campbell County Drug-Free Alliance General Meeting - Team Kentucky - Prevention & Promotion Branch | 5 |
| Building external partnerships: | Grant staff meet with the following community agencies: - North Key - City of Bellevue - Starbucks - Kroger - Trader Joe | 5 |
| Other infrastructure development: | - Review & update the webpage with resources weekly. MH&Prevention Webpage - Resource mapping review & update support for students, staff, & families. BISD Resource Map | 5 |
| PLANNING |  |  |
| Accomplishments | Description | Align |
| Articulation of a vision for prevention activities: | Grant staff will work with school leadership to discuss the following: - Implementation of #iCANendthetrend, tobacco use & vaping prevention program through the UK. - Planned for 12/13 - Implementing a chapter of Rae of Sunshine at BMHS - SMILE Club Meetings #6, 7, 8 - Next meeting 1/12 - Members will lead ENGAGE sessions for middle and high school on 1/8 - Continuing with positive posters; will display throughout school upon return from break - MTSS tiered level of support & SEB Screener Capacity & Decision Rules | 1-5 |
| Articulation of a vision for prevention activities: | Grant staff are working toward planning the following: District - Lockbox Video Campaign GES - Too Good for Drugs Curriculum BMHS - Prevention Campaign (BHS) DECEMBER - 12/17 - Dinner Table Project #2 - 12/18 - Emotional First Aid for Teacher presented by SMILE Club - 12/20 - Spill the Tea - 12/20 - Sober Fun for the Holidays and abbreviated SPF Newsletter, including sober fun & support for the holidays JANUARY - National Thank You Month - National Mentoring Month - MLK Day - Chinese New Year - 01/08 - Self Esteem groups at GES - 01/08 - SMILE Club leading ENGAGE sessions - 01/09 - SMILE Club - 01/17 - Spill the Tea - 01/17 - I3 Newsletter #3 - 01/21 - I3 Advisory Meeting - 01/22 - 5K Planning - 01/24 - National Compliment Day WINTER - Newsletter - Dinner Table Project - Weekly Rae of Sunshine - SMILE Club Meetings - Prevention Day (Feb 2025) - Pop the Stigma - #SELday SPRING - Newsletter - Dinner Table Project - Weekly Rae of Sunshine - SMILE Club Meetings - Mental Health Roundtables - Mental Health Month - Mental Health Day of Action - 5K Initiative | 1-4 |
| Identification of the district-level priorities: | Mental Health & Prevention Services Handbook - I³ team continues to create an evidence-based policy & procedural handbook for BISD’s mental health & prevention services. - Outlines the screening process - Details referral process - Includes information about MTSS | 1-5 |
| Identification/coordination/allocation of resources: | Prevention Specialist trained in Catch My Breath. | 1-3 |
| Identification/coordination/allocation of resources: | Trauma-Informed Grant - The I³ team is working with NKCES to evaluate the strength and weaknesses of BISD’s Trauma Plan. The team will review suggestions based on trauma-informed walkthrough that took place on 12/4. | 4 |
| IMPLEMENTATION |  |  |
| Accomplishments | Description | Align |
| Specific community-level interventions being implemented: | Grant staff implemented the following: NOVEMBER - 11/13 - World Kindness Day - 11/19 - I3 Advisory Meeting - Meeting Slides - 11/20 - Self Esteem groups at GES - 11/26 - Support for the Holidays - 11/22 - Trauma Book Study DECEMBER - 12/04 - Trauma Walk Through (GES & BMHS) - 12/06 - Trauma Book Study - 12/12 - Weekly Rae of Sunshine - SMILE Club Meetings - 12/13 - #iCANendthetrend |  |
| Implemented policies within organizations to facilitate interventions | Grant staff works with the following grants to create procedures for the BISD mental health & prevention team in response to students' & families' mental health & prevention needs. These align with best practices. - Trauma-Informed Grant - Grant staff continues to work with TISS Grant to revise BISD’s trauma-informed plan & create action steps to ensure the implementation of best practices. - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - School-Based Mental Health Grant - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - Prevention - Grant staff continues to review & revise BISD’s Prevention plan, creating action steps to ensure the implementation of best practices. - Created district tobacco/nicotine-free procedure in response to HB-142; the procedure was added to the Code of Conduct and middle/high school behavior matrix. | 4 |
| Specific community-level interventions being implemented: | SBMH Breakdown of time and/or student reached/seen: - Direct: 1,880 minutes = 31.4 hours - Extra Sessions: 125 minutes = 2.1 hours - Meetings: 600 minutes = 10 hours - Indirect: 780 minutes = 13 hours SBMH GES Caseload Numbers: - Active cases: 16 - Tier 2 performance: 0 - Referrals: 7 | 4 |
| Specific community-level interventions being implemented: | Prevention Breakdown of time and/or student reached/seen: - Direct sessions: 500 minutes; 8.3 hours - Groups: 0 minutes = 0 hours - Tier 2 performance: 0 minutes = 0 hours - Indirect: 6 students; 440 minutes; 7.3 hours Prevention Caseload Numbers: - Active cases: 3 - Referrals: 2 - Pending: 2 - Tier 2 performance: 0 | 1-4 |  |
| Developed systems for distributing resources: | 1 lockbox has been provided to families of students. | 1-3 |
| EVALUATION |  |  |
| Accomplishments | Description | Align |
| Monitor & evaluate all activities: | Evaluating SEB data to support our developing MTSS. | 4 |
| Monitor & evaluate all activities: | SPF Grant Data - Outcome data collected on the number of event impressions and post-survey information - Data submitted to SPARS Total Served to Date = 3,110 Total Reached to Date = 33,929 KIP Survey = 12 served Newsletter #2 = 101 served, 712 reached GES Health Class for Self-esteem = 81 served, 1386 reached Lockboxes = 22 served GES Trauma-informed Training @ ERD = 25 served SMILE Club Meetings = 18 reached | 4 |
| Monitor & evaluate all activities: | Dinner Table Project #1 Post-Survey Data reviewed and used to modify elements of the project to better suit students and families | 4 |
| Grant Reporting: | - 10/31 - SPF SPARS Quarter 4 Report – Submitted - 12/31 - SPF eRa Commons Annual Performance Review - Due - 01/31 - SPF SPARS Quarter 1 Report - Due - 01/31 - SPF Continuation Report - Due |  |

| SUSTAINABILITY |  |
| --- | --- |
| Planning for sustaining the infrastructure: | Continue developing & improving the district's MTSS system & mental health support. SEL teams deliver substance abuse prevention curriculum to students. |