Strategic Prevention Framework

I³: Inspired, Individualized, Inclusive

December 2024 - January 2025

| Goal: To reduce the onset & progression of substance misuse & its related problems in Bellevue, KY, by supporting the development & delivery of community substance misuse prevention & mental health promotion services. |  |
| --- | --- |
| Objective 1: | By 9/29/2027, reduce the 30-day use of alcohol among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 2: | By 9/29/2027, reduce regular (30-day) vaping use among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 3: | By 9/29/2027, reduce regular (30-day) cigarette smoking among tenth-grade students by 2% each year as measured by annual KIP data. |
| Objective 4: | By 9/29/2027, tenth-grade students reporting serious psychological distress, according to the K6 KIP data, will decrease by 4% each year. |
| Objective 5: | By 9/29/2027, expand collaboration with community prevention partners, demonstrated by support from community prevention partners at least 2x each year in the project’s family prevention education opportunities, documented by photographic evidence & meeting notes. |

| ASSESSMENT |  |  |
| --- | --- | --- |
| Accomplishments | Description | Align |
| Assessment of schools’ capacity: | I³ staff, in collaboration with GES & BMHS school leadership to complete the SEB Winter Screener | 1-5 |
| Specification of baseline data: | SEB screeners will be given to all K-5 students (teacher-rated) and 6-12 (teacher-rated and youth-rated). The data will be used within the MTSS framework to proactively detect students who need support beyond Tier 1 instruction & support. * - GES completed teacher-rated on 12/18/24 (194 students) - BMHS incomplete; scheduled to complete teacher-rated on 1/3/25 *Data utilized in MTSS meetings at GES, BMHS SEB data utilization unknown | 1-4 |
| Monitoring schools needs assessment activities: | Internal Referrals for mental health services. * 1 internal referral for services (GES only) 1 internal referral accepted 0 internal referrals in progress 5 internal referrals for prevention services 1 internal referral assessment completed for prevention services BMHS MTSS Tracker GES MTSS Tracker *Specific BMHS mental health referral data and internal referral assessments unknown | 1-4 |
| Monitoring schools needs assessment activities: | External Referrals for mental health & prevention services. * 0 student/family external referral 0 student/family Care Solace referrals 0 staff member's Care Solace referrals *Specific BMHS external referral data unknown | 1-4 |
| Monitoring schools needs assessment activities: | Grant staff collect & monitor data on all grant lead initiatives. This includes, but is not limited to: - Outreach & Engagement Data - Participation Data - Outcome Data - Financial Data - Progress Monitoring | 1-5 |
| Use of needs assessment data: | Grant staff continues to redirect efforts to target the community with infrastructure development initiatives. | 5 |
| CAPACITY |  |  |
| Accomplishments | Description | Align |
| Professional Development: | SPF Grant Staff: - PTAC Navigating Prevention Systems Changes at the State-Level - UK CTAC TIPE Learning Collaborative Learning Call - Stronger Together: Leveraging School-Community Partnerships for Prevention Success - Defining, Analyzing, and Selecting Tier 2 Supports - Prevention Science in Action: Supporting Families & Schools in Raising Healthy Kids - The SAMHSA Grant Application Process GES Mental Health Professional: - Play Therapy for Children, Adolescents and Adults - Going from Reactive to Proactive Getting Tier 3 Right - Am I doing Tier 2 & 3 Right? 5 Indicators to Implement Tier 3 with Confidence - The Body Keeps the Score Trauma Training (In progress) | 5 |
| Building internal coalitions: | Grant staff participated in the following monthly coalition/committee meetings: - GES PBIS Tier 2/3 Meeting - GES Student Care Team Meeting - GES Student Care Team - Ancillary Meeting - 5K Initiative Planning Committee - Rae of Sunshine - SMILE Club Meeting - Finance meetings | 5 |
| Building external coalitions: | Grant staff participated in the following monthly coalition/committee meetings: - North Key - NKY ASAP - SBMH Grant Committee Meeting - TISS Grant Committee Meeting - NKISP Steering Committee Meeting - Campbell County Drug-Free Alliance General Meeting - River Cities Drug-Free Coalition Meeting - Team Kentucky – Prevention & Promotion Branch | 5 |
| Building external partnerships: | Grant staff meet with the following community agencies: - North Key - City of Bellevue - Starbucks - Kroger - Trader Joe - Perfetti Van Melle | 5 |
| Community Conversations: | - Bullitt County Meeting to discuss Vape Disposal - NKY Health Department – to discuss TGFD - CCDFA to discuss video campaign & Prom initiative - 5k - Vets - St. Elizabeth - Sun Behavioral - Ryan Salzman – City Council - City of Bellevue |  |
| Other infrastructure development: | - Review & update the webpage with resources weekly. MH&Prevention Webpage - Resource mapping review & update support for students, staff, & families. BISD Resource Map | 5 |
| PLANNING |  |  |
| Accomplishments | Description | Align |
| Articulation of a vision for prevention activities: | Grant staff will work with school leadership to discuss the following: - Implementation of video campaign. - Planned for 01/30 (kickoff) - MTSS tiered level of support & SEB Screener Capacity & Decision Rules | 1-5 |
| Articulation of a vision for prevention activities: | Grant staff are working toward planning the following: District - Lockbox Video Campaign with CCDFA and SMILE Club GES - Too Good for Drugs Curriculum with NKY Health Department BMHS - Prevention Campaign (BHS) JANUARY - 01/03 – BMHS Screener scheduled - 01/06 – Compliment Bulletin Board - 01/07 – SMILE Club – prep for leading empathy lesson during ENGAGE (canceled) - 01/08 - SMILE Club leading ENGAGE sessions (canceled) - 01/09 - SMILE Club - 01/17 - Spill the Tea - 01/17 - I3 Newsletter #3 - 01/21 - I3 Advisory Meeting - 01/22 - Self-esteem Groups @ GES - 01/22 - 5K Planning - 01/24 - National Compliment Day - 01/28 - NKCES Trauma Make & Take - 01/29 - SMILE Club Concession Stand Fundraisers - 01/30 - Video Campaign Kickoff FEBRUARY - National Thank You Month - 02/03 - SMILE Club Concession Stand Fundraisers - 02/07 - Pop the Stigma Initiative partnered with Perfetti Van Melle - 02/10 - SMILE Club Concession Stand Fundraisers - 02/17 - Random Acts of Kindness Day - 02/18 – Dinner Table Project #3 - 02/19 - SMILE Club Concession Stand Fundraisers - 02/21 – Spill the Tea Initiative WINTER - Newsletter - Dinner Table Project - Weekly Rae of Sunshine - SMILE Club Meetings - Prevention Day (Feb 2025) - Pop the Stigma - #SELday SPRING - Newsletter - Dinner Table Project - Weekly Rae of Sunshine - SMILE Club Meetings - Mental Health Roundtables - Mental Health Month - Mental Health Day of Action - 5K Initiative | 1-4 |
| Identification of the district-level priorities: | Mental Health & Prevention Services Handbook—I³ team continues to create an evidence-based policy and procedural handbook for BISD’s mental health and prevention services. - Outlines the screening process - Details referral process - Includes information about MTSS | 1-5 |
| Identification/coordination/allocation of resources: | Prevention Specialist trained in Catch My Breath. | 1-3 |
| Identification/coordination/allocation of resources: | Trauma-Informed Grant – The I³ team is working with NKCES to evaluate the strengths and weaknesses of BISD’s Trauma Plan. The team will review recommendations based on the trauma-informed walkthrough that took place on 12/4. | 4 |
| IMPLEMENTATION |  |  |
| Accomplishments | Description | Align |
| Specific community-level interventions being implemented: | Grant staff implemented the following: DECEMBER - 12/04 - Trauma Walk Through (GES & BMHS) - 12/04 – GES Trauma/SEL Presentation during ERD - Bellevue Newspaper article - 12/06 - Trauma Book Study - 12/11 - BMHS Character Strong Audit (rescheduled) - 12/12 - Weekly Rae of Sunshine - SMILE Club Meetings - 12/13 - UK #iCANendthetrend Presentations - 12/16-12/20 – SEB Screener Window #2 - 12/17 – #iCANendthetrend post-survey #1 - 12/17 – Dinner Table Project #2 - 12/18 – GES Screener completed - 12/18 – Emotional First Aid for Teacher presented by SMILE Club (Rescheduled) - 12/20 – Abbreviated Newsletter - 12/20 – Spill the Tea - 12/20 – Sober Fun for the Holidays and abbreviated SPF Newsletter, including sober fun & support for the holidays |  |
| Implemented policies within organizations to facilitate interventions | Grant staff works with the following grants to create procedures for the BISD mental health & prevention team in response to students' & families' mental health & prevention needs. These align with best practices. - Trauma-Informed Grant - Grant staff continues to work with TISS Grant to revise BISD’s trauma-informed plan & create action steps to ensure the implementation of best practices. - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - School-Based Mental Health Grant - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - Prevention - Grant staff continues to review & revise BISD’s Prevention plan, creating action steps to ensure the implementation of best practices. - Created district tobacco/nicotine-free procedure in response to HB-142; the procedure was added to the Code of Conduct and middle/high school behavior matrix. | 4 |
| Specific community-level interventions being implemented: | SBMH Breakdown of time and/or student reached/seen: - Direct: 1,160 minutes = 19.3 hours - Total Sessions: 29 - Extra Sessions: 227 minutes = 3.8 hours - Meetings: 570 minutes = 9.5 hours - Indirect: 630 minutes = 10.5 hours SBMH GES Caseload Numbers: - Active cases: 17 - Tier 2 performance: 0 - Referrals: 1 | 4 |
| Specific community-level interventions being implemented: | Prevention Breakdown of time and/or student reached/seen: - Direct sessions: 500 minutes; 8.3 hours - Groups: 0 minutes = 0 hours - Tier 2 performance: 0 minutes = 0 hours - Indirect: 6 students; 440 minutes; 7.3 hours Prevention Caseload Numbers: - Active cases: 3 - Referrals: 2 - Pending: 2 - Tier 2 performance: 0 | 1-4 |  |
| Developed systems for distributing resources: | 0 lockbox has been provided to families of students 22 lockboxes have been distributed in total Receiving Deterra bags from NKY ASAP to distribute | 1-3 |
| EVALUATION |  |  |
| Accomplishments | Description | Align |
| Monitor & evaluate all activities: | Evaluating SEB data to support our developing MTSS. | 4 |
| Monitor & evaluate all activities: | SPF Grant Data - Outcome data collected on the number of event impressions and post-survey information - Data submitted to SPARS Total Served to Date = 3,361 Total Reached to Date = 33,929 Holiday Newsletter = 43 served GES Health Class for Self-esteem = 81 served, 1386 reached Lockboxes = 22 served SMILE Club Meetings = 12 served Dinner Table Project #2 = 163 served (75 students) Total to Date: Dinner Table Project = 457 served, 3167 reached Spill the Tea = 29 served, 4728 reached | 4 |
| Monitor & evaluate all activities: | Dinner Table Project #2 Post-Survey Data collected and reviewed; used to modify elements of the project to better suit students and families. | 4 |
| Monitor & evaluate all activities: | #iCANendthetrend post-survey #1 collected; will review once results are received from the program. | 1-5 |
| Grant Reporting: | - 12/31 - SPF eRa Commons Annual Performance Review - Submitted - 12/31 - SPF eRa Commons Carryover - Submitted - 01/31 - SPF Continuation Report – Submitted - 3/30 - SPF SPARS Quarter 1&2 Report – Due |  |

| SUSTAINABILITY |  |
| --- | --- |
| Planning for sustaining the infrastructure: | Continue developing & improving the district's MTSS system & mental health support. SEL teams deliver substance abuse prevention curriculum to students. |