“Aim High and Dare to be Great”

Berea Independent Schools

Draft Superintendent Search Timeline

January 27	Meeting with the Board

January 31	Job posted with KDE

January 31	Screening Committee selection process started

February 17	Board Orientation:

- timeline established

- survey approved by the board

February 18	Job Posted on KASA site

February 20 	Survey link posted on school and district website

March 6	Community survey closes

March 17	Board work session:

- review survey results

- establish qualities

- designate the number of applicants expected to interview.

March 18	Application closes (5:00pm EDT)

March 21	Applications submitted to Board and Screening Committee

March 24 	Screening Committee Orientation and review of applications

March 31	Screening Committee meets to recommend applicants

March 31	Special Called Board Meeting

- receive screening committee recommendations

- add or delete applicants

- set interview dates

April 4	Finalist for interviews complete Gallup Strength Finder*

April 7	Strength Finder results to Board

April 14-16	Interviews

April 17-21	Contract negotiations

April 21	Board meeting to announce new superintendent.