COX’S CREEK ELEMENTARY SCHOOL

School Improvement Plan 2010-2012

Maximizing Potential for All!

Action Component: Academic Performance/Curriculum

District: Nelson 	Component Manager: Sonya Zielke	School: Cox’s Creek Elementary Date: November, 2010

| Priority Need | Goal (Addresses the Priority Need) |
| --- | --- |
| According to the 2010-2011 Interim Performance Report, Cox’s Creek Elementary School students performed at the following levels: Reading--80% scored Proficient and Distinguished with 2% scoring Novice Mathematics—80.8% scored Proficient & Distinguished with 3.6% scoring Novice Science—83% scored Proficient and Distinguished with 3% scoring Novice Social Studies—73% scored Proficient & Distinguished with 0% scoring Novice Writing/On-Demand—71% scored Proficient & Distinguished with 0% scoring Novice In order to continue to meet NCLB goals and continue improvement, Cox’s Creek Elementary School needs to be rated proficient/distinguished on the following Standards and Indicators for School Improvement: Standard 1: The school develops and implements curriculum that is rigorous, intentional, and aligned to state and local standards. | By April 2014, all students will score proficient in all areas. By 2012, the percentages of Proficient and Distinguished for Cox’s Creek Elementary School will exceed the NCLB yearly targets and will reflect the corresponding reduction in Novice in each subject area tested: Target performance levels: Reading—86% Prof & Dist with 0% Novice Writing On Demand—81% Prof & Dist with 0% Novice Mathematics—90% Prof & Dist with 2% Novice Science—90% Prof & Dist with 0% Novice Social Studies—90% Prof & Dist with 2% Novice . By 2012, the Cox’s Creek Elementary School will be rated Proficient/Distinguished on the following Standard and related Indicators. |
| Causes and Contributing Factors | Objectives with Measures of Success |
| A. 1. Curriculum, instructional delivery, and assessment do not reflect content integration and continuity that support student diversity and instructional best practice. | A. 1. By May, 2012, curriculum reflecting content integration, instructional best practice, and response to student diversity will be implemented and will be measured by lesson plans, curriculum units, curriculum maps, walkthrough observations, student work, and on-going assessment data (GRADE, GMADE, ThinkLink, SRI, common assessments.) |

Strategies/Activities

| Objective Label | Strategy/Activity | Expected Impact in Terms of Progress and Success | Responsible Person | Start Date | End Date |
| --- | --- | --- | --- | --- | --- |
| A1a | Teachers will participate in ongoing refinement of curriculum maps and related standards based unit development to create broad-based thematic units that integrate content and reflect instructional best practice through professional development, embedded PD, PLC meetings, faculty meetings. | Teacher-developed units built around school wide themes (Change, Adaptations, Systems, Patterns) will be used to deliver integrated content that is responsive to diverse student needs as evidenced by lesson plans, walk- throughs, and student work. | Principal, PD consultants, All teachers | 6/10 | 6/12 |
| A1b | Manipulatives, hands-on materials, kits, videos, and CD programs will be made available to enhance curriculum areas. A resource/inventory list will be made for each teacher and updated when new material is purchased and made available. | Materials and resources that support content units and instructional best practice will be available to provide effective instruction to students as evidenced by lesson plans, walkthroughs, and student work | Principal/media specialist/CRC/ Team leaders | 6/10 | 6/12 |
| A1c | Assessment data (ThinkLink, GRADE, GMADE, common assessments, etc.) will be analyzed regularly in team meetings, PLCs, embedded PD, and faculty meetings to monitor student progress and to plan curriculum/instruction adjustments and interventions. | Instructional adjustments will be made throughout each unit of study to monitor mastery and to provide diagnostic interventions based on performance data, fostering continuous progress of 1 month of growth for each month of instruction. | All teachers, Principal | 8/10 | 6/12 |
| A1d | Lesson plans and related curriculum documents will be reviewed and revised regularly to assure incorporation of instructional best practice, writing across the curriculum, regular use of OR, high level questioning, and appropriate accommodations (interventions and extenstions) to make content accessible to all students at all levels. | Groupings and instructional resources developed by collaborative teams will reflect individualized attention to the continuous progress of every student as measured by formative assessments, GRADE, GMADE, ThinkLink, Aimsweb, etc. | Principal, All teachers, Resource Teachers | 8/10 | 6/12 |

Action Component: Academic Performance/Instruction

District Name: Nelson Component Manager: Emily Borders	School Name: Cox’s Creek Elementary School 	Date : November, 2010

| Priority Need | Goal (Addresses the Priority Need) |
| --- | --- |
| Priority Need: In order to accomplish the NCLB goals, Cox’s Creek Elementary School needs to be rated proficient/distinguished on the following Standards and Indicators for School Improvement: Standard 3: The school’s instructional program actively engages all students by using effective, varied and research-based practices to improve student academic performances. | By 2012, Cox’s Creek Elementary School will be rated Proficient/Distinguished on the following Standard and related Indicators of the Scholastic Audit: Standard 3: The school’s instructional program actively engages all students by using effective, varied and research-based practices to improve student academic performances. |
| Causes and Contributing Factors | Objectives with Measures of Success |
| B. 1. Staff needs ongoing support in order to implement effective and varied classroom instructional methods. 2. Instruction is not consistently responsive to student needs to ensure continuous progress. 3. Increasing range of needs of students requires continual instructional refinement, analysis, and accountability. 4. Student performance on open response and on demand writing does not match their levels of performance on multiple choice. | B. 1. By May, 2012, teachers will consistently implement a variety of best practice instructional strategies as measured by lesson plans, intervention groups, open response and on demand samples, classroom observations and increased student achievement. 2. By May, 2012, students who need additional academic assistance and/or extensions will be identified and services will be provided as evidenced by intervention groups, ESS roster, Title I roster, iimproved ThinkLink, GRADE, GMADE, SRI, and common assessment scores. 3. By May, 2012, instructional groupings and differentiation strategies will be used consistently to facilitate continuous progress for all students as measured by pre-post assessments reflecting at least one (1) month growth for one (1) month of instruction. |

Strategies/Activities

| Objective Label | Strategy/Activity | Expected Impact in Terms of Progress and Success | Responsible Person | Start Date | End Date |
| --- | --- | --- | --- | --- | --- |
| B1a | Teachers will refine use of Best Practice strategies in all content areas through the use of hands-on activities, manipulatives, active engagement, and feedback strategies to guide student progress. Real world connections and high engagement activities in social studies and science will be emphasized. Levels of rigor and relevance will be improved for each teacher. | Students will demonstrate progress as teachers integrate differentiation, real-world connections, attention to learning styles, and instructional Best Practice strategies into instruction in all content areas as evidenced by lesson plans, teacher reflections, walkthroughs, student work samples, and assessment progress, reducing novice by 1% in all areas and reflecting 1 mon. growth for each month of instruction. Principal will monitor lesson plans and instruction for levels of rigor and relevance and personal growth goals established for each teacher. | District Resource Teachers/ Principal | 6/10 | 6/12 |
| B1b | Teachers will maintain a binder of Best Practice resources, including curriculum maps, open responses, on demand prompts, rubrics, and scoring guides. | Students will receive varied and effective instruction, including practice with open response 2x weekly and writing to proficiency as evidenced by lesson plans, learning stations, walkthroughs, student samples, progress within performance levels, and performance data that reflects at least 1 month growth for 1 month of instruction. | All teachers, CRC, Principal | 8/10 | 6/12 |
| B1c | Teachers will participate in workshops, embedded PD, and book studies in order to learn about, share, and implement instructional strategies. | Teachers will implement instructional strategies matched to student needs as evidenced by lesson plans, reflections, walkthroughs, and student work. | Principal, All Teachers | 8/10 | 6/12 |
| B1d | Teachers will develop articulated intervention plans and use diagnostic instructional groupings in all content areas, will use graphic organizer(s) and testing vocabulary for Open Response, implementation of engagement qualities, and refine implementation of Junior Great Books. | Students will receive instruction at the appropriate level and increase capacity to write proficient Open Response by receiving instruction based on high level thinking skills. Students will demonstrate improved comprehension and critical thinking skills as evidenced by GRADE reading scores, DRA, ThinkLink, SRI, and common assessments. Students will improve ability to write proficient open response as measured by reduction in number of students who score 0, 1, or 2 by 12%. | All teachers, Principal, CRC | 8/10 | 6/12 |
| B1e | Literacy Team, RTA intervention teacher, ESS assistants, and classroom teachers will provide support for continuous progress in reading, writing, and math. | Groupings based on pre-assessment for continuous progress, modeling, reading-writing connections, and vocabulary and comprehension instruction will be in evidence in lesson plans, learning stations, walkthroughs, and student work. Novice performance will be reduced by 1% in reading, writing, and math. Distinguished will be increased by 2% | Principal, all staff | 8/10 | 6/12 |
| B1f | Teachers will use common vocabulary and graphic organizers to support writing across the curriculum, 2x weekly use of Open-Response/open-response like writing; regular practice with On-Demand, Kentucky Marker Papers, and writing to proficiency. | All teachers will participate in on-going training in writing and will participate as portfolio buddies and in portfolio scoring as evidenced by student-teacher pairings and sign-in sheets. All teachers will incorporate OR and OR-like activities in all content areas as evidenced by lesson plans, walk-throughs, and student work samples. On-demand novice will be reduced by 1% and the number of students who score 0,1,2 on OR will be reduced by 12%. | Principal, Component Manager, all teachers | 8/10 | 6/12 |
| B1g | Collaboration time will be used to diagnose and address student needs and to develop common assessments, reflecting shared responsibility for student success. | Student progress will be monitored through ongoing data and teachers will design interventions that support continuous progress. Novice will be reduced by 1% in all content areas. PLC meetings will document use of assessment data and performance data to group and inform instruction | All teachers, Principal | 8/10 | 6/12 |
| B2a | Instructional technology will be utilized to support instruction through ongoing teacher training in technology. | Students will use diagnostic/intervention software aligned with identified student needs. (ThinkLink probes, ALS, related websites; etc.) Teacher data will reflect student progress and interventions. | All teachers, STC, CRC | 8/10 | 6/12 |
| B2b | Teachers will work in teams during faculty meetings, collaboration time, PLCs, and planning periods to analyze student work and diagnose intervention needs. | Instruction and assessment will demonstrate increased incorporation of purposeful strategies as evidenced by lesson plans, learning stations, walkthroughs, teacher products, assessments, and student work. Novice will be reduced by 1% in all content areas. | District resource personnel, all teachers, principal | 8/10 | 6/12 |
| B2c | At-risk readers will be targeted for reading interventions through Reading Recovery, Read to Achieve interventions, ESS, Breakfast Club, Study Buddies, Great Leaps, etc. | Student progress will reflect 1 or more months of progress for each month of instruction. | ESS teachers and assistants, all teachers, principal | 8/10 | 6/12 |
| B2d | Teachers will develop Intervention Plans to target specific student/curriculum needs. | Targeted students will demonstrate improved mastery of skills required for academic success as evidenced by anecdotal records, skills checklists, and testing, reflecting 1 or more months growth for each month of instruction. | All teachers, principal | 8/10 | 6/12 |
| B3a | Teachers will conduct and analyze ongoing assessments, including GRADE, GMADE, ThinkLink, Aimsweb, and common assessments. | Targeted student/curriculum needs will show improvement/gap reduction as evidenced by student work samples, ThinkLink testing, GRADE and GMADE tests; scrimmage testing, lesson plans and walk-throughs. | All staff | 6/10 | 6/12 |
| B3b | Staff will participate in training focused on gap issues (unique populations and student needs) ie: learning disabilities, behavior, ADD, ADHD, gender, economic status, etc. | Instructional strategies responsive to unique student needs will be used as evidenced by lesson plans, learning stations, walkthroughs, IEP documentation, and student work to reduce ESS and disability gaps by 2%. | All Teachers, Principal | 6/10 | 6/12 |
| B3c | Implement interest/content focused hands-on events to foster real-world connections (Career Day, environmental education, outdoor classroom, Agriculture Day, Kentucky Heritage and Pioneer Events, Science Club, Living History Club, economics activities, school newspaper, performance opportunities, etc.) | Students will participate in events focused on bringing resources and speakers in to the classroom; and will participate in follow-up activities across all content areas reflected in lesson plans, walk-throughs, and student work. Will reduce ESS gap and gender gap by 4% in all event areas. | Principal, all teachers | 5/10 | 6/12 |

Action Component: Learning Environment/Student Needs

District Name: Nelson County Component Manager: Susan Santa Cruz School Name: Cox’s Creek Elementary School Date : November, 2010

| Priority Need | Goal (Addresses the Priority Need) |
| --- | --- |
| In order to accomplish TEST goals, Cox’s Creek School needs to be rated proficient/distinguished on the following Standards and Indicators for School Improvement. Standard 4: The school/district functions as an effective learning community and supports a climate conducive to performance excellence. A. Consistent performance and behavioral expectations in the common areas throughout the school. | A. Our students will demonstrate grade level appropriate performance and behavioral expectations throughout the school learning community. |
| Causes and Contributing Factors | Objectives with Measures of Success |
| A.1. Student expectations vary from teacher to teacher and staff member to staff member and are not consistently modeled and reinforced. | A.1. Students will be made aware of performance standards and behavior expectations and will successfully self-assess performance through Learning for Life and CHAMPS/Champs-like assessments, rubrics, performance checklists, and reflection. |

Strategies/Activities

| Objective Label | Strategy/Activity | Expected Impact in Terms of Progress and Success | Responsible Person | Start Date | End Date |
| --- | --- | --- | --- | --- | --- |
| A1 | CHAMPS graphics and rules and positive behavior management expectations will be reviewed and reinforced to ensure consistent leadership/behavioral expectations across all settings. | Bulldogs skills taught and reinforced throughout the building; multiple positive contingency plans in place; Classroom on-task behavior and work completion will increase by 5% and office referrals decrease by 5%. | Principal, STAT team, counselor, teachers | 8/10 | 8/12 |
| A2 | Standards in the form of I Can statements will be posted and referred to during instruction and coverage will be documented to assure Core Content 4.1 coverage prior to testing. | Students and teachers will identify instructional and behavior standards as evidenced by lesson plans, posted I-Can statements, lesson closure, and dating of standards in maps. | All staff | 5/10 | 8/12 |
| A3 | STAT plans will be developed for students who experience on-going behavioral and/or academic difficulties. | Targeted students will improve behaviorally and academically as measured by office discipline referrals, TEST, scores, grades, and behavior data. RTI pyramid of interventions will be refined and applied to address the needs of students to improve academic and behavioral performance. | Principal, STAT team, CCES special education teachers | 8/10 | 8/12 |

Action Component: Learning Environment/Student Needs

Component Manager: Susan Santa Cruz	School Name: Cox’s Creek Elementary School 	     Date: November, 2010

| Priority Need | Goal (Addresses the Priority Need) |
| --- | --- |
| In analyzing 2010 test Data the following needs were identified: Performance Gaps were identified among our students with disabilities in Science, Math, and Reading; and between males and females in reading, science, and in On-Demand Writing.. Standard 5: The School /district works with students, families, and community groups to remove barriers in an effort to meet the intellectual, social, career, and developmental needs of students and provide equitable opportunities for all students. | D. To provide adequate students support services and remove barriers to learning. |
| Causes and Contributing Factors | Objectives with Measures of Success |
| B. 1. Wide range of student needs creates a need for support services that are not yet adequately supporting all students so they can succeed academically and behaviorally. | B. 1. By May, 2012, services and practices will be in place to support all students so that they can be successful academically and behaviorally as measured by grades, test scores, and discipline records. 2. By May, 2012, the performance gap for students with disabilities will be reduced by 4% and the gender gap for males will be reduced by 4% in reading and the gender gap for females in science will be reduced by 4%. |

Strategies/Activities

| Objective Label | Strategy/Activity | Expected Impact in Terms of Progress and Success | Responsible Person | Start Date | End Date |
| --- | --- | --- | --- | --- | --- |
| B1a | Target students for interventions and reading programs utilizing several assessment sources and develop a focused intervention program. | Progress will be assessed through pre and post tests. GRADE, GMADE, ThinkLink, running records, anecdotal data and targeted interventions implemented. Students will demonstrate a minimum of 1 month growth for 1 month of instruction in all content areas. | ESS Coordinator, All teachers, Daytime waiver staff | 8/10 | 6/12 |
| B1b | At-risk students will be identified for targeted instruction in basic skills. | Targeted students will participate in diagnostic interventions to address basic skills in reading, writing, and math. | All teachers, | 8/10 | 6/12 |
| B1c | Family Resource support (school supplies, clothing needs, referrals to community support services, parent education) will be utilized for students and families who need services | Targeted students will demonstrate increased mastery of basic skills to improve school achievement as measured by anecdotal records, skills checklists, attendance, and test scores | Principal; Guidance Counselor, Family Resource Center, Psychologist | 8/10 | 6/12 |
| B1d | The FRYSC, Title I, and school will offer Family Math, Science, and Family Literacy Nights and workshops for parents to bridge performance gaps. | Increased family and student support services will result in higher student achievement as measured by test scores and improved classroom grades. | Family Resource Center Title I teachers | 8/10 | 6/12 |
| B1e | A Parent’s Bookshelf on homework, discipline, and learning strategies will be expanded. | Increased parent involvement will result in higher student achievement as measured by grades, test scores, and improved behavior as measured by discipline referrals. | PTO/Family Resource Center | 8/10 | 6/12 |
| B1f | Design units and implement strategies which include facilitate continuous progress for all, including talent pool/gifted students. | Identified students will increase achievement as measured by test scores. | CRC, collaboration resource teachers, all teachers | 8/10 | 6/12 |
| B1g | Purchase high interest reading materials targeting male and low SES students at Breakfast Club; Make reading materials available in all homes. Provide leadership opportunities on school newspaper and video reporting to promote on-demand writing. | Increased motivation, increased access, and improved reading strategies will lead to increased confidence and reading achievement as measured by GRADE, GMADE, running records, SRI. Targeted students will increase reading and writing performance by 2%. | Librarian/Principal, Literacy Team | 8/10 | 6/12 |
| B1h | Volunteer tutoring will be made available for students who need extra assistance. (Study Buddies, Great Leaps Reading and Math) | Identified students’ scores will improve as measured by GMADE, GRADE, ThinkLink, running records, and common assessments by 2%. | Component Manager, Principal | 8/10 | 6/12 |
| B1i | All students will have frequent performance and audience opportunities with emphasis on integration of Arts and Humanities concepts. | Students will use A & H concepts in performance, in discussion, in writing, and with technology support as measured by common assessments. A & H concepts will be related to science and social students in order to engage and to make real-world connections. | All teachers; principal; related arts team | 8/10 | 6/12 |