| DISTRICT NAME | Bellevue Independent Schools |
| --- | --- |
| LOCATION | Bellevue, Kentucky |
| PLAN YEAR(S) | 2025-2026 |

|  |  | www.bellevue.kyschools.us |
| --- | --- | --- |

## Table of Contents

Table of Contents

Planning Team

Previous Year’s Strategies Evaluation

Upcoming Year’s Strategies Preview

Student Voice

KETS Master Plan Areas of Emphasis
      Collaborative Leadership

Robust Infrastructure & Ecosystem

Data Security, Safety, Privacy & Use

Budget & Resources

Partnerships

Digital Learning, Curriculum, Instruction & Assessment

Personalized Professional Learning

Use of Space & Time

## Planning Team

| District Staff [Recommended to include CIO/DTC, DLC, technician, finance officer, superintendent, academic officer, DAC, etc.] |  |
| --- | --- |
| Jim Seward, Director of Technology | Misty Middleton, Superintendent |
| Emma Barrett, Desktop Technician | Tiffany Hicks, Assistant Superintendent |
| Building Staff [Recommended to include principals, LMS, STC, counselors, teachers, teaching assistants, etc.] |  |
| Scott Spicher, BMHS Principal | Susan Short, Grandview Elementary Principal |
| Additional District Contributors [Recommended to include board members, SBDM members, program directors, etc.] |  |
| Students [Recommended to include middle and/or high school students ] |  |
| Other [parents/community members, business and nonprofit leaders, etc. ] |  |

## Previous Year’s Strategies Evaluation

In this section include a discussion of the previous year’s strategies using the prompts below. Attempt to limit your narrative to the space provided.

The previous plan included a goal to increase the number of mobile student devices. As of the 20-21 school year, BISD is a 1-1 district! We have iPads available for PK-2, Chromebooks for 3-5 and Winbooks for 6-12! Staff desktops have been replaced with 2-1 laptops for maneuverability around the building, as well as their classroom. Another goal was for teachers and staff to be provided increased professional development opportunities to address their technology needs. Staff will continue to attend technology-related training in the district, in the local community and at state conferences. This will continue to be an area of emphasis moving forward. Specifically, all grade level school teachers have implemented Google Classroom The previous plan included a goal to implement research based instructional software into the classrooms. Although we are implementing a variety of instructional software, we need to do a better job of evaluating the instructional effectiveness of each program. Audit of existing software use in both buildings: How are they being used? Are they being used? What instructional benefits exist for each resource? When does technology enhance instruction vs. just replacing paper/pencil? Use of clever

## Upcoming Year’s Strategies Preview

If this is the first year of a multi-year plan, this section acts more like an executive summary of the plan as a whole. If this is the second or third year of a multi-year plan then aim your discussion to any new strategies or adjustments you are planning for this year.

[See Technology Planning section of KETS Master Plan for more information]

Our team met and discussed the previous year’s plan. We have adjusted to reflect changes that have occurred and what possible changes that each school building is anticipating for the coming year(s).

The 2025-2026 technology plan was developed through a collaborative effort involving Grandview Elementary and Bellevue Middle/High schools. It includes goals and strategies for addressing the Area of Emphasis identified in the KETS Master Plan. Specific needs were determined by each school’s administrative team and the District Tech Team. . The committees utilized key findings to identify strengths and/or areas for improvement. The technology plan was then developed with goals, objectives and activities specific to each school. The district plan is a compilation of each school’s plan along with additional district initiatives. The CIO along with each school’s administrators will monitor the implementation and impact of the plan. The district technology goal is to provide our students a strong foundation in the utilization of technology. For innovative and effective teaching and learning to occur, every classroom is currently equipped with televisions and/or interactive displays and mobile document cameras. Student performance is measured through the use of online assessments such as MAP, TestNav, and software-specific content assessments. These tests are administered via online platforms utilizing a variety of devices. The district communicates with parents and the larger community through the district and school websites, email, phone system, Facebook, Twitter, Infinite Campus parent portal, district mobile app and the IC mobile app. Our continued goal is that information is available at all families’ convenience. The district has an updated infrastructure with wireless connectivity, inventory management and a mobile device management solution. The wireless network was updated in the 21-22 school year. This has resulted in a more reliable internet experience along with an increase in the use of mobile devices across the district. Our goal is to continue to increase the density of the wireless network with additional access points. The district plans to upgrade the network backbone in 25-26. This includes all data closets throughout the district. Existing equipment is reaching end-of-life and will be replaced with more robust technology to meet our ever-changing needs. The district put our leased fiber connection out to bid in 2024. This connection serves our gymnasium. This connection will run from our data center to the gymnasium. With the E-rate bid we were able to see a cost saving on a new multiple year contract. AI should be used in schools to support learning, enhance creativity, and provide personalized education experiences while ensuring ethical use and data privacy. As this is emerging, we are continuing to grow and learn with the process.

## Student Voice

Personalized learning allows students to develop deeper learning competencies including critical thinking, using knowledge and information to solve complex problems, collaboration, and communication. Capturing student input about their access to opportunities that build these competencies is key to effective technology planning.  Please answer the questions in the space provided below.

We have a very limited method to collect student voices for this purpose. The goal is to explore methods for collecting the students’ voice and begin collecting this data during the 2025-2026 school year. We are looking to review BrightBytes, Google Docs or Online IC Registration to collect and analyze captured student data.

Some items we are looking to collect and include; home internet access (we are collecting this information with OLR), software usage, computer literacy, social-emotional learning, and more.

## KETS Master Plan Areas of Emphasis

Connected to the Future Ready Framework

The Future Ready Framework identifies eight Gears to assist districts in developing a roadmap for student success through personalized student learning and collaborative leadership. The KETS Master Plan has identified 44 Areas of Emphasis connected to the Future Ready Framework and are categorized as either 1) Acceleration Area (AA) or 2) Growth Opportunity Area (GO). The “acceleration areas” are considered big wins, successes, and major milestones of the KETS are identified for continuation work. The “growth opportunity areas” address improvement targets for the Master Plan.

Use the Areas of Emphasis and Future Ready Framework as a lens to analyze current trends, initiatives, needs and goals of your district. Link the work of this new plan identified by your planning team to the Gears and Areas of Emphasis of the KETS Master Plan on the following pages. There is no expectation to address all 44 Areas of Emphasis of the KETS Master Plan. Any strategy that involves Erate, please include in the Budget & Resources gear. If your district has lease agreements (i.e.; device, fiber, etc.), be prepared to reference the quantity during the final submission process.

|  | ### Collaborative Leadership Future Ready Gear |
| --- | --- |
| KETS GUIDING PRINCIPLE – Collaborative leadership creates a shared vision of digital teaching and learning, an environment of collaboration (where partners make stuff together), encourages embracing innovation and empowerment, and a culture of evidence-based systems and processes. |  |

Areas of Emphasis: Acceleration Area (AA) /Growth Opportunity Areas (GO)

| AA-1 | Continue to use structures providing opportunities for feedback from shareholders and evidence of how KETS systems and processes are working or not working (360 feedback, CIO Summit) |
| --- | --- |
| AA-2 | Continue the fostering of strategic partnerships and collaborations among educational institutions, technology companies, policymakers, and community organizations. Develop networks that facilitate knowledge exchange, collaborative research, and resource-sharing to promote innovation and address common challenges in education technology. |
| AA-3 | Continue the recognition and support for the crucial role of teachers as leaders in educational technology integration. Provide professional learning opportunities and resources that enable teachers to develop expertise in leveraging technology to enhance instruction and student engagement. |
| GO-1 | Improve collaboration among educators, technologists, administrators, and researchers to foster a holistic approach to education technology development, implementation, and evaluation. Encourage open channels of communication and provide platforms for sharing best practices, ideas, and resources across different disciplines and institutions. |

| KETS AA or GO | Strategy/Action Item | Person(s) Involved | Anticipated Timeframe | Anticipated Funding Source | Anticipated Funding Amount | How will you know this is successful? (including metrics) |
| --- | --- | --- | --- | --- | --- | --- |
| AA-2 | Continue to implement a 5- year replacement plan for replacement of student/staff devices | DTC | Annually | General Fund KETS Title 1 | $75,000 | New devices ordered for K/3, 6, 9 each year. End of life devices will be surplused. |
| AA-3 | Increase the density of the wireless network for BISD with additional access points | DTC Tech Team | July 2025-August 2025 | General Funds | Erate funding has been requested | Continue to monitor for areas to improve coverage. |
| AA-4 | Continue to improve teacher use of Infinite Campus | DTC IC Coor | Ongoing | State Provided |  | -Improved communication with parents/students. -Accurate Data |
| AI-1 | Ongoing evaluation of current technologies available at BISD, for staff and students | Principals DTC | Ongoing | General Fund KETS Grants Donations | $50,000 | -Technology will continue to function with limited disruptions -Technology will meet the growing needs of staff/students |
| AA-3 | Replace all MDF/IDF closets with new switching equipment. Including core router and wireless | DTC Finance | July 2025-August 2025 | KETS ERate | Erate funding has been requested | -Improved network speeds -More secure -It will meet the needs of the district for the next 5 years. |
| AA-1 | Security Camera and systems | DTC Operations Director | August 25 – May 26 | General Funds Safe Schools | $10,000 | Continued improvement of security system. Reviewing camera placement. Additions/subtractions as warranted. |
| AA-4 | Alternative Teaching Technologies -Oculus, Microscope cameras, robotics | School Admin DTC | August 25 – May 26 | SBDM Grants | $25,000 | Develop a new curriculum that aligns with standards to provide a different approach to learning. |
| AA-4 | Various Educational Software | Academic Dir | August 25 – May 26 | Title 1 Grants General Fund | $5,000 | Lesson Plans Student work |

|  | ### Robust Infrastructure & Ecosystem Future Ready Gear |
| --- | --- |
| KETS GUIDING PRINCIPLE – A robust infrastructure delivers the device, identity, network, leadership, and support needs of staff and students to create personalized learning environments using digital tools and resources. |  |

Areas of Emphasis: Acceleration Area (AA) /Growth Opportunity Areas (GO)

| AA-1 | Continue to provide nation’s first, fastest, highest quality, and most reliable and secure internet access to 100% of Kentucky’s public schools |
| --- | --- |
| AA-2 | Continue to ensure equity and standardization for delivery of device, network, data and support creating best in class staff and student digital experiences AND provide a system of shared/brokered/managed services maintaining low infrastructure costs and providing support structures promoting the use of personalized learning environments |
| AA-3 | Continue to provide digital equity and foster a culture of digital connectedness for students and staff by ensuring access to a 1:1 device assignment, prioritizing mobile devices over traditional computer labs, and providing consistent Wi-Fi coverage throughout schools. This approach emphasizes always-on, everywhere seamless digital opportunity and access, and includes an emphasis on empowering schools/districts to have a full understanding of digital access beyond the campus |
| AA-4 | Continue to encourage the use of instructional programs and administrative processes requiring cloud-based services |
| AA-5 | Continue to implement efficient and effective interoperability strategies with statewide, districts, and schools EdTech systems and platforms (including integrations and seamless data exchange). Interoperability strategies aim to enhance user experiences and drive administrative efficiencies with education technologies. |
| GO-1 | Improve responsive EdTech support systems by securing leadership positions designed to make decisions to improve teaching and learning through technology integration. This role outlines the district’s vision for education technology, implements digital learning strategies, and ensures that technology resources align with students’ learning needs. Responsibilities and expectations are primarily focused on understanding the educational needs and challenges of the district with a “seat at the table.” Responsibilities would likely include influencing district-level budget conversations, leading planning efforts, research, procuring state and federal program funding, and establishing overall direction and vision of using technology for school efficiencies and instruction/learning. |
| GO-2 | Improve formal cycles for review, refresh, and replacement - ensure upgrades, additions, and when called for, sunsetting/eliminations in a timely, environmentally responsible and proactive manner of devices, infrastructure, and digital tools and resources. Where possible, teams make concerted efforts to automate systems to drive effectiveness and efficiency. (This is also connected to budget gear) |

| KETS AA or GO | Strategy/Action Items | Person(s) Involved | Anticipated Timeframe | Anticipated Funding Source | Anticipated Funding Amount | How will you know this is successful? (including metrics) |
| --- | --- | --- | --- | --- | --- | --- |
| AA-2 | Continue to implement a 5- year replacement plan for replacement of student/staff devices | DTC | Annually | General Fund KETS Title 1 | $75,000 | New devices ordered for K/3, 6, 9 each year. End of life devices will be surplused. |
| AA-3 | Increase the density of the wireless network for BISD with additional access points | DTC Tech Team | July 2025-August 2025 | General Funds | Erate funding has been requested | Continue to monitor for areas to improve coverage. |
| AA-4 | Continue to improve teacher use of Infinite Campus | DTC IC Coor | Ongoing | State Provided |  | -Improved communication with parents/students. -Accurate Data |
| AI-1 | Ongoing evaluation of current technologies available at BISD, for staff and students | Principals DTC | Ongoing | General Fund KETS Grants Donations | $50,000 | -Technology will continue to function with limited disruptions -Technology will meet the growing needs of staff/students |
| AA-3 | Replace all MDF/IDF closets with new switching equipment. Including core router and wireless | DTC Finance | July 2025-August 2025 | KETS ERate | Erate funding has been requested | -Improved network speeds -More secure -It will meet the needs of the district for the next 5 years. |
| AA-1 | Security Camera and systems | DTC Operations Director | August 25 – May 26 | General Funds Safe Schools | $10,000 | Continued improvement of security system. Reviewing camera placement. Additions/subtractions as warranted. |
| AA-4 | Alternative Teaching Technologies -Oculus, Microscope cameras, robotics | School Admin DTC | August 25 – May 26 | SBDM Grants | $25,000 | Develop a new curriculum that aligns with standards to provide a different approach to learning. |
| AA-4 | Various Educational Software | Academic Dir | August 25 – May 26 | Title 1 Grants General Fund | $5,000 | Lesson Plans Student work |

|  | ### Data Security, Safety, Privacy & Use Future Ready Gear |
| --- | --- |
| KETS GUIDING PRINCIPLE – Strategic use of student data is a cornerstone of digital learning and must be done securely, safely, and with a focus on maintaining privacy. Laws, policies, and procedures are enacted at the federal, state, district, and school levels that work in conjunction for this purpose. Student data are then utilized by security-aware, data-fluent, and data-informed educators for improved decision making leading to increased learning for students. |  |

Areas of Emphasis: Acceleration Area (AA) /Growth Opportunity Areas (GO)

| AA-1 | Continue to support districts in securely accessing and managing key student and administrative data sets through improved user experiences, refined data collection processes, continuously updated policies and practices regarding student data security, and timely access to data sets that improve the depth and efficiency of student learning (Infinite Campus, Early Warning, MUNIS, eTranscripts, School Report Card) |
| --- | --- |
| AA-2 | Continue to identify key aspects of data security regularly to build upon the current systems, procedures and policies to remain a leader in mitigating emerging threats (acceptable use policies, firewall updates, data privacy studies, digital citizenship, content filtering) |
| AA-3 | Continue to utilize adoption metrics or trending data for planning purposes that allow EdTech and instructional leaders to identify what’s working and what’s not working based upon data quality and evaluate current systems and solutions to determine the effectiveness and future direction (annual auditors, Impact survey, Technology Activity Report, Digital Readiness, Data Quality Study, Data Quality Campaign, SpeakUp) |
| AA-4 | Continue to migrate key administrative and student data sets to secure cloud providers that allow everywhere, all-the-time secure access for the improvement of student learning (Infinite Campus, Early Warning, School Report Card, MUNIS) |
| GO-1 | Educate and support districts in the importance of personnel with duties related to student/staff data quality, security and privacy as well as bringing data privacy to the “radar screen” of teachers/staff (The People Side of EdTech) |
| GO-2 | Improve and enhance the tools available to maximize the use of data through enhanced reporting, tools that help improve data quality, and visual data analytic tools. Kentucky K-12 data systems are first-class, and we need enhanced tools to create a more usable and more interesting story for the average person who may not have a technology and data background. |

| KETS AA or GO | Strategy/Action Items | Person(s) Involved | Anticipated Timeframe | Anticipated Funding Source | Anticipated Funding Amount | How will you know this is successful? (including metrics) |
| --- | --- | --- | --- | --- | --- | --- |
| AA-1 | Continue to support schools in ensuring the privacy of student data through the monitoring and refining of user IC rights | District IC Coor | Annually | N/A |  | IC user rights will display an appropriate but limited number of users for each tool. |
| AA-3 | DTC will review and update the Acceptable Use Policy and the district’s data privacy policy. The Board of Education will be briefed on the district’s data security procedures annually. | DTC | Annually | N/A |  | AUP is updated and will be noted in BOE meeting minutes. |
| AA-5 | All students in K-5 will participate in lessons involving appropriate online behavior, social networking and cyberbullying prevention. | Media Specialist | Ongoing | N/A |  | Lesson plans and observations of student use will demonstrate lessons taught. |
| AA-5 | Teachers will instruct students on the use of technology in an appropriate, safe and responsible manner. Students will use appropriate behavior to related to acceptable technology etiquette, internet safety and good | Bldg. Principals Teachers | Ongoing | N/A |  | 100% signed AUP. Lesson Plans Observation of student tech usage. |
| AI-1 | Special Education Director will provide confidentiality training to all staff including data security and privacy per FERPA | Director of Special Populations | 2x a Year | N/A |  |  |
| AA-1 | CUES Project | DTC | 2025 | State | State | Implement a more robust type of single sign on to support our students and staff. |
| AA-1 | PhishID | DTC | 2025 | State | State | Implemented tool to help protect our staff from Phishing attempts. In collaboration with the CUES project. |
| AA-2 | CISA | DTC | Ongoing |  | Free Federal Program | Continue to monitor our weekly CISA report to help ensure that our network is meeting security requirements. |

|  | ### Budget & Resources Future Ready Gear |
| --- | --- |
| KETS GUIDING PRINCIPLE – The Master Plan, as well as district and school technology plans, are aligned to the vision for digital teaching and learning for students and staff. Revenue streams are aligned to account for the recurring and nonrecurring total cost of ownership to support the modernized and personalized learning experiences (and environment) in a manner that reflects good stewardship of tax dollars to include devices, infrastructure, support, data and human capital services. (i.e. The People Side of EdTech) |  |

Areas of Emphasis: Acceleration Area (AA) /Growth Opportunity Areas (GO)

| AA-1 | Continue to maximize local and state education technology expenditures through a system of shared/brokered/managed services |
| --- | --- |
| AA-2 | Continue use of long-term planning strategies that allow for continuity of initiatives and systems (ex. Accounting for cost of ownership over the lifespan of equipment so monies are allocated for repairs/upgrades) |
| AA-3 | Continue to leverage all available state and federal funding opportunities to address required basic cost of living increases, previous budget cuts of basic services, projected growth by districts (e.g. Internet consumption) while maximizing education technology programs and initiatives (Technology Need, E-rate) |
| GO-1 | Educate districts on the ongoing cost of position/roles requiring technology-related duties in support of technology and instruction as well as modern drivers that require differentiated and strategic staffing models (The People side of K-12 EdTech |
| GO-2 | Educate districts on how to reduce expenditures on printing/print services (both in consolidated contract pricing as well as shifting from paper to digital experiences) |
| GO-3 | Evaluate the need and explore new contracts that drive costs down for statewide summative online assessment, learning management systems, printing services and interim based assessments |
| GO-4 | See an increased percentage of districts examining which education technology investments are or are not being maximized (through adoption, frequency of use, and impact) |

| KETS AA or GO | Strategy/Action Items | Person(s) Involved | Anticipated Timeframe | Anticipated Funding Source | Anticipated Funding Amount | How will you know this is successful? (including metrics) |
| --- | --- | --- | --- | --- | --- | --- |
| AA-3 | Continue to collaborate with district leaders to maximize available funds and consolidate funding to meet the technology needs of the district. | Superintendent DTC Academics Dir SpEd Dir Finance | Ongoing | General Fund Erate KETS Grants IDEA | N/A | Purchase Order Finance Report |
| AI-4 | Evaluate the usage of software purchased throughout the district to determine future funding needs. | Principals Academic Dept. | Ongoing | N/A |  | Use software analytics (Clever) to determine a baseline report for software usage. |
| AI-3 | Leverage Papercut to reduce monthly printing costs. | DTC Finance | Ongoing | N/A |  | Monitor monthly reports and look for ways to improve efficiency. |
| AA-1 | Maximize Erate Funding | DTC Finance Superintendent | Ongoing | Fed Gov | $100,000 (5 years) | Maximize federal dollars to continue to support our connectivity via point to point connections, networking, data, UPS, etc. |
| AA-1 | Maximize KETS Funding | DTC Finance Superintendent | Ongoing | State | $24,000 | Continue to match district funds to state funds to support technology cycles, upgrades, software, etc. |

|  | ### Partnerships Future Ready Gear |
| --- | --- |
| KETS GUIDING PRINCIPLE – Connecting students, leaders, and educators to the local and global community is a key factor to student success. The Master Plan will continue to provide opportunities for trusted relationships to build those connections as well as increase communication and transparency with shareholders, including families, districts, vendors, regional education collaboratives, postsecondary institutions, public libraries, and business/industry, in support of student learning and preparation beyond K-12. |  |

Areas of Emphasis: Acceleration Area (AA) /Growth Opportunity Areas (GO)

| AA-1 | Continue to build trusted relationships with shareholders (families, districts, partners) to increase engagement, outreach, and connecting classroom experiences outside of school. (districts, vendors, higher-education, regional education cooperatives, KET, KyVL) |
| --- | --- |
| AA-2 | Continue to utilize avenues of communication with shareholders allowing pertinent information and dialog to further student learning efforts (Webcasts, Technology Activity Report, KETS Service Desk, Office of Education Accountability studies, independent studies, etc.) |
| AA-3 | Continue to utilize tools engaging postsecondary institutions, community members, districts and families in student learning and life after K-12 (eTranscripts, School Report Card and Dashboard tool, Infinite Campus parent and student portal, KDE Open House, Digital Readiness Survey) |
| GO-1 | Partner with postsecondary pre-service teacher and principal programs to provide support in candidate preparation, especially in regard to student project-based demonstrations of technology competencies; get more students on college/university campuses while they are a K-12 student. Encourage postsecondary institutions (as well as other partners) to host STLP events and/or fully maximize the opportunity to showcase the university and its programs while students are on campus |
| GO-2 | Improve access to resources and professional learning for district-based online/virtual and remote learning programs to engage in continuous improvement in order to create high-quality online learning experiences for students |

| KETS AA or GO | Strategy/Action Items | Person(s) Involved | Anticipated Timeframe | Anticipated Funding Source | Anticipated Funding Amount | How will you know this is successful? (including metrics) |
| --- | --- | --- | --- | --- | --- | --- |
| AA-3 | Continue to utilize avenues of communication with our families through technology. | DTC Principals | Ongoing | General Fund | $10,000 | District wide use of email, IC, website, to communicate relevant information to students, parents, community |
| AA-3 | Provide parent information and assistance in accessing student information through IC parent portal and other communication avenues (open houses, newsletters, conference, social media) | Principals Teachers Comm Dir | Ongoing | N/A |  | An increase of 10% in the IC usage reports for parental accounts. Monitor analytics with Apptegy and mobile app downloads. |
| AI-2 | Continue to encourage STLP students to participate in the regional and state events. | DTC Principals Teachers | Ongoing | General Fund | $3,000 | Increase in the number of STLP students. |
| AA-1 | Continue to use Clever platform to help with secure access to 3rd party applications | DTC Principals IC Coord | Ongoing | N/A |  | Improved efficiency of log in times. Improved database updates during summer. |
| AA-2 | Attend KAST conference each year. | DTC Bldg Admin Finance | March 2026 | General Funds | $1250 per | The state’s premier technology and education conference. The goal is to have the technology department, media specialist and other teachers attend. |
| AA-2 | NetAdmin Meetings | DTC Technology | Monthly | Tech Budget | $2,500 | Continue to meet with other regional schools for continued professional development. |
| AA-1 | Vendor Fair | DTC | October 2025 |  |  | Attend the annual Vendor Fair with my region. Develop vendor partner relationships and monitor new product lines. |

|  | ### Digital Curriculum, Instruction & Assessment Future Ready Gear |
| --- | --- |
| KETS GUIDING PRINCIPLE – A digital learning experience is fostered by a teacher or coach with the use of rich digital instructional materials that are vetted to the rigor of Kentucky Academic Standards (KAS). A robust digital environment provides students with the opportunity to assess their own learning/progress towards mastery of content/skills or utilize instructional technology to provide timely feedback that moves learning forward. Digital curriculum and instruction can also provide students the opportunity to create digital products showcasing a deep understanding of core competencies of every subject, demonstrating mastery of Kentucky Academic Standards for Technology, and utilizing digital collaboration tools that provide a realistic connection to postsecondary and career readiness. |  |

Areas of Emphasis: Acceleration Area (AA) /Growth Opportunity Areas (GO)

| AA-1 | Continue to provide access to high-quality learning experiences which further aligns to the Kentucky Digital Learning Guidelines |
| --- | --- |
| AA-2 | Continue to promote, for ALL students, the use of Kentucky-approved/adopted Kentucky Academic Standards (KAS) for Technology, KAS for Computer Science, and KAS for Library Media Learning (all based on national and international learner standards) |
| AA-3 | Continue providing opportunities for students to demonstrate learning connected to and through KAS for Technology, KAS for Computer Science, and KAS for Library Media Learning (empowering students through technology with STLP, CS/IT Academy, etc.) |
| AA-4 | Continue to provide efficient and effective access to online assessment tools that allow teachers and administrators to assess student learning, provide timely feedback to students, and make curriculum decisions (online formative assessment tools, interim based assessments, and summative assessments) |
| AA-5 | Continue to provide districts/classrooms access to high-quality and effective digital instructional materials through an equitable and robust digital experience |
| AA-6 | Continue to support teacher efforts in taking ownership of digital citizenship skills and educating their students in the same skills to foster a responsible, safe, secure, and empowered digital learning environment. |
| AA-7 | Continue to play a vital role in implementation of summative online assessment and school report card |
| AA-8 | Continue to create a closer connection with Career and Technical Education to explain computer science career pathway offerings specifically related to computer programming/coding and increase valuable industry-level certifications and exams available through the CS & IT Academy |
| GO-1 | Identify high-quality digital content and tools (curriculum, instruction and assessment) designed to have the highest impact and value (e.g. is the technology making or not making an instructional and learning difference?), including frequency of use by teachers and students |
| GO-2 | Encourage, engage, and empower the safe and responsible uses of Artificial Intelligence (AI) into school efficiency and the learning space by teachers and students (ensuring humans remain in the loop with strong AI implementations) |

| KETS AA or GO | Strategy/Action Item | Person(s) Involved | Anticipated Timeframe | Anticipated Funding Source | Anticipated Funding Amount | How will you know this is successful? (including metrics) |
| --- | --- | --- | --- | --- | --- | --- |
| AA-1 | Teachers will evaluate, select, and utilize updated software in their lessons. | Academic Dir Principals Teachers | Ongoing | General Fund | $10,000 | Usage reports and increase in student’s reading proficiency. |
| AA-2 | Students will select and use available technology to complete assignments and projects | Teachers Principals | Ongoing | N/A |  | New and updated software Lesson Plans |
| AA-2 | K-5 students will continue to be introduced to coding with multiple technology avenues (Ozobots, Dash and Dot, robots, Spheros, etc). | Media Specialist | Ongoing | General Fund KETS | $5,000 | Coding activities in lesson plans Classroom observations |
| AA-2 | Teachers will develop interactive lessons to assist students in gaining confidence in the use of technology. Students will use a variety of technology to demonstrate competence in the area of technology. | Teachers Academic Dir | Ongoing | N/A |  | Lesson plans Formal and informal observations Student assignments and projects |
| AA-2 | Students will have an opportunity to expand their knowledge and experiences With technology through membership in the STLP program. | STLP | Ongoing | General Fund | $2,000 | 10% increase in club memberships Participation in local, regional, and/or state events. |
| AA-4 | Students will be assessed via the MAP assessment 3x a year. Teachers will interpret and utilize MAP data to drive instructional decisions. | Academic Dir Principals Teachers | August 25 – May 26 | General Fund | $3,500 | Testing schedules Assessment results RTI documentation and schedules |
| AA-4 | Students in grades 6-12 will use IXL to reinforce math concepts to address RTI needs | Principals Teachers | August 25, - May 26 | Title 1 | $3,000 | Usage reports Assessment results Math RTI schedules |
| AA-5 | Students in grades K-5 will use the I-Ready program to reinforce math and reading standards. | Principals Curriculum Team Teachers | August 25 – May 26 | General Funds | $11,500 | Lesson Plans Usage Reports Team meetings |
| AI-1 | Evaluate, purchase and implement educational iPad applications to increase personalized learning opportunities | Principals Coaches Teachers | Ongoing | Pilot Program General Fund IDEA | $5,000 | Approved iPad apps will be purchased and available on student iPads. |
| AI-1 | Evaluate, purchase and implement STEAM related devices and software (coding software and robots, 3D printers, etc.). | Principals DTC Media Specialist Teachers | August 25 – May 26 | General Fund Grants | $10,000 | Increase in STEAM devices Lesson Plans Tech Clubs and STLP projects |
| AI-1 | Update existing educational software and evaluate new | DTC Net Admin | August 25 – May 26 | General Fund Grants | $10,000 | Software will be the latest version. |

|  | ### Personalized Professional Learning Future Ready Gear |
| --- | --- |
| KETS GUIDING PRINCIPLE – Digital learning expands the access to quality strategies and experiences for educators beyond the traditional methods of professional development. A culture of digital collaboration, workflow and relationships allows educators to build skill sets and instructional best practices with colleagues globally. This approach of increased access and flexibility for professional learning ultimately leads to greater success for students. |  |

Areas of Emphasis: Acceleration Area (AA) /Growth Opportunity Areas (GO)

| AA-1 | Continue building a culture of digital collaboration and connected digital relationships that allow administrators to support and encourage the use of digital tools by staff for professional learning |
| --- | --- |
| AA-2 | Continue to promote and support the design and implementation of coaching models as a high-quality professional learning strategy (digital learning coach network, STLP coach network, etc) |
| GO-1 | Provide districts with guidance and support to determine the learning needs of teachers resulting in high-quality professional learning opportunities related to digital curriculum and learning tools |

| KETS AA or GO | Strategy/Action Item | Person(s) Involved | Anticipated Timeframe | Anticipated Funding Source | Anticipated Funding Amount | How will you know this is successful? (including metrics) |
| --- | --- | --- | --- | --- | --- | --- |
| AA-1 | Teacher’s and administrator’s technology literacy will be assessed per the district evaluation instrument and professional development needs will be identified. | Superintendent Academic Dir Principals | Ongoing | N/A |  | A list of identified needs for the technology related PD will be developed. PD opportunities will be offered based on need. |
| AA-1 | Curriculum Department will collaborate and train teachers to integrate instructional technology in delivering the curriculum. (Including AI and emerging technologies). | Curriculum Team DTC | Ongoing |  |  | Lesson plans and classroom observations will provide evidence. |
| AA-1 | Teachers will be provided opportunities to attend technology related trainings | Academic Dir DTC Principals | August 25 – May 26 | PD Funds KETS General Fund | $5,000 | Documentation of attendance at technology related training and conferences. |
| AI-1 | A needs assessment will be completed to determine the technology professional development needs in order to provide effective technology utilization | Principals | August 25 – May 26 | N/A |  | Teacher survey will be completed. List of identified technology PD needs. |
| AI-1 | Training will be provided on television/interactive displays, miracasting, document cameras and other classroom technologies. Coaches will be available to provide ongoing assistance. | Principals | Ongoing | N/A |  | Lesson Plans Classroom observations Training Sessions |
| AI-1 | New PK-2 elementary teachers will attend training on how to effectively personalize learning with iPads. | Curriculum Tech Team | Ongoing | PILOT Program General Funds | $5,000 | Lesson Plans Coach Meetings New iPad apps purchased, deployed and utilized. |
| AI-1 | Training will be provided on effectively implement instructional software, purchased by the district. | Academic Dir Principals | Ongoing | PD Funds | $5,000 | PD sign in sheets Increase utilization of software as evidenced by usage reports. |
| AA-2 | Attend the KAST conference each year. | DTC Bldg Admin Finance | March 2026 | General Funds | $1250 per | The state’s premier technology and education conference. The goal is to have the technology department, media specialist and other teachers attend. |
| AA-2 | NetAdmin Meetings | DTC Technology | Monthly | Tech Budget | $2,500 | Continue to meet with other regional schools for continued professional development. |

|  | ### Use of Space & Time Future Ready Gear |
| --- | --- |
| KETS GUIDING PRINCIPLE – The personalized learning environment for students requires reimagining the use of school space and time. Virtual instruction, cloud-based learning tools, digital instructional material, digital collaboration, digital workflows, digital efficiencies, and digital relationships, etc., assist in providing the vehicle for everywhere, all-the-time teaching and learning. |  |

Areas of Emphasis: Acceleration Area (AA) /Growth Opportunity Areas (GO)

| AA-1 | Continue to provide guidance, support and resources for districts in the development and application of high-quality online, virtual, and remote learning programs as well as implementation of learning management systems |
| --- | --- |
| GO-1 | Educate and support districts in the implementation and facilitation of digital learning tools and portable/mobile technologies that foster everywhere, all-the-time, always on, and ‘always on you’ access for staff and students |

| KETS AA or GO | Strategy/Action Item | Person(s) Involved | Anticipated Timeframe | Anticipated Funding Source | Anticipated Funding Amount | How will you know this is successful? (including metrics) |
| --- | --- | --- | --- | --- | --- | --- |
| AA-1 | Expand course programs and offerings through a digital online learning platform. | Academic Dir Principals | August 25 – May 26 | General Funds | $15,000 | Increase number of students participating in and successfully completing Edgenuity courses. |
| AI-1 | Increase teacher knowledge and use Google learning applications. | Academic Dir Principals Teachers | Ongoing | N/A |  | An increasing number of teachers will use the Google Suite of tools to collaborate with colleagues and students. An increased number of Google certified staff members. |
| AA-1 | Increase available outdoor WiFi coverage | DTC | Fall 2025 | Erate | $5,000 | Improve available options for our students who have no/limited access at home. This will also improve conditions for our students who participate in athletics to complete school work as needed. |