Strategic Prevention Framework

I³: Inspired, Individualized, Inclusive

May 2025 - June 2025

| Goal: To reduce the onset & progression of substance misuse & its related problems in Bellevue, KY, by supporting the development & delivery of community substance misuse prevention & mental health promotion services. |  |
| --- | --- |
| Objective 1: | By 9/29/2027, reduce the 30-day use of alcohol among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 2: | By 9/29/2027, reduce regular (30-day) vaping use among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 3: | By 9/29/2027, reduce regular (30-day) cigarette smoking among tenth-grade students by 2% each year as measured by annual KIP data. |
| Objective 4: | By 9/29/2027, tenth-grade students reporting serious psychological distress, according to the K6 KIP data, will decrease by 4% each year. |
| Objective 5: | By 9/29/2027, expand collaboration with community prevention partners, demonstrated by support from community prevention partners at least 2x each year in the project’s family prevention education opportunities, documented by photographic evidence & meeting notes. |

| ASSESSMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Accomplishments | Description |  |  |  |  | Align |
| Specification of baseline data: | Teacher-rated SEB screeners were sent to all educators to rate student behavior for grades K-5 and 6-12. The data used within the MTSS framework to proactively detect students who need support. - GES Spring 24-25 Universal Screening - 194 students rated in total - 231 students enrolled - BMHS Spring 24-25 Universal Screening - 91 students rated in total - 293 students enrolled |  |  |  |  | 1-4 |
| Monitoring school needs assessment activities: | Internal Referrals for mental health services. 0 internal referrals for services (GES only) 0 internal referral accepted 0 internal referral in progress 0 students fading out of services 1 internal referral for prevention services 0 internal referral assessments completed for prevention services |  |  |  |  | 1-4 |
| Monitoring schools needs assessment activities: | External Referrals for mental health & prevention services. * 0 student/family external referral 0 student/family Care Solace referrals 0 staff member's Care Solace referrals 0 external resources distributed *Specific BMHS external referral data unknown |  |  |  |  | 1-4 |
| Monitoring schools needs assessment activities: | Grant staff collect & monitor data on all grant lead initiatives. This includes, but is not limited to: |  |  |  |  | 1-5 |
|  | - Outreach & Engagement Data - Participation Data - Outcome Data | - Financial Data - Progress Monitoring |  |  |  |  |
| CAPACITY |  |  |  |  |  |  |
| Accomplishments | Description |  |  |  |  | Align |
| Professional Development: | SPF Grant Staff: - SPTAC Regions III and IV: LISTENING SESSION - Care Solace: Transition Into Summer and Fall - Care Solace: Next Year Planning Call for District Leaders - FY25 School Violence Prevention Program - UK - Trauma-Informed Care - 2025 Adult Allies Learning Series |  | - Navigators of the Commonwealth - UK Center on Trauma and Children - Character Strong: MTSS Game Plan GES Mental Health Professional: - The Body Keeps the Score: Trauma Training - In Progress Ethics and Risk Management in Behavioral Health |  |  | 5 |
| Building internal coalitions: | Grant staff participated in the following monthly coalition/committee meetings: |  |  |  |  | 5 |
|  | - GES Student Care Team Meeting - Mental Health & Prevention Staff & Treatment | - Rae of Sunshine - SMILE Club Meetings |  |  |  |  |
| Building external coalitions: | Grant staff participated in the following monthly coalition/committee meetings: |  |  |  |  | 5 |
|  | - NKY ASAP - SBMH Grant Committee Meeting - TISS Grant Committee Meeting - Youth Summit Planning Committee | - NKISP Steering Committee Meeting - Campbell County Drug-Free Alliance General Meeting - River Cities Drug-Free Coalition Meeting - Adult Allies |  |  |  |  |
| Building external partnerships: | Grant staff meet with the following community agencies: |  |  |  |  | 5 |
|  | - Character Strong - Care Solace - SAMHSA – SPF Grant | - NKCES – Mental Health Roundtable - Perfetti Van Mel – May Mentos Moment Initiative |  |  |  |  |
| Community Conversations: | - Wellcare & CCDFA – Bellevue Story Walk |  |  |  |  | 5 |
| Other infrastructure development: | - Review & update the MH&Prevention Webpage with resources weekly - BISD Resource Mapping review & update support for students, staff, & families |  |  |  |  | 5 |
| PLANNING |  |  |  |  |  |  |
| Accomplishments | Description |  |  |  |  | Align |
| Articulation of a vision for prevention activities: | Grant staff are working toward planning the following: |  |  |  |  | 1-4 |
|  | JUNE/JULY - Trauma Plan Review - Prevention Plan Review - MTSS Process Review - Mental Health & Prevention Services Handbook & Procedure Review - SPF Documentation & Planning - Too Good for Drugs Curriculum with Health Department & North Key - SMILE Club | AUGUST - Back-to-School Bash - Prevention one-pager for all district families FALL - Dinner Table Project 25-26 - Suicide Prevention Awareness - World Mental Health Day - Red Ribbon Week |  |  |  |  |
| IMPLEMENTATION |  |  |  |  |  |  |
| Accomplishments | Description |  |  |  |  | Align |
| Specific community-level interventions being implemented: | Grant staff implemented the following: MAY - Weekly Rae of Sunshine – SMILE Club - 05/01 – Daily Mental Health Social Media Campaign - 05/15 - Mental Health Day of Action Day - 05/15 – GES Field Day |  |  | - 05/15 – SMILE Club Awards - 05/16 – Prevention Newsletter - 05/20 – SPF Grant Advisory Board Meeting - 05/27 – Smile Club - Chalk the Walk JUNE - 06/05 - Character Strong Training |  | 1-4 |
| Implemented policies within organizations to facilitate interventions | Grant staff works with the following grants to create procedures for the BISD mental health & prevention team in response to students' & families' mental health & prevention needs. These align with best practices. - Trauma-Informed Grant - Grant staff continues to work with TISS Grant to revise BISD’s trauma-informed plan & create action steps to ensure the implementation of best practices. - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - School-Based Mental Health Grant - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - Prevention - Grant staff continues to review & revise BISD’s Prevention plan, creating action steps to ensure the implementation of best practices. - Created district tobacco/nicotine-free procedure in response to HB-142; the procedure was added to the Code of Conduct and middle/high school behavior matrix. |  |  |  |  | 4 |
| Specific community-level interventions being implemented: | SBMH Breakdown of time and/or student reached/seen: - Direct: 920 minutes = 15.3 hours - Total Sessions: 23 - Extra Sessions: 3 extra sessions 100 minutes = 1.7 hours - Indirect: 1,080 minutes = 18 hours |  |  |  | SBMH GES Caseload Numbers: - Active cases: 0 - Tier 2 performance: 0 - Internal Referrals: 0 - Total referred, awaiting consent in last month: 0 - Total fading out of services in last month: All - All students have been discharged for the summer. | 4 |
| Specific community-level interventions being implemented: | Prevention Breakdown of time and/or student reached/seen: - Total sessions: 20 - Total direct sessions: 0 - Total extra sessions: 0 - Groups: 0 - Tier 2 performance: 0 |  |  |  | Prevention Caseload Numbers: - Active cases: 0 - Referrals: 0 - Pending: 0 - Tier 2 performance: 0 | 1-4 |
| Developed systems for distributing resources: | 0 lockbox distributed to families - 23 distributed in total |  |  |  | 0 Deterra bags distributed to families - 0 distributed in total - 75 available | 1-3 |
| EVALUATION |  |  |  |  |  |  |
| Accomplishments | Description |  |  |  |  | Align |
| Monitor & evaluate all activities: | Annually evaluating the following data collected: - SEB tiered intervention data (tiers 1, 2, & 3) - SUD related behavior referral data - General behavior referral data - TISS/SBMH data - Mental health services data - Prevention services & prevention tiered intervention data Reviewing and revising procedures/processes to enhance and increase data literacy and collection across the district level. |  |  |  |  | 1-4 |
| Monitor & evaluate all activities: | SPF Outreach Data & Collection - Outcome data collected on the number of event impressions and post-survey information - Data submitted to SPARS - Reviewing new system requirements for data collection and revising current data collection processes 4,142 TOTAL SERVED Direct service or interaction with student, staff, family member, or community member 44,725 TOTAL INTERACTION Indirect, organic reach for social media post 124,971 TOTAL REACH Indirect, count of times content is displayed or viewed across all platforms Recent Implementation: Mindful Moments with Mentos for Mental Health Awareness = 5756 reach, 3135 interactions, 16 served Youth Mental Health Roundtables = 2091 reach, 1011 interactions, 22 served Field Day = 2049 reach, 953 interactions, 303 served DeStress Mondays = 2743 reach, 1658 interactions, 7 served Planet Fitness Free Teen Memberships = 535 reach, 343 interactions, 6 served |  |  |  |  | 1-5 |
| Monitor & evaluate all activities: | Tracking the occurrence of substance use related office referrals at BMHS since the beginning of the grant; overall, we continue to see a decrease in substance use related office referrals. SUD Behavior Office Referral Data |  |  |  |  | 1-3 |
| Monitor & eval activities: | #iCANendthetrend post-surveys completed; waiting to receive data to review from the program. |  |  |  |  | 1-5 |
| Monitor & evaluate all activities: | Creating process to evaluate outreach data and increased prevention messaging data for this academic year to inform decisions and initiatives for the next academic year. |  |  |  |  | 1-5 |
| Grant Reporting: | - 12/31 – SPF eRa Commons Annual Performance Review – Under Review - 01/31 – SPF Continuation Report – Under Review - 04/15 – SPF eRa Commons Carryover – Approved - 05/05 – Annual Target Report – Approved - 05/26 – SPF SPARS Quarter 1 Report – Submitted - 06/23 – SPF SPARS Quarter 2 Report – Due |  |  |  |  | 1-5 |

| SUSTAINABILITY |  |
| --- | --- |
| Sustaining infrastructure: | Continue developing & improving the district's MTSS system & mental health support. |

Data utilization for GES & BMHS unknown

According to Infinite Campus enrollment report

According to Infinite Campus enrollment report

Specific BMHS mental health referral data and internal referral assessments unknown