Board Memo

DATE:  8/14/2025

AGENDA ITEM DETAILS:

School/Department

Yealey Elementary School

Product Vendor or Grant Issuer

Change Order

Product or Grant Name

Change Order #7 for Yealey Elementary School, Renovations, BG 23-207

Date/Term (Beginning and End Dates/Year)

8/14/2025

APPLICABLE BOARD POLICY & STRATEGIC PLAN GOAL:

05.1

Goal 4E: Boone County Schools will provide safe, clean, learner ready facilities. 1. Prioritize the district facilities plan to ensure alignment with the desired state as directed by the strategic plan.

DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT

Change Order #7  – This Change Order includes the following:

Proposal 26 – This change order is to support aid devices, clean, and reinstall into the new grid in each of the back classrooms. Existing air devices were indicated in what appeared to be existing ceiling grid; however, one of the main issues encountered is the ceiling grids not going back in the same location so the contractor had to support and reinstall grilles attached to hard ductwork where the ceilings shifted, up to 6-12 inches in some areas.

ADD $17,336.00

Proposal 40 – Custom door size was required in one location as it was an odd existing size. This cost is only for the upcharge of the custom manufactured one.

ADD $2,381.00

Proposal 42 – Due to higher than anticipated elevations of the electric conduit, it was advised to raise the retaining wall slightly to provide Duke with 3’ of cover.

ADD $19,172.00

Proposal 44 – This change order is for redoing the flooring in the end zones of the Gymnasium, adding new rubber flooring at other miscellaneous small areas, and installing a solid surface panel behind one of the drinking fountains.

ADD $39,668.00

FUNDING FOR PURCHASES AND OTHER REQUESTS:

Total Cost

ADD $78,557.00

New Contract Sum $14,071,967.00

Funding Source

Building Fund

*If more than one funding source, list below along with amount or percent for each source

N/A

IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:

RECOMMENDATION:

I recommend the Board approve Change Order #7 for Yealey Elementary School, Renovations, BG 23-207,

as presented.

CONTACT PERSON: (submitter)

Kim Best, Assistant Superintendent of Operations