Strategic Prevention Framework

I³: Inspired, Individualized, Inclusive

July 2025 - August 2025

| Goal: To reduce the onset & progression of substance misuse & its related problems in Bellevue, KY, by supporting the development & delivery of community substance misuse prevention & mental health promotion services. |  |
| --- | --- |
| Objective 1: | By 9/29/2027, reduce the 30-day use of alcohol among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 2: | By 9/29/2027, reduce regular (30-day) vaping use among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 3: | By 9/29/2027, reduce regular (30-day) cigarette smoking among tenth-grade students by 2% each year as measured by annual KIP data. |
| Objective 4: | By 9/29/2027, tenth-grade students reporting serious psychological distress, according to the K6 KIP data, will decrease by 4% each year. |
| Objective 5: | By 9/29/2027, expand collaboration with community prevention partners, demonstrated by support from community prevention partners at least 2x each year documented by photographic evidence & meeting notes. |

| ASSESSMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Accomplishments | Description |  |  |  | Align |
| Monitoring school needs assessment activities: | Internal Referrals for mental health services. 0 internal referrals for services (GES only) 0 internal referral accepted 0 internal referral in progress 0 students fading out of services 0 internal referral for prevention services 0 internal referral assessments completed for prevention services |  |  |  | 1-4 |
| Monitoring schools needs assessment activities: | External Referrals for mental health & prevention services. * 0 student/family external referral 0 student/family Care Solace referrals 0 staff member's Care Solace referrals 0 external resources distributed *Specific BMHS external referral data unknown |  |  |  | 1-4 |
| Monitoring schools needs assessment activities: | Grant staff collect & monitor data on all grant lead initiatives. This includes, but is not limited to: |  |  |  | 1-5 |
|  | - Outreach & Engagement Data - Participation Data - Outcome Data | - Financial Data - Progress Monitoring |  |  |  |
| CAPACITY |  |  |  |  |  |
| Accomplishments | Description |  |  |  | Align |
| Professional Development: | SPF Grant Staff: - CharacterStrong: Reimagine your Tier 2 Support - Care Solace: The Adaptive Brain: Approaches to Enhance Neuroplasticity for Emotional Health |  | - Vector Training - Girls On the Run: Coaching Certification Mental Health Professional: - n/a |  | 5 |
| Building internal coalitions: | Grant staff participated in the following monthly coalition/committee meetings: |  |  |  | 5 |
|  | - Mental Health & Prevention Staff Meeting | - MTSS Planning Meeting |  |  |  |
| Building external coalitions: | Grant staff participated in the following monthly coalition/committee meetings: |  |  |  | 5 |
|  | - NKY ASAP - SBMH Grant Committee Meeting - TISS Grant Committee Meeting | - NKISP Steering Committee Meeting - Campbell County Drug-Free Alliance General Meeting - River Cities Drug-Free Coalition Meeting |  |  |  |
| Building external partnerships: | Grant staff meet with the following community agencies: |  |  |  | 5 |
|  | - Character Strong - Care Solace - SAMHSA – SPF Grant | - NKCES – Mental Health Roundtable - Sun Behavioral - NorthKey |  |  |  |
| Community Conversations: | - Sun – Mobile Assessor - CharacterStrong Meetings | - Wellcare & CCDFA – Bellevue Story Walk |  |  | 5 |
| Other infrastructure development: | - Review & update the MH&Prevention Webpage with resources weekly - BISD Resource Mapping review & update support for students, staff, & families |  |  |  | 5 |
| PLANNING |  |  |  |  |  |
| Accomplishments | Description |  |  |  | Align |
| Articulation of a vision for prevention activities: | Grant staff are working toward planning the following: AUGUST - Prevention one-pager for all district families SEPTEMBER - Rae of Sunshine - SMILE Club Meetings - Update Trauma Plan - Suicide Prevention & Awareness Initiative - Too Good for Drugs Curriculum with Health Department & North Key - The American Lung Association Prevention Training (Tier 1-3) | FALL - Dinner Table Project 25-26 - Suicide Prevention Awareness - World Mental Health Day - Unity Day - Bullying Prevention - Red Ribbon Week - Advisory Committee Meeting - Prevention Newsletter |  |  |  |
| IMPLEMENTATION |  |  |  |  |  |
| Accomplishments | Description |  |  |  | Align |
| Specific community-level interventions being implemented: | JULY - 7/30 - 6th Grade Orientation - 7/30 - Sun – MOU - 7/31 - MTSS Meeting AUGUST - 8/4 - New to the Vue - 8/5 - Clifton Strengths - 8/6 - Character Strong Training | - 8/7 - Back to school block party - distributing education and information surrounding substance misuse prevention. - 8/9 - CCDFA Prevention in the Park - 8/11 - 25.26 District PD: Educator Wellness by Solution Tree - 8/12 – Opening Day - 8/12 - SPF & Mental Health / Building Leadership Team Calibration Meeting - 8/13 - CCDFA general coalition meeting - 8/13 - River Cities DFA Meeting |  |  | 1-4 |
| Implemented policies within organizations to facilitate interventions | Grant staff works with the following grants to create procedures for the BISD mental health & prevention team in response to students' & families' mental health & prevention needs. These align with best practices. - Trauma-Informed Grant - Grant staff continues to work with TISS Grant to revise BISD’s trauma-informed plan & create action steps to ensure the implementation of best practices. - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - School-Based Mental Health Grant - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - Prevention - Grant staff continues to review & revise BISD’s Prevention plan, creating action steps to ensure the implementation of best practices. - Created district tobacco/nicotine-free procedure in response to HB-142; the procedure was added to the Code of Conduct and middle/high school behavior matrix. |  |  |  | 4 |
| Specific community-level interventions being implemented: | SBMH Breakdown of time and/or student reached/seen: - Direct: 0 - Total Sessions: 0 - Extra Sessions: 0 extra sessions 0 minutes = 0 hours - Indirect: 0 minutes = 0 hours |  |  | SBMH GES Caseload Numbers: - Active cases: 0 - Tier 2 performance: 0 - Internal Referrals: 0 - Total referred, awaiting consent in last month: 0 - Total fading out of services in last month: 0 - All students have been discharged for the summer. | 4 |
| Specific community-level interventions being implemented: | Prevention Breakdown of time and/or student reached/seen: - Total sessions: 0 - Total direct sessions: 0 - Total extra sessions: 0 - Groups: 0 - Tier 2 performance: 0 |  |  | Prevention Caseload Numbers: - Active cases: 0 - Referrals: 0 - Pending: 0 - Tier 2 performance: 0 | 1-4 |
| Developed systems for distributing resources: | 1 lockbox distributed to families - 24 distributed in total |  |  | 0 Deterra bags distributed to families - 0 distributed in total - 75 available | 1-3 |
| EVALUATION |  |  |  |  |  |
| Accomplishments | Description |  |  |  | Align |
| Monitor & evaluate all activities: | Annually evaluating the following data collected/attempted to be collected: - SEB tiered intervention data (tiers 1, 2, & 3) - SUD related behavior referral data - General behavior referral data - TISS/SBMH data - Mental health services data - Prevention services & prevention tiered intervention data Reviewing and revising procedures/processes to enhance and increase data literacy and collection across the district level. |  |  |  | 1-4 |
| Monitor & evaluate all activities: | SPF Outreach Data & Collection - Outcome data collected on the number of event impressions and post-survey information - Data submitted to SPARS - Reviewing new system requirements for data collection and revising current data collection processes 326 TOTAL SERVED Direct service or interaction with student, staff, family member, or community member TBD TOTAL INTERACTION Indirect, organic reach for social media post 326 TOTAL REACH Indirect, count of times content is displayed or viewed across all platforms Recent Implementation: Back to School Bash, approx. 275-300 Prevention in the Park, approx. 50 Lockboxes, 1 Deterra Bags, 0 |  |  |  | 1-5 |
| Monitor & evaluate all activities: | Tracking the occurrence of substance use related office referrals at BMHS since the beginning of the grant; overall, we continue to see a decrease in substance use related office referrals. SUD Behavior Office Referral Data |  |  |  | 1-3 |
| Monitor & eval activities: | #iCANendthetrend post-surveys completed; waiting to receive data to review from the program. |  |  |  | 1-5 |
| Monitor & evaluate all activities: | Creating process to evaluate outreach data and increased prevention messaging data for this academic year to inform decisions and initiatives for the next academic year. |  |  |  | 1-5 |
| Grant Reporting: | - 12/31 – SPF eRa Commons Annual Performance Report – Under Review - 01/31 – SPF Continuation Report – Under Review - 04/15 – SPF eRa Commons Carryover – Approved - 05/05 – Annual Target Report – Approved - 05/26 – SPF SPARS Quarter 1 Report – Submitted - 06/23 – SPF SPARS Quarter 2 Report – Due (unable to complete until Q1 is approved) - 07/23 – SPF SPARS Quarter 3 Report – Due (unable to complete until Q1 is approved) - 10/31 – SPF SPARS Quarter 4 Report – Due |  |  |  | 1-5 |

| SUSTAINABILITY |  |
| --- | --- |
| Sustaining infrastructure: | Continue developing & improving the district's MTSS system & mental health support. |

Specific BMHS mental health referral data and internal referral assessments unknown