Board Memo

DATE:  10/9/2025

AGENDA ITEM DETAILS:

School/Department

Yealey Elementary School

Product Vendor or Grant Issuer

Change Order

Product or Grant Name

Change Order #9 for Yealey Elementary School, Renovations, BG 23-207

Date/Term (Beginning and End Dates/Year)

10/9/2025

APPLICABLE BOARD POLICY & STRATEGIC PLAN GOAL:

05.1

Goal 4E: Boone County Schools will provide safe, clean, learner ready facilities. 1. Prioritize the district facilities plan to ensure alignment with the desired state as directed by the strategic plan.

DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT

Change Order #9 – This Change Order includes the following:

Proposal 49R – The existing sanitary route slope and size was not sufficient for the new plumbing fixtures. This new route was required for proper use of equipment.

ADD $7,335.00

Proposal 50R2 – Providing some additional underground camera work as many of the existing lines were not run according to the original drawings. This work was performed second shift.

ADD $18,678.00

Proposal 52R – The existing master mixing valve was found to be leaking. This replacement was accepted in a meeting.

ADD $4,183.00

Proposal 53 – The building department requested additional firestopping at a condition that was discovered once the ceilings were torn out.

ADD $4,525.00

Proposal 57 – Adjusting some of the room signage as the District desired a couple of the rooms to be used for different functions and some of the signs had to be moved around and reassigned.

ADD $1,080.00

Proposal 58 – A new fan coil unit located in the corridor was found to need a new piping shroud to fully conceal piping.

ADD $953.00

Proposal 60 – Credit is being offered back to the District for allowances that were included in the project and didn’t need to be fully utilized.

DEDUCT $184,756.00

FUNDING FOR PURCHASES AND OTHER REQUESTS:

Total Cost

DECREASE  $148,002.00

New Contract Sum $13,981,645.00

Funding Source

Building Fund

*If more than one funding source, list below along with amount or percent for each source

N/A

IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:

RECOMMENDATION:

I recommend the Board approve Change Order #9 for Yealey Elementary School, Renovations, BG 23-207, as presented.

CONTACT PERSON: (submitter)

Kim Best, Assistant Superintendent of Operations