## THOMAS NELSON
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
1 | Tennis Technologies |  | 31355 | The track is being changed from half-inch red to three-eights black. This is an initial deduction. | 2011-01-18
31 | Badgett |  | 1071 | In various locations bar joists were added and reduced as determined by the structural engineer with a final credit resulting for labor. | 2011-01-18
32 | Vulcraft |  | 1299 | In various locations bar joists were added and reduced as determined by the structural engineer. A credit of $1,299 from Vulcraft for materials is realized. | 2011-01-18
33 | M&J Construction | 3920 |  | The field house foundation must rest on either all rock or all soil. With 75% rock the remaining 25% must be rock filled. | 2011-01-18
35 | Kalkreuth Roofing |  | 664.32 | An exterior wal at TNHS in Phase I becomes an interior wall in Phase II. With wall status change a credit for metal siding was realized. | 2011-01-18
36 | Fox Painting | 714 |  | Labor and materials to Fox Painting to finish wall that was revised from exterior to an interior wall.
38 | Knight's Mechanical | 9161.04 |  | Change order has two separate issues. An additional $2600.00 is charged for rock removal. The second issue is also Knight's Mechanical for pipe installation. Installation of science room piping has been completed now in order to avoid future wall demolition for a cost of $6,561.04. This is a shifting of costs among Phases. | 2011-01-18
17 | Knight's Mechanical | 3830.48 |  | A test well originally drilled was found to be unacceptable and replaced. | 2011-01-18
2 | California Products |  | 5000 | Track specs were changed which resulted in a materials credit of $5000. | 2011-02-15
3 | Stephens Pipe and Steel |  | 4000 | After a review of fence specifications it was determined the quality was in excess of what is needed. | 2011-02-15
4 | Stephens Pipe and Sreel |  | 44839 | Fencing for TNHS was revised from vinyl coated to galvanized. | 2011-02-15
| TOTAL | 17625.52 | 88228.32
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0

## NCHS ATHLETICS
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
2 | Re-Tel Products | 1700 |  | With the change in track surfacing an ultimate deduct of $19,000 will be realized. However, some materials costs will increase. | 2011-01-18
5 | Stephens Pipe and Steel | 4100 |  | Fence specification was changed to light commercial from residential. Upgrade resulted in a materials add of $4100. | 2011-02-15
6 | BCD, Inc. | 1509.36 |  | Blocking was added to softball building to make purlins 2' on center rather than 32" on center. Stability will be increased. | 2011-02-15
| TOTAL | 7309.36 | 0
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0

## F HEIGHTS PHASE 2
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0

## PRESCHOOL
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
| TOTAL | 0 | 0