Peck Flannery Gream Warren Architects, LLC

112 North Main St.		Elizabethtown, Kentucky 42701

Phone: 270-765-2147		Fax: 270-765-2148

Email: lgream@pfgw.org

February 10, 2011

# Ms. Nannette Johnston

Hardin County Board of Education

65 W.A. Jenkins Rd.

Elizabethtown, KY 42701

RE:	February 2011

Hardin County Schools

(Report of Projects in Progress)

Dear Nannette:

Please consider the following as a report on projects which our firm is presently providing Architecture/Engineering services.  I have one action item to present to the board this month.

1.    HEARTLAND ELEMENTARY SCHOOL:  MOREL CONSTRUCTION COMPANY

Building Bid Package “A”:   Remaining work on the Nelson Drive extension change order project consist of seeding and grass growth in the Spring.

2.  NORTH HARDIN HIGH SCHOOL - PHASE 5

Mark McNutt reports that masonry work is to begin Monday, February 14.

3.  JOHN HARDIN HIGH SCHOOL – Baseball/Softball Restroom/Concession Facility

Mark McNutt reports that masonry work to begin shortly.

4.  LINCOLN TRAIL ELEMENTARY SCHOOL – Kitchen Freezer Replacement

Construction has not begun as yet. Construction is to be coordinated for completion by the end of Spring break.

5.  RENOVATIONS OF VINE GROVE ELEMENTARY SCHOOL

ACTION ITEM

I plan to present Design Development documents to the board in the February 17th meeting to include attached schedule.  After the presentation if the board is in agreement then a motion to the effect of…

“I make a motion that the design development documents for the Vine Grove Elementary School Renovation project be approved.”

Please give me a call if you have questions regarding this report.

Sincerely,

Larry Gream

C:      Gary Milby

David Wyatt

Vine Grove Elementary School Renovations

Anticipated schedule

| Date | Item | Comments |
| --- | --- | --- |
| Thursday, February 17, 2011 | Board approval of design development documents. |  |
| Thursday, February 24, 2011 | Board approval of construction documents |  |
| Tuesday, March 1, 2011 | Gary Milby and Larry Gream to meet with David Bryant to review construction documents. |  |
| Thursday, March 10, 2011 | Production plans available from printer for bidders and DOH | Twenty one days before bid date. |
| Monday, March 14, 2011 | Receive DOE approval to advertise |  |
| Thursday, March 17, 2011 | Advertisement date |  |
| Thursday, March 31, 2011 | Bid Date |  |
| Friday, April 1, 2011 | HCS Board approves bids |  |
| Thursday, April 21, 2011 | Date desired for ordering steel trusses | Six weeks prior to start of school |
| Thursday, June 2, 2011 | Last day of school |  |
| Monday, August 1, 2011 | First day of school | Phase 1 to be complete |
| August 1, 2011 to June 2, 2012 |  | Phase 2 work to be performed. |
| June 2, 2012 to August 1, 2012 |  | Phase 3 work to be performed. |

* Adjustment in dates may vary due to snow day, etc.