## Summary
District: | Gallatin County
1. Planning Committee (must include name and position for each member) :
Dorothy Perkins |  | Superintendent
Ray Spahn |  | Assistant Superintendent
Lenny Whalen |  | Deputy Superintendent
Renee Cameron |  | Director of Special Education
Deb Foltz |  | Director of Federal Programs/DAC
Michelle Cruey |  | Middle School Teacher
Jerraine Dailey |  | Asst. Principal Lower/Upper Elementary
Diane Scott |  | Teacher SBDM Upper Elementary
Jackie Mylor |  | Community Member
Roxann Booth |  | High School Principal
Kaycee Thompson |  | High School SBDM Teacher
Jennifer Brown |  | High School SBDM Parent
Gena Noell |  | Classified Lower Elementary
Myra Morgan |  | Minority SBDM Teacher Lower Elementary
Joe Wright |  | Lower Elementary Principal
Sue Beach |  | Classified Middle School
Sonya Giles |  | Board of Education Member
Shaughn Williamson |  | Recent Graduate
Elizabeth Brinker |  | Lower Elementary Parent
Michelle Dameron |  | SBDM Middle School Parent
Deb Brown |  | Principal Upper Elementary
Cindy Baker |  | High School Classified
Jackie Satchwell |  | Upper Elementary Classified
Curt Bieger |  | Principal Middle School
Shannon Stephenson |  | Upper Elementary Parent
2. Reason Previous Corrective Action Improvement Plan did not Provide the Results Needed to Make Adequate Yearly Progress:
The review of our Improvement Plan revealed that we did make progress. However, the analysis of our data revealed that the diagnostic assessment that we are using with our students may be skewing our scores causing an over inflation of these scores as compared to the KCCT. Our district is now in the process of reviewing a more rigorous diagnostic test in math, reading, and other content areas to allow us a more focused and accurate assessment of our students’ abilities and progress. With better diagnostic assessment information we will be better able to change instruction and improve learning for all students. We will also be able to accurately identify students for ESS and RTI, as well as provide information/data to improve learning in all sub-groups. Our plan was monitored throughout the year. Implementation and impact checks were presented to the public at the regular Board of Education meetings. The analysis of our data indicates our Free & Reduced Lunch students and our students with disabilities did not score well on open response questions. There were too many blank responses on open response questions and not enough students scoring at the 3-4 level. Students’ test-taking strategies on open response need improvement. In addition to improving our strategies with open response questions with our students, our data revealed that RTI was not as effective as it could be due to no organized consistent plan for RTI district wide. RTI is addressed in our new Comprehensive District Corrective Action Improvement Plan. There are two other areas that our data analysis has indicated we may need to address – 1. Making sure our available resources meet the needs of our students by reducing class sizes with high needs/high risk students (behaviorally and academically) and 2. Identifying, utilizing, monitoring, and evaluating research based math strategies district wide.

## Data Analysis and Goals
District: | Gallatin County
1. NCLB Report Analysis (include all areas where the district did not may AYP):
The district met 8 out of 13 goals. The district did not meet goals in Math and Reading for Free/Reduced Lunch Students and Student with Disabilities. The district did not meet goals in Graduation Rate. Reading goal was 68.69. Free/Reduced Lunch students scored 57.47 and Students with Disabilities scored 40.31 in reading. The district scored 64.54. Math goal was 59.79. Free/Reuced Lunch students scored 51.99 and Students with Disabilities scored 26.40 in math. The district scored 57.82. Graduation rate goal was 86.75 and the district score was 71.76. The high school improvement plan has addressed the graduation rate indicator.
2. Sources of Data (What other sources of data are you using to determine needs and causes and contributing factors?) Include cognitive and non-cognitive data.
KCCT , NCLB, EXPLORE, PLAN, ACT, Think Link, Learning Checks/Common Assessments, Graduation Rate
3. Data Analysis Summary (What is the data saying?)
Steve Hutton, a former HSE, facilitated data analysis with a committee consisting of district and building level administrators, teachers, SBDM members, and board members. Data indicated the need to increase the % of Free and Reduced lunch students and % of Students with Disabilities scoring at the proficient level in open response questions and multiple choice questions. In reading, non Free and Reduced Lunch students scored 80 percent proficiency. Free and Reduced Lunch students scored 57.47 percent proficiency. Students with Disabilities scored 40.31 percent proficiency. In math, non Free and Reduced Lunch students scored at a level of 70.26 percent proficiency. Free and Reduced students scored at a level of 51.99. Students with Disabilities scored at a level of 26.4 percent.
4. Causes and Contributing Factors (What are the root causes for the low achievement in the district? Include only causes and contributing factors where the district has the ability to make changes. Do not include socio-economic status or poverty levels as a cause or contributing factor.) Need RTI district wide to add uniformity of process, language and forms. Need greater district support in developing a plan after the administering of each universal shared assessment that is consistent throughout the district. Utilization of a common strategy to attack open response questions.
SMART Goals
All goals should directly correlate to a need based on the data analysis and causes and contributing factors.
5. District Reading Goal(s):
The Gallatin County School District will have an AMO of 77 in Reading for all Students with Disabilities based on the 2011 AYP (NCLB) Report scores. Gaps between Students with Disabilities and Students without Disabilities will decrease and be less than 15%. The Gallatin County School District will have an AMO of 77 in reading for all students in Free & Reduced Lunch based on the 2011 AYP (NCLB) Report scores. Gaps between students who qualified for Free & Reduced Lunch and students who did not qualify for Free & Reduced lunch will decrease and be less than 7%.
6. District Math Goal(s):
By May 2011 we will increase the percentage of students scoring proficient or distinguished by 14.92 for a total percentage of 70% as measured by the KCCT. Also by May 2011, the percentage of students scoring novice will decrease by 2.5% for a total of 12.5% of students scoring novice as measured by the KCCT.
7. District Other Academic Indicator Goal(s):
By September 2011, we will increase the graduation rate by 10.56 pts. to meet the state goal of 82.32. Strategies and interventions are addressed in the high school's improvement plan.
8. Instruction
By December 2011 80% of staff will recieve professional development related to improving instructional practices. Based on staff attendance at PD activities.
9. Special Education
We will have an AMO of 77 in reading for all Students with Disabilities and a 70 in math for all Students with Disabilities based on the 2011 NCLB report. Gaps between Students with Disabilities and Students Without Disabilities will decrease and be less than 26 in reading and 43 in math.
10. ESS
We will increase the percentage of ESS students scoring proficient or distinguished by 10 percent in math and reading based on the 2011 IPR Report.
11. Parental Involvement
By May, 2011, parent involvement will increase based on parent survey results indicating number of parent volunteer hours and parent participation in activities and leadership workshops.Parentla involvment last year was 4,849 hours by parents. This year we look to improve that by a total of 6062 for a total percentage increase of 25% for the district.
Note on A25: Spahn, Ray:

## Strategies and PD
District: | Gallatin County
Strategies/Activities that Address the Needs Assessment (based on the causes and contributing factors)
Strategies and Activities must address the fundamental teaching and learning needs of the schools in the district, incorporate strategies that are grounded in scientifically based research, include student learning before school, after school, during the summer or any extension of the school year (as appropriate), provide for high quality professional development and strengthen parental involvement (see Requirements tab for more information).
Need #1: READING - District will increase the % of students scoring in proficient/distinguished and reduce the gaps in disabilites and free and reduced.
Strategy/Activity |  | Impact Measurement/Outcome (How will this strategy/activity address the identified needs? How will effectiveness be evaluated?) | Responsible Person (include position) | Start/End Date (need specific timeframe) | Estimated Cost | Funding Source
The district will implement a diagnostic assessment that closely mirrors the KCCT in scoring. |  | The diagnostic assessment will closely monitor KCCT assessment that will help determine instructional needs of the students | Ray Spahn | 1/1/2011-9/1/2011 | 28000 | General Fund
The district will continue to use a diagnostic evaluation for student academic progress at set intervals at a minimum 3 times during the school year prior to KCCT assessment. Common Assessments/Learning Checks will be used at each grade/subject level to monitor student progress with adjustments being made in instruction as necessary to ensure student success. |  | School will report diagnostic assessment to Assistant Superintendent after each assessment. A plan will then be developed to further improve instruction and learning in gap areas. The effectiveness of the plan will be determined by the number of students meeting the goal of the district and the school. The goal will be 77% proficient/distinguished. | Pam Scudder, Linda Edmondson, Tony Jury | 9/01/2010 - 12/30/2011 | 0 | N/A
Reading coaches will collaborate with fellow teachers to develop and implement activities which help improve student achievement. This will be done by closely monitoring literacy skills. |  | Reading coaches will meet with the building principal after each literacy assessment to determine a plan for improving on the goals that not being met. After the plan is developed, the Reading Coaches will meet with the Assistant Superintendent to discuss goals and plan for improvement. | Pam Scudder, Linda Edmondson, Tony Jury | 9/1/2010 - 12/20/2011 | 0 | N/A
Coaches and reading teachers will research interventions for RTI that are research-based that will be consistent throughout the district that will allow data to be tracked and show signs of reading improvement |  | A research-based assessment will be used throughout the district for Tier III RTI . Common forms will be developed to provide transition between grade levels. A research-based intervention will be identified and implemented. A grade-to-grade conversation plan will be developed to ensure no student is left behind. Common data tools will be used throughout the district. | Curt Bieger | 12/1/2010-12/30/2011 | 5000 | General Fund
District will continue provide reading coaches grades K-8 |  | Improve instructional practice of teachers including the monitoring of new standards and 'Stiggins' implementation. | Deb Foltz | 7/1/2010-12/20/2011 | $68,268 $2,191 | Title I SFSS
Teachers will be provided with Professional Development on the diagnostic assessment that the district selects in order to help identify and improve low-achieving students including sub-groups. |  | Improve instructional practice of teachers as it relates to identify where students are in relation to proficiency and provide teachers with means of helping sub-group populations. | Ray Spahn, Principals | 1/1/2011-9/30/2011 | 500 | PD
Reading coaches and High School Assistant Principal will monitor students entering and exiting RTI Reading to ensure proper placement and monitoring of student progress |  | Students entering RTI will be successful at least 75% of the time in exiting Tier II within appropriate time. Reports will be given monthly to the RTI Director principal who will meet with Assistant Superintendent to determine effectiveness of the program and to make adjustments where needed. | Curt Bieger Ray Spahn, Pam Scudder, Linda Edmondson, Tony Jury | 1/1/2011 - 12/30/2011 | 500 | N/A
Language Arts teacher(3) and one special education teacher will attend the Language Arts content regional meeting on rolling out the standards |  | Provide instructional professional development in the understanding of Stiggins, CHETL, and standard deconstruction. | Ray Spahn | 9/1/2011-6/30/2011 | 500 | PD
Utilize ESS funding before, during, and after school to support students who are not performing at the proficient level in reading. |  | Students who need additional support will be given assistance and support to be proficient. | Deb Foltz & ESS Building Coordinators | 9/1/10-4/15/11 | 24107 | ESS
The District Parent Involvement Coordinator will work closely with the Gallatin County Public Library to have family reading and writing nights |  | To provide parent and students reading together, an important piece to literacy. | Kerri Alexander, YSC. Family Resource Center | 2/1/2011-12/30/2011 | 0 | N/A
Need #2: MATH - District will increase the % of students scoring proficient and distiguished and reduce novice.
Strategy/Activity |  | Impact Measurement/Outcome (How will this strategy/activity address the identified needs? How will effectiveness be evaluated?) | Responsible Person (include position) | Start/End Date (need specific timeframe) | Estimated Cost | Funding Source
Math Teachers (3) will attend the Math content regional meeting on rolling out the new math standards |  | Through the standard deconstruction process, teachers will develop learning targets. This will allow student learning to be more self-directed. Training of staff will occur with collaboration of math coaches | Ray Spahn, Bonnie Humphries, Brenda Alexander, Kim Jones, Tony Jury | 9/1/2011-6/30/2011 | 500 | PD
District will remain in collaboration with monthly meetings with Carroll County on improving math instruction and rolling out standards |  | Through the standard deconstruction process, teachers will develop learning targets. This will allow student learning to be more self-directed. Training of staff will occur with collaboration of math coaches | Dot Perkins | 9/1/2011-9/1/2012 | 500 | PD
District will continue to provide Math coaches grades K-8 |  | Through collaboration, cognitive coaching conversations, and consulting regarding math resources, coaches will aid teachers in planning and reflecting on unit development with new math core content standards | Deb Foltz | 7/1/2010-12/20/2011 | $40,939 $2190 | Title I SFSS
The district will continue to use a diagnostic evaluation of student academic progress at set intervals at a minimum 3 times during the school year prior to KCCT assessment. Common Assessments/Learning Checks will be used at each grade/subject level to monitor student progress with adjustments being made in instruction as necessary to ensure student success |  | School will report diagnostic assessment to Assistant Superintendent after each assessment. A plan will then be developed to further improve instruction and learning in gap areas. The effectiveness of the plan will be determined by the number of students meeting the goal of the district and the school of 70% proficiency. | Ray Spahn | 9/1/2010-9/1/2012 | 0 | N/A
Math coaches and regular content teachers will collaborate with fellow teachers to develop and implement activities which help improve student achievement in gap areas. This will be done by closely monitoring Math skills especially in gap areas |  | Math coach will meet with the building principal after each math assessment to determine a plan for improvement gap areas and to determine the goals that have been met. After the plan is developed, the Math Coach will meet with the Assistant Superintendent to discuss goals and plan for improvement. | Bonnie Humphries Brenda Alexander Kim Jones | 9/1/2010-9/1/2012 | 0 | N/A
Coaches and math teachers will research interventions for RTI that are research-based that will be consistent throughout the district and will allow data to be tracked and show signs of math improvement especially in gap areas by implementing new math standards |  | Professional development will be provided for all teachers regarding data analysis and next steps for instruction. | Bonnie Humphries Brenda Alexander Kim Jones | 1/1/2011-9/1/2012 | 1000 | General fund
The district will purchase math textbooks or resource materials for all students once new standards are finalized and textbook companies have incorporated those standards. Book should provide research-based strategies |  | To improve math instruction and meet the goal of 70% proficiency | Ray Spahn, principals and SBDM councils | 5/30/2011-9/1/2011 | 100750 | General Fund
Need #3: INSTRUCTION - Develop and provide Professional development in instructional practices
Strategy/Activity |  | Impact Measurement/Outcome (How will this strategy/activity address the identified needs? How will effectiveness be evaluated?) | Responsible Person (include position) | Start/End Date (need specific timeframe) | Estimated Cost | Funding Source
The district will continue with the DILT team (District Instructional Leadership Team) that is focused on new standards rollout. Membership includes leaders in the content areas as well as district administrators |  | Improve instructional practices as well as best practices for teachers and administrators | Ray Spahn | 7/1/2010 - 12/30/12 | 27000 | SSFS
Principals will attend KLA (Kentucky Leadership Academy) |  | Improve best practices for principals | Ray Spahn | 7/1/2010-6/30/2011 | 500 | SBDM
District leaders will attend the regional ISLN (Instructional Support Leadership Network) meetings |  | Improve best practices for district administrators | Ray Spahn | 7/1/2010-6/30/2011 | 500 | PD
The district will provide monthly professional development on standards roll out, Stiggins, and CHETL (Characteristics of Highly Effective Teachers) to the District Instructional Leadership team. |  | Improve instructional practices of teachers. In turn, the PLC's will train all teachers. Students will be engaged in learning based on the criteria set in CHETL. Formative assessment will increase. Student-lead conferences will be implemented. | Ray Spahn | 7/1/2010-12/30/2011 | 0 | N/A
An administrators and instructional coaches team will be trained in the instructional rounds. |  | Each school will develop a theory of action and identify a problem of practice. Data will be gathered and analyzed through the instructional rounds process to target the problem of practice and improve student achievement. | Dot Perkins | 10/1/2010-12/20/2010 | 2400 | General Fund
The district leadership team will partner with Carroll County in participating with instructional rounds at various schools within each district |  | Each district will target one school specifically in 2010-2011 and will go district wide in 2011-2012. Gallatin's leadership team will do an instructional rounds visit in Carroll County at one of their schools and Carroll County's leadership team will do an instructional rounds visit in Gallatin County at our targeted school. | Dot Perkins | 1/1/2011-12/30/2011 | 0 | N/A
District leadership team will be trained in Turnaround training; which in turn will provide professional development on this process to all administrators. |  | Our 7 member Turnaround Team will be comprised of the HS Principal, 2 high school teachers, the MS Principal, 2 middle school teachers and the superintendent. They will receive all training that a Highly Skilled Educator receives. They will utilize this training in our district and provide professional development for our DILT. | Dot Perkins | 1/1/2011-12/30/2011 | 8400 | General Fund
District Instructional practices will improve in all areas through the implementation and monitoring of the 'Stiggins' professional development as assessed through district walkthroughs |  | Teachers will display "I can statements" 100% of the time as monitored through district walkthroughs | Ray Spahn | 2/1/2011-12/30/2012 | 0 | N/A
The district will research and provide a diagnotistc assessment that closely relates to KCCT. This plan will also have an RTI component that will help with the improvement of sub-group populations. This will be used district wide grades K-11 |  | This will provide a more accurate method for analyzing data of students for proficiency and sub-group populations. | Ray Spahn | 11/1/2010 6/30/2011 | 30000 | General Fund
An RTI director will be used to develop a district wide policy on RTI implementation of policies and procedures. Need RTI district wide to add uniformity of process language and forms. |  | This will provide a missing link in providing policy and implementation of RTI. This will focus on sub-groups and their needs to meet NCLB | Curt Bieger | 11/1/2010 12/30/2011 | 1200 | General Fund
The RTI director will monitor the implementation of RTI of all groups TIER I, II, III and be responsible for data. The director will meet with the Assistant Superintendent and Director of Special Education to determine if sub-groups are being successful and to develop a plan to address deficiencies for students not being successful. |  | This is to provide dialogue and ensure that all stakeholders are aware and address the needs of sub-group populations. | Curt Bieger | 11/1/2010 12/30/2011 | 0 | N/A
Purchase update and implement Proficiency Quest as a resource for teachers to more quickly and easily streamline their lesson plans in a way that ties in the core content, program of studies, DOK information, embeds ACT related rigor, and also helps give ideas for open response questions. It is expected that all lesson plans will have and list ties to core content and the Program of Studies and include various questioning techniques and provide questions that reference various levels of DOK. |  | Continue to align lesson plans to the new core standards to ensure all plans are aligned and meeting the needs of the students as well as assessing at the appropriate level. | Ray Spahn | 9/1/2011 - on going | 1000 | General Fund
All principals will develop a plan after each common assessment or diagnostic test to improve proficiency and to improve sub-groups in each content area. All plans will be with the goal of 77 in reading and a 70 in math. All principals will meet with the Assistant Superintendent to review the plan after each common assessment to review the plan and provide for assistance if needed in meeting proficiency goal and meeting sub-group populations goal. |  | Reach a goal of 77 in reading and 70 in math. These meetings will take place after each common assessment 3 times a year. Goals will be reported as well as sub-group report and ways to improve. | Ray Spahn | 12/1/2010- 0ngoing | 0 | N/A
District will provide 2 days of Professional Development in June for teachers in math and language arts to finalize student friendly new content standards. This will include a collaboration with the Carroll County Schools. |  | All schools will have a finalized new standards document in reading and math | Ray Spahn | 6/1/2011-6/30/2011 | 7000 | Edujobs funds
Each school will develop and submit an Accountability Plan including a schedule of Learning Checks to be administered and a calendar of events in preparation for the State Testing Schedule. |  | This will provide the district with a timeline of data analysis as well as developing a plan for improvement of sub-groups that do not meet proficiency benchmarks in all content areas. | Ray Spahn | 8/30/2010- 12/30/2011 | 0 | N/A
Need #4: Parental Involvement - District will increase the number parents involved in school acvities and increase the number of parent volunteer hours.
Strategy/Activity |  | Impact Measurement/Outcome (How will this strategy/activity address the identified needs? How will effectiveness be evaluated?) | Responsible Person (include position) | Start/End Date (need specific timeframe) | Estimated Cost | Funding Source
Schools will use a volunteer sign-up at registration and the beginning of the year for parents to help out in schools |  | Increase parental involvement in school if there is a list of volunteers. | Kerri Alexander | 9/1/2010-6/30/2012 | 0 | N/A
Schools will keep an email list and send correspondence to parents regarding academic and other pertinent information related to school functions |  | To keep parents informed of school events | Kerri Alexander | 9/1/2010-6/30/2012 | 0 | N/A
The district will continue to purchase and use the automated phone system that can contact parents automatically and deliver messages as needed at a moment's notice. |  | Provide an avenue to keep parents informed but also a safe school module to inform parents. | Kerri Alexander | 9/1/2010-6/30/2012 | 3600 | Technology
District wide PT3's meeting (Parents, Teachers talking together) will be held quarterly. |  | To provide dialogue between teachers and parents. To help parents get involved in their child's education. | Kerri Alexander | 9/1/2010-6/30/2012 | 0 | N/A
Monthly district parental involvement meetings will be held. |  | To help plan needs of the school in volunteering. | Kerri Alexander | 9/1/2010-6/30/2012 | 0 | N/A
Each school will have at least 2 activities that focus on parental information regarding career and colleges. Whether it deals with saving, curriculum, enrollment etc., it will focus on students and parents being educated in allowing students to make a successful transition to adult life. |  | Provide key information at appropriate grade levels to help parents plan for making a successful transition to adult life. | Kerri Alexander | 9/1/2010-6/30/2012 | 0 | N/A
The district will provide and maintain the Parent Involvement Coordinator. |  | To coordinate and provide assistance to schools in relation to parent involvement. | Kerri Alexander | 9/1/2010-6/30/2012 | 15000 | RLIS
In order to bring parents into schools, the Upper and Lower Elementary will have a Doughnuts with Dad, and Muffins with Mom assemblies. |  | An avenue to bring dads and moms into school and provide them with a successful experience with school. | Kerri Alexander | 9/1/2010-6/30/2012 | 1000 | Title I
There will be a parent night for 2nd, 5th and 8th grade students to ease the transition into their new school. |  | To ease the transition to the next level for both student and parent. | Kerri Alexander | 9/1/2010-6/30/2012 | 0 | N/A
The Middle School will sponsor a Father/Daughter dance and a Mother/Son activity. |  | An avenue to bring dads and moms into school and provide them with a successful experience with school. | Michelle Cruey Jamie Swartzel | 8/1/2010-6/30/2011 | 0 | N/A
By February the Parent Involvement Coordinator will survey parents to determine barriers and to establish new goals for improving parental involvement throughout the schools |  | To provide feedback to better understand the needs of school parents. |  | 2/1/2011-3/1/2011 | 0 | N/A
Need #5: SPECIAL EDUCATION - To reduce the gap between students with disabilities and students without disabilities in reading and math
Strategy/Activity |  | Impact Measurement/Outcome (How will this strategy/activity address the identified needs? How will effectiveness be evaluated?) | Responsible Person (include position) | Start/End Date (need specific timeframe) | Estimated Cost | Funding Source
Special Education teachers will review formative assessment results to determine where the students are in relation to proficiency. |  | Teachers will make a plan to move students closer to proficiency and meet with DoSE to review plan. (85% Reading; 80% Math) | Renee Cameron | 9/1/2010 - 9/1/2011 | 0 | N/A
Adaptive Physical Education Program developed which allows Alternate Portfolio (FMD) teachers additional planning time 2x week specifically dedicated to alternate portfolio development/organization. |  | This allows teachers more planning time for alternate portfolio organization. Effectiveness measured through alt. assessment scores. | Renee Cameron | 9/1/2010-9/1/2011 | 30000 | IDEA
Each Special Education teacher will complete AYP forms monthly to give feedback regarding targeted students (math/reading). |  | This allows each teacher to target specific students (2 reading /2 math) who need additional help. The effectiveness is measured monthly and AYP forms are submitted to building principals and DoSE monthly. | Renee Cameron | 9/1/2010-9/1/2011 | 0 | N/A
DoSE and Special Education teachers will be on the appropriate committees dedicated to standards |  | DoSE, ISLN Special Education teacher attend content meetings. Information is shared through District Instructional Leadership Team meetings. | Renee Cameron | 9/1/2010-6/30/2011 | 0 | N/A
Provide supplemental web-based reading enrichment program for grade K-12 |  | Earobics - K-3 Reach - 4-12 Effectivess is measured through student progress | Renee Cameron | 9/1/2010-9/1/2011 | 0 | N/A
Special Education Team Leader or School Psychologist will attend Tier 3 meetings to ensure smooth transition in case it leads to a referral. |  | Special Education Team Leader or School Psychologist will look for appropriate interventions. | Renee Cameron | 9/1/2010 - 9/1/2011 | 0 | N/A
Need #6: ESS - Increase the % of students scoring proficient and distinguished in math and reading
Strategy/Activity |  | Impact Measurement/Outcome (How will this strategy/activity address the identified needs? How will effectiveness be evaluated?) | Responsible Person (include position) | Start/End Date (need specific timeframe) | Estimated Cost | Funding Source
Utilize daytime waiver to provide additional support and instruction to students who are identified as needing ESS services. |  | Student's classroom progress will be monitored weekly and student ESS goals will be monitored quarterly. Daytime waiver teacher/instructional assistant will assist in identifying targeted students and working on a more individualized basis to increase student achievement and decrease achievement gaps. | Deb Foltz | 9/1/2010-6/30/2011 | 15201 | ESS
School will continue to utilize before- and after-school tutoring |  | Student's classroom progress will be monitored weekly and student ESS goals will be monitored quarterly. Before school/after school teacher/instructional assistant will assist in identifying targeted students and working on a more individualized basis to increase student achievement and decrease achievement gaps. | Deb Foltz | 9/1/2010-6/30/2011 | 8906 | ESS
ESS will be monitored for effectiveness by the ESS coordinator. The ESS coordinator will meet with principals of each building every other month to adjust or develop new plans to ensure the effectiveness of ESS |  | The student's progress will be monitored weekly and targeted student lists will be modified as indicated by student achievement. | Deb Foltz | 9/1/2010-6/30/2011 | 0 | N/A
RTI research-based programs will be used in support of ESS |  | Students will show a better understanding of math and reading based on classroom progress and have fewer failing grades | Deb Foltz | 9/1/2010-6/30/2011 | 0 | N/A

## High Quality Teacher
District: | Gallatin County
Are all teachers in all Title I schools highly qualified (based on the NCLB definition in 1119(a)(2) of No Child Left Behind)? |  |  |  |  | YES | NO
x
1. Documentation of highly qualified status (include date of measure):
In the year 2009-2010, not all teachers were Highly Qualified. This year, 2010-2011, all teachers are believed to be Highly Qualified based on the LEAD report and conversations with principals.
2. Describe the district's plan to ensure the equitable distribution of highly qualified and effective teachers among all schools:
The deputy superintendent attends recruiting fairs across the Commonwealth to recruit Highly Qualified teachers. All principals have been informed to hire Highly Qualified teachers.
3. If all teachers are not highly qualified, list the reasons that are prevent the district from achieving highly qualified status.
The only reason highly qualified teachers would be not employed is being a rural district, highly qualified teachers do not apply even though recruited. The district then tries to provide leadership in getting these teachers certified to become highly qualified.
4. If all teachers are not highly qualified, complete the plan to increase percentage of highly qualified staff.
Strategy/Activity |  | Impact Measurement/Outcome | Responsible Person (include position) | Start/End Date (need specific timeframe) | Estimated Cost | Funding Source
Deputy Superintendent attends recruiting fairs across the state |  | All Teachers are now Highly Qualified | Lenny Whalen | 2011-07-01 | 1000 | PD Travel

## Budget
District: |  | Gallatin County
MUNIS OBJECT CODE | DESCRIPTION |  | AMOUNT FROM 10% PD FOR DISTRICT IMPROVEMENT | AMOUNT FROM DEFERRED | OTHER STATE OR FEDERAL SOURCES
110 | 3.0 FTE Instructional Coaches; 1.0 FTE Certified Teacher |  | 50579 | 0 | 109207
111 |  |  | 0 | 0 | 0
112 | 7.0 FTE Extra Service |  | 0 | 0 | 22000
113 | 12 ESS Teachers |  | 0 | 0 | 27910
120 |  |  | 0 | 0 | 0
130 | 2.0 ESS Instructional Aide; 1.0 Coordinator |  | 0 | 0 | 26398
131 |  |  | 0 | 0 | 0
140 |  |  | 0 | 0 | 0
150 |  |  | 0 | 0 | 0
160 |  |  | 0 | 0 | 0
170 |  |  | 0 | 0 | 0
213 |  |  | 0 | 0 | 0
214 |  |  | 0 | 0 | 0
219 |  |  | 0 | 0 | 0
221 |  |  | 0 | 0 | 0
222 | Medicare Contribution |  | 634 | 0 | 0
231 | KTRS Employer Contribution |  | 6885 | 0 | 0
232 |  |  | 0 | 0 | 0
233 |  |  | 0 | 0 | 0
240 |  |  | 0 | 0 | 0
251 |  |  | 0 | 0 | 0
253 |  |  | 0 | 0 | 0
260 | Workmen's Comp. |  | 180 | 0 | 0
291 |  |  | 0 | 0 | 0
293 |  |  | 0 | 0 | 0
294 | Fed. FD Health Ins. Benefits |  | 7065 | 0 | 0
295 | Fed. FD Life Ins. Benefits |  | 23 | 0 | 0
296 | Fed. FD State Adm. Fee |  | 60 | 0 | 0
297 |  |  | 0 | 0 | 0
322 | Educational Consultant |  | 0 | 100 | 0
335 |  |  | 0 | 0 | 0
338 | Registration Fees |  | 0 | 1000 | 0
342 |  |  | 0 | 0 | 0
345 |  |  | 0 | 0 | 0
349 |  |  | 0 | 0 | 0
432 |  |  | 0 | 0 | 0
433 |  |  | 0 | 0 | 0
434 |  |  | 0 | 0 | 0
435 |  |  | 0 | 0 | 0
439 |  |  | 0 | 0 | 0
441 |  |  | 0 | 0 | 0
442 |  |  | 0 | 0 | 0
443 |  |  | 0 | 0 | 0
444 |  |  | 0 | 0 | 0
450 |  |  | 0 | 0 | 0
511 |  |  | 0 | 0 | 0
513 |  |  | 0 | 0 | 0
514 |  |  | 0 | 0 | 0
519 |  |  | 0 | 0 | 0
521 |  |  | 0 | 0 | 0
522 |  |  | 0 | 0 | 0
524 |  |  | 0 | 0 | 0
529 |  |  | 0 | 0 | 0
531 |  |  | 0 | 0 | 0
532 |  |  | 0 | 0 | 0
533 |  |  | 0 | 0 | 0
541 |  |  | 0 | 0 | 0
542 |  |  | 0 | 0 | 0
552 |  |  | 0 | 0 | 0
553 |  |  | 0 | 0 | 0
561 |  |  | 0 | 0 | 0
580 | Travel |  | 0 | 1691 | 1000
581 |  |  | 0 | 0 | 0
582 |  |  | 0 | 0 | 0
584 |  |  | 0 | 0 | 0
585 |  |  | 0 | 0 | 0
586 |  |  | 0 | 0 | 0
589 |  |  | 0 | 0 | 0
591 |  |  | 0 | 0 | 0
610 | General Supplies |  | 0 | 0 | 2000
616 |  |  | 0 | 0 | 0
617 |  |  | 0 | 0 | 0
626 |  |  | 0 | 0 | 0
627 |  |  | 0 | 0 | 0
629 |  |  | 0 | 0 | 0
641 |  |  | 0 | 0 | 0
642 |  |  | 0 | 0 | 0
643 |  |  | 0 | 0 | 0
644 | Textbooks |  | 0 | 0 | 100750
645 |  |  | 0 | 0 | 0
646 | Tests |  | 0 | 0 | 58000
647 |  |  | 0 | 0 | 0
649 |  |  | 0 | 0 | 0
650 |  |  | 0 | 0 | 0
661 |  |  | 0 | 0 | 0
662 |  |  | 0 | 0 | 0
663 |  |  | 0 | 0 | 0
673 |  |  | 0 | 0 | 0
674 |  |  | 0 | 0 | 0
680 |  |  | 0 | 0 | 0
695 |  |  | 0 | 0 | 0
697 | Materials |  | 0 | 0 | 2000
732 |  |  | 0 | 0 | 0
733 |  |  | 0 | 0 | 0
734 |  |  | 0 | 0 | 0
735 |  |  | 0 | 0 | 0
738 |  |  | 0 | 0 | 0
810 |  |  | 0 | 0 | 0
892 |  |  | 0 | 0 | 0
894 | Instructional Field Trips |  | 0 | 100 | 0
896 |  |  | 0 | 0 | 0
899 |  |  | 0 | 0 | 0
913 |  |  | 0 | 0 | 0
| Totals |  | 65426 | 2891 | 349265

## Timeline
District: | Gallatin County
1. Committee Meeting Dates:
Review Data SBDM and Board Member in Working data Analysis Session October 15, 2010 |  | CDIP November 8, 2010 | 2010-11-17 | 2010-11-29
2. Date Plan Presented to the BOE for Approval:
2010-12-13
3. Date of Revisions to the Corrective Action Improvement Plan including budget amendments:

## Requirements
A district identified for corrective action must develop a corrective action plan no later than three (3) months after the identification (on or before December 20, 2010). The district must consult with parents, school staff, and others in the development of the plan. The purpose of the plans is to improve student achievement throughout the district. The corrective action plan must be submitted to the Kentucky Department of Education for review and approval. the plan must be implemented as soon as possible after approval has been given. The plan must specify how deferred funds will be used.
The plan must:
1. Address the fundamental teaching and learning needs of schools in the district, especially the academic problems of low-achieving students;
2. Define specific measurable achievement goals and targets for each of the student subgroups whose disaggregated results are included on the NCLB Report;
3. Incorporate strategies grounded in scientifically based research that will strengthen instruction in core academic subjects;
4. Include, as appropriate, student learning activities before school, after school, during the summer, and during any extension of the school year;
5. Provide for high quality professional development for instructional staff that focuses primarily on improved instruction;
6. Include strategies to promote effective parental involvement in the schools served by the district; and
7. Include a determination of why the district's previous plan did not bring about increased student academic achievement.
The plan also must:
1. Include objectives to ensure the annual increase of highly qualified teachers; and
2. Provide equitable distribution of highly qualified teachers to ensure that low-income and minority students are not taught at higher rates than other children by non-highly qualified and/or inexperienced teachers.