Board Memo

DATE:  2/12/2026

AGENDA ITEM DETAILS:

School/Department

Boone County Schools

Product Vendor or Grant Issuer

Change Order

Product or Grant Name

Change Order #4 for BCS HVAC 2024, BG 24-145

Date/Term (Beginning and End Dates/Year)

2/12/2026

APPLICABLE BOARD POLICY & STRATEGIC PLAN GOAL:

05.1

Goal 4E: Boone County Schools will provide safe, clean, learner ready facilities. 1. Prioritize the district facilities plan to ensure alignment with the desired state as directed by the strategic plan.

DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT

Change Order #4 – This Change Order includes the following:

Proposal 4(D) – Run data drops from controls cabinets to the nearest IT data racks at ATC, Collins, and Stephens. Data drops are required for connectivity with the Building Automation System and functionality of controls. These connections were not included in the bidding documents, but were requested by the contractor based on their final controls installation.

ADD $5,910.00

Proposal 8R2(H) – Existing piping exposed during removal of existing units revealed excessive corrosion and rust in piping in several locations of Collins Elementary. Some of the piping was in such poor condition that replacements were necessary to ensure successful pipe connections. Isolation ball valves were also added to hydronic lines above ceiling in accessible locations.

ADD $4,264.00

FUNDING FOR PURCHASES AND OTHER REQUESTS:

Total Cost

INCREASE  $10,174.00

New Contract Sum $2,998,612.00

Funding Source

Cash- Building Fund

*If more than one funding source, list below along with amount or percent for each source

N/A

RECOMMENDATION:

I recommend the Board approve Change Order #4 for Boone County Schools, HVAC 2024, BG 24-145 as presented.

CONTACT PERSON: (submitter) Kim Best, Assistant Superintendent of Operations