Strategic Prevention Framework

I³: Inspired, Individualized, Inclusive

January 2026 - February 2026

| Goal: To reduce the onset & progression of substance misuse & its related problems in Bellevue, KY, by supporting the development & delivery of community substance misuse prevention & mental health promotion services. |  |
| --- | --- |
| Objective 1: | By 9/29/2027, reduce the 30-day use of alcohol among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 2: | By 9/29/2027, reduce regular (30-day) vaping use among tenth-grade students by 2% each year as measured by annual KIP survey data. |
| Objective 3: | By 9/29/2027, reduce regular (30-day) cigarette smoking among tenth-grade students by 2% each year as measured by annual KIP data. |
| Objective 4: | By 9/29/2027, tenth-grade students reporting serious psychological distress, according to the K6 KIP data, will decrease by 4% each year. |
| Objective 5: | By 9/29/2027, expand collaboration with community prevention partners, demonstrated by support from community prevention partners at least 2x each year documented by photographic evidence & meeting notes. |

| ASSESSMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Accomplishments | Description |  |  |  |  | Align |
| Monitoring school needs assessment activities: | Internal Referrals for mental health services 14 internal referrals for services (14 GES/0 BMHS) 0 internal referrals accepted 14 internal referrals in progress 0 students fading out of services 1 internal referral for prevention services (0 GES/1 BMHS) 1 internal referral assessments completed for prevention services (0 GES/1 BMHS) 0 student fading out of services (0 GES/0 BMHS) |  |  |  |  | 1-4 |
| Monitoring schools needs assessment activities: | External Referrals for mental health & prevention services. 0 student/family external referral 3 student/family Care Solace referrals (1 GES/2 BMHS) 0 staff member's Care Solace referrals 0 external resources distributed |  |  |  |  | 1-4 |
| Monitoring schools needs assessment activities: | The following universal screeners were completed during the district winter screening window: - Winter BMHS Universal Screening (teacher-rated) - 228 students screened using teacher’s 4th bell rosters - Completed in ERD 01/07/2026 - Winter GES Universal Screening (teacher-rated) - 200 students screened using teacher’s classroom rosters - Completed in ERD 12/17/2025 |  |  |  |  |  |
| Monitoring schools needs assessment activities: | As required by SAMHSA, grant staff systematically collect and monitor comprehensive data on all grant-led initiatives. This includes indirect counts of individuals reached, direct counts of participants served, outreach and engagement efforts, progress monitoring, financial reporting, data sources, demographic and enrollment information, as well as data related to mental health and prevention services and substance use referrals. SPF Grant Data Dashboard |  |  |  |  | 1-5 |
| CAPACITY |  |  |  |  |  |  |
| Accomplishments | Description |  |  |  |  | Align |
| Professional Development: | SPF Grant Staff: - 01/15/2026 - Coaching for Success: Strengthening Prevention at the Community Level - 01/27/2026 – CS: Introducing Intellispark: MTSS Platform - 01/28/2026 – CS: 2026 MTSS Summit - 01/27/2026 - Creating Real Change in Student Mental and Behavioral Health Systems |  | - 01/28/2026 - BH WELL Workshop on Tobacco, Cannabis, and Behavioral Health - 01/30/2026 - Staying Inside the Window of Tolerance - An Advanced Training on STS and Resilience - 02/03/2026 - CS: School Counseling Summit - 02/10/2026 - CS: Winning Hearts and Minds: 3 School Culture Strategies Staff Actually Love |  |  | 5 |
| Building internal coalitions: | Grant staff participated in the following monthly coalition/committee meetings: |  |  |  |  | 5 |
|  | - Mental Health & Prevention Staffing - SPF/BMHS Weekly Initiatives Meeting - SPF Advisory Meeting |  | - GES BASE meeting - GES Referral Meeting - BMHS BASE Meeting - BMHS Referral Meeting |  |  |  |
| Building external coalitions: | Grant staff participated in the following monthly coalition/committee meetings: |  |  |  |  | 5 |
|  | - NKY ASAP - SBMH Grant Committee Meeting - TISS Grant Committee Meeting |  | - Campbell County Drug-Free Alliance General Meeting - River Cities Drug-Free Coalition Meeting |  |  |  |
| Building external partnerships: | Grant staff meet with the following community agencies: |  |  |  |  | 5 |
|  | - Perfetti Van Melle | - Kroger | - Trader Joes |  |  |  |
| Community Conversations: | - NKY Safety Net Alliance | - Prevention Meeting (Youth Summit) | - CADCA Prevention Conference |  |  | 5 |
| Other infrastructure development: | - Review & update the MH&Prevention Webpage with resources weekly - BISD Resource Mapping review & update support for students, staff, & families |  |  |  |  | 5 |
| PLANNING |  |  |  |  |  |  |
| Accomplishments | Description |  |  |  |  | Align |
| Articulation of a vision for prevention activities: | Grant staff are working toward planning the following: FEBRUARY - 02/13 – SMILE Club Valentine's Day - 02/27 – SPF Newsletter #3 MARCH - Vaping Awareness Month - 03/02 - #SEL Action Day - 03/06 - First Friday/ Spill the Tea - 03/12 – 03/20 - Tiger Tracks - 03/26 - Dinner Table Project - 03/23 – Advisory Meeting |  | SPRING - Stress Awareness Month - Alcohol Awareness Month - Take Down Tobacco Day - Mental Health Awareness Month Ongoing Initiatives: - TBD – First Friday: Spill the Tea - SMILE Club (High School Tuesday) - SMILE Club (Middle School Thursday) - TBD - Girls on the Run - GES – Tier 2 Groups |  |  | 1-4 |
| IMPLEMENTATION |  |  |  |  |  |  |
| Accomplishments | Description |  |  |  |  | Align |
| Specific community-level interventions being implemented: | JANUARY - 01/30 – Dinner Table Project #2 - 01/26 – Advisory Meeting - 01/31 – Prevention Conference FEBRUARY - 02/04 – SMILE Club Concession - 02/06 – Pop The Stigma - National Bubble Gum Day |  | Ongoing Initiatives: - SMILE Club (High School Tuesday) - SMILE Club (Middle School Thursday) Tier 2 SEL Weekly Groups - GES - Courage Small Group (Sarah) - GES - Courage Group (Deanna) - GES - Relationship Group (Deanna) |  |  | 1-4 |
|  | Dinner Table Project January 2026 SMILE Club: Club Day Jan 2026 CADCA National Forum 2026 (National Harbor, MD) Pop the Stigma 2026 |  |  |  |  |  |
| Implemented policies within organizations to facilitate interventions | Grant staff works with the following grants to create procedures for the BISD mental health & prevention team in response to students' & families' mental health & prevention needs. These align with the best practices. - Trauma-Informed Grant - Grant staff continues to work with TISS Grant to revise BISD’s trauma-informed plan & create action steps to ensure the implementation of best practices. - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - School-Based Mental Health Grant - Grant staff continues to work with SBMH Grant to review & revise BISD’s Mental Health plan & create action steps to ensure the implementation of best practices. - Prevention - Grant staff continues to review & revise BISD’s Prevention plan, creating action steps to ensure the implementation of best practices. - Created district tobacco/nicotine-free procedure in response to HB-142; the procedure was added to the Code of Conduct and middle/high school behavior matrix. |  |  |  |  | 4 |
| Specific community-level interventions being implemented: | SBMH Breakdown of time and/or student reached/seen: - Direct: 0 - Total Sessions: 0 - Extra Sessions: 0 extra sessions 0 minutes = 0 hours - Indirect: 0 minutes = 0 hours |  |  | SBMH Caseload Numbers: - Active cases: 25 - Referrals: 14 - Pending: 14 - Tier 2 performance: 2 - Tier 2 small groups: 0 - Total fading out of services in last month: 0 |  | 4 |
| Specific community-level interventions being implemented: | Tier 2 Breakdown of time and/or student reached/seen: - Direct: 0 - Indirect: 0 - Total Sessions: 0 - Extra Sessions: 0 extra sessions 0 minutes = 0 hours - Indirect: 0 minutes = 0 hours |  |  | Tier 2 Numbers: - Active: 10 students GES; 19 students BMHS - Referrals: 0 - Pending: 19 - Tier 2 performance: 5 students GES - Tier 2 small groups: 1 group GES, 4 students; 0 groups BMHS - Total fading out of tier 2 in last month: 7 Tier 3 Numbers: - Active: 22 students GES; 0 students BMHS - Referrals: 15 - Pending: 0 - Tier 3 individual: 15 students GES - Tier 3 small groups: 1 group, 7 students GES; 0 groups BMHS - Total fading out of tier 3 in last month: 0 |  | 4 |
| Specific community-level interventions being implemented: | Prevention Breakdown of time and/or student reached/seen: - Total sessions: 3 - Total direct sessions: 3 - Total extra sessions: 0 - Groups: 0 - Tier 2 performance: 0 |  |  | Prevention Caseload Numbers: - Active cases: 1 - Referrals: 0 - Pending: 0 - Tier 2 performance: 0 - Tier 2 small groups: 2 groups GES - Total referred, awaiting consent in last month: 0 - Total fading out of services in last month: 1 |  | 1-4 |
| Developed systems for distributing resources: | 0 lockbox distributed to families - 24 distributed in total |  |  | 0 Deterra bags distributed to families - 0 distributed in total - 75 available |  | 1-3 |
| EVALUATION |  |  |  |  |  |  |
| Accomplishments | Description |  |  |  |  | Align |
| Monitor & evaluate all activities: | As part of our federal grant requirements, staff collect (or attempt to collect) and monitor data to ensure accountability and measure the impact of all grant-funded initiatives. This includes tracking how many students, families, and community members we reach, how many directly participate in programs, and the progress they make over time. We also review financial reports, demographic and enrollment information, and data on mental health services, prevention services and activities, and substance-use related behavior referrals or incidents. Collecting this information allows us to show how funds are used and how these efforts strengthen student well-being and community health. We continue to review and revise procedures/processes to enhance and increase data literacy and collection across the district level. In addition to SPF grant-specific data, we continue to collect and monitor data for the SBMH and TISS grants. We continue to review new system requirements for data collection and revise current data collection processes as needed. |  |  |  |  | 1-4 |
| Monitor & evaluate all activities: | SPF Grant Data Dashboard - Data collected through data sources including demographic information, enrollment data, mental health and prevention service lines data, substance-use related behavior referrals, count of directly served, count of directly reached - Data recorded on SPF Grant Data Dashboard - Data submitted to SPARS each quarter, then annually - Data included in BOE reports monthly - Reviewing new system requirements for data collection and revising current data collection processes |  |  |  |  | 1-5 |
| Monitor & evaluate all activities: | KEY METRICS (SPF Grant Data Dashboard) Indirect: # of individuals reached by grant-funded population-based prevention strategies delivered indirectly to a population. - Total Individuals Reached (Actual), 6572 - Total Individuals Reached (Estimated), 1592 - Total New Individuals Reached (Unduplicated), 2108 Direct: # of individuals served by grant-funded, individual-based prevention strategies or services, delivered directly in a one-on-one setting or group format. - Total Individuals Served, 1952 - Total New Individuals Served, 232 |  |  |  |  | 1-5 |
| Monitor & evaluate all activities: | Care Solace Utilization & Key Performance Indicators Inbound Interactions 23, total 24 Communications Saved 91, total 92 Warm Handoffs 1, total 1 Family-Initiated Cases 1, total 2 Total Unreachable 0, total 0 Declined Services 2, total 3 Total Appointments 0, total 0 Anonymous Searches 1, total 2 |  |  |  |  | 1-5 |
| Grant Reporting: | - 10/31 – Annual Target Report – Approved - 12/28 – Financial Report - Submitted - 12/28 – SPF eRa Commons Annual Performance Report – Submitted - 12/28 – SPF eRa Commons Carryover – Submitted - 02/04 – SPF Continuation Report – Submitted - 01/31 – SPF SPARS Quarter 1 Report – Submitted - 04/30 – SPF SPARS Quarter 2 Report – Due - 07/31 – SPF SPARS Quarter 3 Report – Due - 10/31 – SPF SPARS Quarter 4 Report – Due |  |  |  |  | 1-5 |

| SUSTAINABILITY |  |
| --- | --- |
| Sustaining infrastructure: | Continue developing & improving the district's MTSS system & mental health support. - Building Staff Capacity - Embedding Prevention Into Existing Systems - Institutionalizing Data & Decision-Making - Identifying Future Fundings |