DECISION PAPER

TO: MEMBERS OF THE NELSON COUNTY BOARD OF EDUCATION

FROM: Charles Thompson, Construction and Maintenance Director/DPP

CC: Anthony Orr, Superintendent

SUBJECT: Change Order # 8 for Nelson County High School athletic renovation

DATE: March 15, 2011

ISSUE: Claunch Construction encountered rock while excavating for storm drainage. Yardage removed was confirmed by project manager and paid by contract unit prices. Total cost for rock removal was $3891.60.

RECOMMENDATION: Approval of Change Order #8 for renovation of athletic facilities at Nelson County High School.

RECOMMENDED MOTION: I move that the Nelson County Board of Education approve Change Order #8 for athletic renovation at Nelson County High School.