DECISION PAPER

TO: MEMBERS OF THE NELSON COUNTY BOARD OF EDUCATION

FROM: Charles Thompson, Director of Construction and Maintenance/DPP

CC: Anthony Orr, Superintendent

SUBJECT: Change Order #5 for Thomas Nelson High School (TNHS) Phase 2

DATE: March 15, 2011

ISSUE: Two areas were determined by geotechnical engineer to have unsuitable soil. M and J Construction will under cut both areas and replace with #3 stone. Cost for removal was set by a pre-determined unit price. M and J Construction will provide all labor and materials for a cost of $993.25.

RECOMMENDATION: Approval of Change Order #5 for TNHS.

RECOMMENDED MOTION: I move that the Nelson County Board of Education approve Change Order #5 for TNHS.