THIS IS A DECISION PAPER

TO:

HARDIN COUNTY BOARD OF EDUCATION

FROM:

TERESA MORGAN, Superintendent
DATE:

JUNE 24, 2026
SUBJECT:
APPROVAL OF CHANGE ORDERS 2-12, 03-05, 04-04, 06-06, 07-03, 08-02, 09-08, 11-03, 13-02, 14-02, 15-06, AND 16-03 FOR CENTRAL HARDIN HIGH SCHOOL PHASE 2 PROJECT
ISSUE:  
During renovation, the lintels in Areas H and J were found to be in need of repair.  The following change orders are all related to the repair work necessary to correct the lintels and the additional time needed for those repairs.

Change Order 2-12 is an increase of $67,326.43 and a request for the addition of 51 calendar days for Parco Constructors Group

Change Order 03-05 is an increase of $102,963.28 and a request for the addition of 51 calendar days for Bailey’s Masonry
Change Order 04-04 is an increase of $107,581.71 and a request for the addition of 51 calendar days for SLA Enterprises

Change Order 06-06 is an increase of $6588.99 and a request for the addition of 51 calendar days for TMP Construction
Change Order 07-03 is a request for the addition of 51 calendar days for WR Cole and Associates

Change Order 08-02 is a request for the addition of 51 calendar days for Rosa Mosaic and Tile

Change Order 09-08 is a request for the addition of 51 calendar days for TMP Construction

Change Order 11-03 is a request for the addition of 51 calendar days for Bastin Painting

Change Order 13-02 is a request for the addition of 51 calendar days for Premier Fire and Safety

Change Order 14-02 is a request for the addition of 51 calendar days for Knight’s Mechanical

Change Order 15-06 is a request for the addition of 51 calendar days for Advanced Electrical Systems

Change Order 16-03 is a request for the addition of 51 calendar days for Riverside Paving and Contracting

FACTS:
See attached change orders for details on each request.  

RECOMMENDATION


I RECOMMEND THE BOARD APPROVE CHANGE ORDERS 2-12, 03-05, 04-04, 06-06, 07-03, 08-02, 09-08, 11-03, 13-02, 14-02, 15-06, AND 16-03 FOR CENTRAL HARDIN HIGH SCHOOL PHASE 2 PROJECT
RECOMMENDED MOTION


I MOVE THE HARDIN COUNTY BOARD OF EDUCATION APPROVE CHANGE ORDERS 2-12, 03-05, 04-04, 06-06, 07-03, 08-02, 09-08, 11-03, 13-02, 14-02, 15-06, AND 16-03 FOR CENTRAL HARDIN HIGH SCHOOL PHASE 2 PROJECT
