DECISION PAPER

TO: MEMBERS OF THE NELSON COUNTY BOARD OF EDUCATION

FROM: Charles Thompson, Construction and Maintenance Director/DPP

CC: Anthony Orr, Superintendent

SUBJECT: Change Order #41 for Thomas Nelson High School (TNHS)

DATE: April 19, 2011

ISSUE: Specifications did not require an exposed foundation wall in a classroom to have a finish that matched the other classroom walls. BCD, Inc will provide all materials and labor to insulate and finish with drywall. It was also determined that certain mechanical room areas did not need finished walls as specified. After mechanical room credit is deducted a cost of $2433.25 remains.

RECOMMENDATION: Approval of Change Order #41 for TNHS.

RECOMMENDED MOTION: I move that the Nelson County Board of Education approve Change Order #41 for TNHS.